## RACI
RACI — AI-enabled Population Health & Clinical Performance Command Center
Synthetic, Meridian/PHS-inspired pilot context. Not real confidential PHS data.
Activity | Responsible | Accountable | Consulted | Informed
Charter sign-off | CPHO | Transformation Office | CFO; Plan COO | AI Governance Council
Data foundation (Wave 1) | Chief Data Architect | CDAO | CISO; Chief Privacy Officer | CIO
Clinical model validation | AI Governance Council Chair | CMIO | CMO; Radiology Chair | CISO
Business case & funding | Transformation Office | CFO | CPHO; Plan COO | CEO
Mobilization & handoff | Transformation Office | CPHO | Control Tower | CFO; Plan COO
Value realization (post-handoff) | Control Tower | CPHO | CDAO; Plan COO | CFO

## Mobilization
Mobilization plan
Milestone | Workstream | Wave | Owner
M1 | Stand up governance + data foundation | Wave 1 | Chief Data Architect
M2 | Conformed analytics + lineage | Wave 2 | CDAO
M3 | Gold layer + first models in shadow | Wave 3 | VP Population Health Analytics
M4 | Clinical-safety gate + limited rollout | Wave 3 | AI Governance Council Chair
M5 | Monitoring + FHIR write-back | Wave 4 | Integration Architecture Lead
M6 | Handoff to Control Tower | Wave 4 | Transformation Office Lead