## RAID
SYNTHETIC — LAKESHORE PILOT — NOT REAL DATA — ABARVA AI ¦ RAID Log ¦ context_domain=strategy_initiatives ¦ generated=2026-06-06
id | type | description | severity | owner | status
RAID-001 | Assumption | ERP freeze window conflict | Low | Tomas Halvorsen | Mitigating
RAID-002 | Dependency | Kyriba bank connectivity slippage | High | Sofia Marchetti | Mitigating
RAID-003 | Dependency | Data quality blocks reporting | Low | Liam O'Sullivan | Open
RAID-004 | Dependency | FX volatility | Medium | Tomas Halvorsen | Open
RAID-005 | Assumption | Control owner capacity | High | Priya Natarajan | Mitigating
RAID-006 | Assumption | ERP freeze window conflict | High | Marcus Reilly | Closed
RAID-007 | Assumption | Data quality blocks reporting | High | Aisha Bello | Mitigating
RAID-008 | Issue | Data quality blocks reporting | High | Maria Donnelly | Open
RAID-009 | Assumption | Cyber finding open | Low | Aisha Bello | Open
RAID-010 | Dependency | Cloud cost overrun | High | David Chen | Closed
RAID-011 | Dependency | Control owner capacity | Medium | David Chen | Closed
RAID-012 | Issue | FX volatility | High | Elena Vasquez | Mitigating
RAID-013 | Issue | Data quality blocks reporting | High | Sofia Marchetti | Mitigating
RAID-014 | Issue | FX volatility | Low | Marcus Reilly | Open
RAID-015 | Assumption | Cloud cost overrun | High | David Chen | Open
RAID-016 | Issue | Kyriba bank connectivity slippage | High | Tomas Halvorsen | Closed
RAID-017 | Assumption | Cloud cost overrun | Low | Elena Vasquez | Mitigating
RAID-018 | Risk | Data quality blocks reporting | Medium | Maria Donnelly | Open
RAID-019 | Risk | SI ramp delay | High | David Chen | Closed
RAID-020 | Dependency | Cyber finding open | Medium | Marcus Reilly | Open
RAID-021 | Dependency | Control owner capacity | High | David Chen | Mitigating
RAID-022 | Risk | ERP freeze window conflict | High | Maria Donnelly | Open
RAID-023 | Assumption | Control owner capacity | High | Raymond Okafor | Mitigating
RAID-024 | Issue | Data quality blocks reporting | Medium | David Chen | Open
RAID-025 | Issue | Control owner capacity | High | Aisha Bello | Closed
RAID-026 | Assumption | Data quality blocks reporting | Medium | Aisha Bello | Mitigating
RAID-027 | Issue | Cyber finding open | Medium | Tomas Halvorsen | Mitigating
RAID-028 | Dependency | Cyber finding open | Medium | Priya Natarajan | Closed