## Estimate
ROM estimate — live formulas
Hours = count × unit hours × friction. Weeks = CEILING(hours ÷ (FTE × hours per FTE-week × productive share)). Cost = FTE × weeks × hours per FTE-week × rate. Cached values equal the engine output; money is in cents.
Block | Code | Release | Driver | Count | Unit hours | Friction | Hours | Unit-hours source | Confidence
Use case | UC-1 | R1 | data_source_count | 20 | 36 | 1.18 | 849.6 | [A:DL7] synthetic demo benchmark | medium
Use case | UC-1 | R1 | source_table_count | 80 | 8 | 1.18 | 755.2 | [A:DL8] synthetic demo benchmark | medium
Use case | UC-1 | R1 | standard_data_entity_count | 55 | 28 | 1.18 | 1817.2 | [A:DL9] synthetic demo benchmark | medium
Use case | UC-1 | R1 | dashboard_view_count | 25 | 24 | 1.18 | 708 | [A:DL10] synthetic demo benchmark | medium
Use case | UC-1 | R1 | design_row_count | 200 | 3 | 1.18 | 708 | [A:DL11] synthetic demo benchmark | medium
Use case | UC-1 | R1 | validation_row_count | 255 | 2 | 1.18 | 601.8 | [A:DL12] synthetic demo benchmark | medium
Use case | UC-2 | R2 | data_source_count | 18 | 36 | 1.18 | 764.64 | [A:DL7] synthetic demo benchmark | medium
Use case | UC-2 | R2 | source_table_count | 80 | 8 | 1.18 | 755.2 | [A:DL8] synthetic demo benchmark | medium
Use case | UC-2 | R2 | standard_data_entity_count | 45 | 28 | 1.18 | 1486.8 | [A:DL9] synthetic demo benchmark | medium
Use case | UC-2 | R2 | dashboard_view_count | 30 | 24 | 1.18 | 849.6 | [A:DL10] synthetic demo benchmark | medium
Use case | UC-2 | R2 | design_row_count | 150 | 3 | 1.18 | 531 | [A:DL11] synthetic demo benchmark | medium
Use case | UC-2 | R2 | validation_row_count | 220 | 2 | 1.18 | 519.2 | [A:DL12] synthetic demo benchmark | medium
Foundation | FOUNDATION | shared | data_source_count | 8 | 36 | 1.18 | 339.84 | [A:DL7] synthetic demo benchmark | medium
Foundation | FOUNDATION | shared | source_table_count | 65 | 8 | 1.18 | 613.6 | [A:DL8] synthetic demo benchmark | medium
Foundation | FOUNDATION | shared | standard_data_entity_count | 20 | 28 | 1.18 | 660.8 | [A:DL9] synthetic demo benchmark | medium
Foundation | FOUNDATION | shared | dashboard_view_count | 8 | 24 | 1.18 | 226.56 | [A:DL10] synthetic demo benchmark | medium
Foundation | FOUNDATION | shared | design_row_count | 100 | 3 | 1.18 | 354 | [A:DL11] synthetic demo benchmark | medium
Foundation | FOUNDATION | shared | validation_row_count | 130 | 2 | 1.18 | 306.8 | [A:DL12] synthetic demo benchmark | medium
Block hours | Code | Release |  |  |  |  | Hours
Use case | UC-1 | R1 |  |  |  |  | 5439.8
Use case | UC-2 | R2 |  |  |  |  | 4906.44
Foundation | FOUNDATION | shared |  |  |  |  | 2501.6
Pod pricing — Release R1 | Certified measures release | not_designed
Adjusted hours | 5439.8
Paid hours needed (adjusted ÷ productive share) | 7999.7059
Total FTE | 10
Productive hours per pod-week | 272
Weeks (whole pod-weeks) | 20
Member | Role | Level | FTE | Weeks | Hours per FTE-week | Paid hours | Rate (cents) | Cost (cents) | Role mapping
1 | ROL-024 | LVL-06 | 1 | 20 | 40 | 800 | 40625 | 32500000 | proposed mapping, unapproved
2 | ROL-023 | LVL-07 | 1 | 20 | 40 | 800 | 34938 | 27950400 | proposed mapping, unapproved
3 | ROL-037 | LVL-08 | 6 | 20 | 40 | 4800 | 29250 | 140400000 | proposed mapping, unapproved
4 | ROL-041 | LVL-08 | 2 | 20 | 40 | 1600 | 24750 | 39600000 | proposed mapping, unapproved
Plan cost (cents) | 240450400
Range low multiplier | 0.75
Range high multiplier | 1.5
Low (cents) | 180337800
High (cents) | 360675600
Pod pricing — Release R2 | Workbook certification and retirement release | not_designed
Adjusted hours | 4906.44
Paid hours needed (adjusted ÷ productive share) | 7215.3529
Total FTE | 10
Productive hours per pod-week | 272
Weeks (whole pod-weeks) | 19
Member | Role | Level | FTE | Weeks | Hours per FTE-week | Paid hours | Rate (cents) | Cost (cents) | Role mapping
1 | ROL-024 | LVL-06 | 1 | 19 | 40 | 760 | 40625 | 30875000 | proposed mapping, unapproved
2 | ROL-023 | LVL-07 | 1 | 19 | 40 | 760 | 34938 | 26552880 | proposed mapping, unapproved
3 | ROL-037 | LVL-08 | 6 | 19 | 40 | 4560 | 29250 | 133380000 | proposed mapping, unapproved
4 | ROL-041 | LVL-08 | 2 | 19 | 40 | 1520 | 24750 | 37620000 | proposed mapping, unapproved
Plan cost (cents) | 228427880
Range low multiplier | 0.75
Range high multiplier | 1.5
Low (cents) | 171320910
High (cents) | 342641820
Pod pricing — Foundation FOUNDATION | Shared governed data foundation | not_designed
Adjusted hours | 2501.6
Paid hours needed (adjusted ÷ productive share) | 3678.8235
Total FTE | 10
Productive hours per pod-week | 272
Weeks (whole pod-weeks) | 10
Member | Role | Level | FTE | Weeks | Hours per FTE-week | Paid hours | Rate (cents) | Cost (cents) | Role mapping
1 | ROL-024 | LVL-06 | 1 | 10 | 40 | 400 | 40625 | 16250000 | proposed mapping, unapproved
2 | ROL-023 | LVL-07 | 1 | 10 | 40 | 400 | 34938 | 13975200 | proposed mapping, unapproved
3 | ROL-037 | LVL-08 | 6 | 10 | 40 | 2400 | 29250 | 70200000 | proposed mapping, unapproved
4 | ROL-041 | LVL-08 | 2 | 10 | 40 | 800 | 24750 | 19800000 | proposed mapping, unapproved
Plan cost (cents) | 120225200
Range low multiplier | 0.75
Range high multiplier | 1.5
Low (cents) | 90168900
High (cents) | 180337800

## Component Library
Driver | Label | Unit hours | Source | Confidence
data_source_count | Data sources | 36 | [A:DL7] synthetic demo benchmark | medium
source_table_count | Source tables | 8 | [A:DL8] synthetic demo benchmark | medium
standard_data_entity_count | Standard data entities | 28 | [A:DL9] synthetic demo benchmark | medium
dashboard_view_count | Dashboard views | 24 | [A:DL10] synthetic demo benchmark | medium
design_row_count | Design rows | 3 | [A:DL11] synthetic demo benchmark | medium
validation_row_count | Validation rows | 2 | [A:DL12] synthetic demo benchmark | medium

## Pod & Rates
# | Role | Level | Location | Provider class | FTE | Base rate (cents) | Base rate source | Location multiplier | Location source | Provider multiplier | Provider source | Hourly rate (cents) | Hourly rate ($) | Rate basis | Role mapping | Rate provenance | Notes
1 | ROL-024 | LVL-06 | LOC-DALLAS | SI-T1 | 1 | 40625 | rate_band:ROL-024-LVL-06:indicative_bill_rate [Workforce_Taxonomy_Master.xlsx:Role Rate Card row RC-0069 (Internal Cost Model + Assumptions formula engine, recomputed — see script header)] | 1 | location:LOC-DALLAS:rate_multiplier [Workforce_Taxonomy_Master.xlsx:Geography row 10] | 1 | provider_class:SI-T1/SI-T1 [Workforce_Taxonomy_Master.xlsx:Assumptions row 28] | 40625 | 406.25 | bill_rate | proposed mapping, unapproved | rate = band ROL-024-LVL-06 indicative_bill_rate $406.25 × location LOC-DALLAS 1.00 × provider 1.00 = $406.25/hr | band rate_basis onshore_si_t1_benchmark (benchmark SI-T1, onshore); band confidence medium, approval global_starter_unapproved; location scarcity_multiplier not applied in this increment; planning rates, not approved
2 | ROL-023 | LVL-07 | LOC-DALLAS | SI-T1 | 1 | 34938 | rate_band:ROL-023-LVL-07:indicative_bill_rate [Workforce_Taxonomy_Master.xlsx:Role Rate Card row RC-0066 (Internal Cost Model + Assumptions formula engine, recomputed — see script header)] | 1 | location:LOC-DALLAS:rate_multiplier [Workforce_Taxonomy_Master.xlsx:Geography row 10] | 1 | provider_class:SI-T1/SI-T1 [Workforce_Taxonomy_Master.xlsx:Assumptions row 28] | 34938 | 349.38 | bill_rate | proposed mapping, unapproved | rate = band ROL-023-LVL-07 indicative_bill_rate $349.38 × location LOC-DALLAS 1.00 × provider 1.00 = $349.38/hr | band rate_basis onshore_si_t1_benchmark (benchmark SI-T1, onshore); band confidence medium, approval global_starter_unapproved; location scarcity_multiplier not applied in this increment; planning rates, not approved
3 | ROL-037 | LVL-08 | LOC-DALLAS | SI-T1 | 6 | 29250 | rate_band:ROL-037-LVL-08:indicative_bill_rate [Workforce_Taxonomy_Master.xlsx:Role Rate Card row RC-0105 (Internal Cost Model + Assumptions formula engine, recomputed — see script header)] | 1 | location:LOC-DALLAS:rate_multiplier [Workforce_Taxonomy_Master.xlsx:Geography row 10] | 1 | provider_class:SI-T1/SI-T1 [Workforce_Taxonomy_Master.xlsx:Assumptions row 28] | 29250 | 292.5 | bill_rate | proposed mapping, unapproved | rate = band ROL-037-LVL-08 indicative_bill_rate $292.50 × location LOC-DALLAS 1.00 × provider 1.00 = $292.50/hr | band rate_basis onshore_si_t1_benchmark (benchmark SI-T1, onshore); band confidence medium, approval global_starter_unapproved; location scarcity_multiplier not applied in this increment; planning rates, not approved
4 | ROL-041 | LVL-08 | LOC-DALLAS | SI-T1 | 2 | 24750 | rate_band:ROL-041-LVL-08:indicative_bill_rate [Workforce_Taxonomy_Master.xlsx:Role Rate Card row RC-0116 (Internal Cost Model + Assumptions formula engine, recomputed — see script header)] | 1 | location:LOC-DALLAS:rate_multiplier [Workforce_Taxonomy_Master.xlsx:Geography row 10] | 1 | provider_class:SI-T1/SI-T1 [Workforce_Taxonomy_Master.xlsx:Assumptions row 28] | 24750 | 247.5 | bill_rate | proposed mapping, unapproved | rate = band ROL-041-LVL-08 indicative_bill_rate $247.50 × location LOC-DALLAS 1.00 × provider 1.00 = $247.50/hr | band rate_basis onshore_si_t1_benchmark (benchmark SI-T1, onshore); band confidence medium, approval global_starter_unapproved; location scarcity_multiplier not applied in this increment; planning rates, not approved
Total FTE |  |  |  |  | 10

## Releases
Release | Name | Design status | Use cases | Hours | Weeks | Low (cents) | Plan (cents) | High (cents) | Shares foundation | Standalone plan (cents) | Low ($) | Plan ($) | High ($)
R1 | Certified measures release | not_designed | UC-1 | 5439.8 | 20 | 180337800 | 240450400 | 360675600 | yes | 360675600 | 1803378 | 2404504 | 3606756
R2 | Workbook certification and retirement release | not_designed | UC-2 | 4906.44 | 19 | 171320910 | 228427880 | 342641820 | no | 228427880 | 1713209.1 | 2284278.8 | 3426418.2
FOUNDATION | Shared governed data foundation | foundation (not_designed) | shared by R1 | 2501.6 | 10 | 90168900 | 120225200 | 180337800 | counted once |  | 901689 | 1202252 | 1803378
Total | releases + foundation once |  |  | 12847.84 |  | 441827610 | 589103480 | 883655220 |  |  | 4418276.1 | 5891034.8 | 8836552.2
Sum of standalone plans | foundation counted in every release that shares it | [8 empty] | 589103480
Double count avoided | standalone sum − total | [8 empty] | 0

## Assumptions
Input | Value | Unit | Source | Confidence
Friction factor | 1.18 | multiplier | [A:DL13] synthetic demo benchmark
Productive share | 0.68 | share of paid hours | [A:DL14] synthetic demo benchmark
Hours per FTE-week | 40 | paid hours | [A:DL15] synthetic demo benchmark
Rate basis | bill_rate |  | ROM structure (caller)
Delivery location | LOC-DALLAS |  | cost foundation: pricing_delivery_locations
Provider class | SI-T1 |  | cost foundation: pricing_provider_classes
Pod | ROM-EXPLICIT-POD |  | ROM structure (caller-specified members)
AI productivity credit | none applied |  | ROM policy: no credit unless explicitly requested
Rate approval status | planning rates, not approved |  | Review every role band and delivery mapping before estimate approval
Release R1 design status | not_designed |  | ROM structure (caller)
Release R1 range low | 0.75 | multiplier | ROM policy ROM-NOT-DESIGNED: not-designed band
Release R1 range high | 1.5 | multiplier | ROM policy ROM-NOT-DESIGNED: not-designed band
Release R2 design status | not_designed |  | ROM structure (caller)
Release R2 range low | 0.75 | multiplier | ROM policy ROM-NOT-DESIGNED: not-designed band
Release R2 range high | 1.5 | multiplier | ROM policy ROM-NOT-DESIGNED: not-designed band
Foundation FOUNDATION design status | not_designed |  | ROM structure (caller)
Foundation FOUNDATION range low | 0.75 | multiplier | ROM policy ROM-NOT-DESIGNED: not-designed band
Foundation FOUNDATION range high | 1.5 | multiplier | ROM policy ROM-NOT-DESIGNED: not-designed band
Unit hours: data_source_count | 36 | hours per unit | [A:DL7] synthetic demo benchmark | medium
Unit hours: source_table_count | 8 | hours per unit | [A:DL8] synthetic demo benchmark | medium
Unit hours: standard_data_entity_count | 28 | hours per unit | [A:DL9] synthetic demo benchmark | medium
Unit hours: dashboard_view_count | 24 | hours per unit | [A:DL10] synthetic demo benchmark | medium
Unit hours: design_row_count | 3 | hours per unit | [A:DL11] synthetic demo benchmark | medium
Unit hours: validation_row_count | 2 | hours per unit | [A:DL12] synthetic demo benchmark | medium
Count: UC-1 data_source_count | 20 | units | ROM structure (caller)
Count: UC-1 source_table_count | 80 | units | ROM structure (caller)
Count: UC-1 standard_data_entity_count | 55 | units | ROM structure (caller)
Count: UC-1 dashboard_view_count | 25 | units | ROM structure (caller)
Count: UC-1 design_row_count | 200 | units | ROM structure (caller)
Count: UC-1 validation_row_count | 255 | units | ROM structure (caller)
Count: UC-2 data_source_count | 18 | units | ROM structure (caller)
Count: UC-2 source_table_count | 80 | units | ROM structure (caller)
Count: UC-2 standard_data_entity_count | 45 | units | ROM structure (caller)
Count: UC-2 dashboard_view_count | 30 | units | ROM structure (caller)
Count: UC-2 design_row_count | 150 | units | ROM structure (caller)
Count: UC-2 validation_row_count | 220 | units | ROM structure (caller)
Count: FOUNDATION data_source_count | 8 | units | ROM structure (caller)
Count: FOUNDATION source_table_count | 65 | units | ROM structure (caller)
Count: FOUNDATION standard_data_entity_count | 20 | units | ROM structure (caller)
Count: FOUNDATION dashboard_view_count | 8 | units | ROM structure (caller)
Count: FOUNDATION design_row_count | 100 | units | ROM structure (caller)
Count: FOUNDATION validation_row_count | 130 | units | ROM structure (caller)