ABARVA · MOVES · EXPERT KERNEL

Costed business-case pack

Fraud Detection Enhancement — First Capital Financial

Tenant key first-capital · Move ref first-capital:move:FC-FRAUD-2026

Generated 2026-05-20

The full Design & Plan business case: costed roadmap, value-and-effort profile and the human+agent RACI, in CFO-readable prose.

# Design & Plan — costed business-case pack

Move: Fraud Detection Enhancement (first-capital)

Verdict: SHAPE — do not fund as-is

The critic raised 1 blocker(s) — fund only once they are resolved. Re-shape the Move to close them.

## Investment & return

| Investment (costed roadmap) | $1,587,595 – $2,614,863 (base $1,867,759) |
| --- | --- |
| Net return | -$1,312,023 – $3,334,245 (base $1,244,581) |
| Payback | Not monetisable — the value rests on a baseline seed gap, so the kernel returns no payback rather than a fabricated one. |

## AI-build vs. business-change effort

| AI-build effort | $1,418,512 |
| --- | --- |
| Business-change effort | $449,248 |
| Business-change share | 24% |

Business change is 24% of effort — a credible build-vs-change balance for an AI Move where value depends on people changing how they work.

## Costed roadmap — per-phase investment & value

| Phase | Investment | Cumulative | Annual value unlocked | Foundational |
| --- | --- | --- | --- | --- |
| Phase 0 — Data & model platform foundation | $232,608 | $232,608 | $0 | Yes — enablement only |
| Phase 1 — Detection-model build on card fraud | $1,024,262 | $1,256,869 | $466,851 | No |
| Phase 2 — Disposition automation + process redesign | $117,289 | $1,374,158 | $311,234 | No |
| Phase 3 — Adoption + run | $493,601 | $1,867,759 | $259,362 | No |

## Three-scenario sensitivity

| Scenario | Investment | Net value | Net return | ROI |
| --- | --- | --- | --- | --- |
| Base | $1,867,759 | $3,112,340 | $1,244,581 | Not recorded — seed gap |
| Conservative | $2,614,863 | $1,302,840 | -$1,312,023 | Not recorded — seed gap |
| Upside | $1,587,595 | $4,921,840 | $3,334,245 | Not recorded — seed gap |

What breaks the case: The case breaks if the baseline seed gap is not closed — without the missing unit economics the value range is a proxy, not a forecast.

Downside read: The conservative case cannot be expressed in hard dollars — the value rests on a seed-gap proxy. Close the baseline gap before reading the downside as a number.

## Human + agent RACI — decision rights

The RACI matrix passes every honesty rule — it is governable as drawn.

| Decision | Kind | Accountable | Responsible |
| --- | --- | --- | --- |
| Approve funding for the Move | governance | James Park (CRO, Executive Sponsor) | David Chen (Risk Technology, Program Manager) |
| Select the detection-model architecture | design | Solution Architect | Solution-Design Agent |
| Clear model-risk governance + OCC MRA control review | governance | James Park (CRO, Executive Sponsor) | BSA Officer |
| Execute the detection-model build | delivery | David Chen (Risk Technology, Program Manager) | Build Agent |
| Approve expansion from card to real-time payment fraud | governance | James Park (CRO, Executive Sponsor) | Patricia Huang (CIO) |
| Own the disposition-automation and analyst change plan | delivery | David Chen (Risk Technology, Program Manager) | BSA Officer |

## Surfaced flags — roadmap, RACI, critic

- [critic/blocker] Value cannot be monetised to a hard dollar figure — the gross value range rests on a seed-gap proxy. The CFO will not approve a fabricated return; the case must close the baseline gap first.

- [critic/concern] Downside net value (1302840) is below conservative effort (2614863.13) — in the pessimistic case the Move does not pay back. The CFO will ask what protects the floor.

- [critic/concern] 3 baseline metric(s) are seed gaps (coverage 73%): Fraud-analyst FTE cost basis, Fraud alert volume / cost-per-alert, False-positive operational cost. The case is grounded only on what is recorded.

- [critic/concern] 3 of the top-3 case-moving assumptions stand in for absent tenant data (alert_volume, false_positive_cost, fraud_analyst_fte_cost). Validating these is the highest-leverage next step.

## Named assumptions

Every estimate rests on assumptions; the kernel makes them first-class. The three flagged TOP MOVERS move roughly 80% of the case.

- alert_volume  [TOP MOVER · SEED-GAP PROXY]

Annual fraud alert volume is a modeled proxy (~120k alerts/yr for a bank of First Capital's scale) — used only to express review load.

Owner: David Chen (Risk Technology) · confidence: low · sensitivity impact: high · source: Modeled proxy — seed gap

- false_positive_cost  [TOP MOVER · SEED-GAP PROXY]

Each false-positive investigation costs a modeled ~$18 of analyst time — no per-alert handling cost is seeded.

Owner: James Park (CRO) · confidence: low · sensitivity impact: high · source: Modeled proxy — seed gap

- fraud_analyst_fte_cost  [TOP MOVER · SEED-GAP PROXY]

Fully-loaded fraud-analyst FTE cost is a modeled proxy (~$135k/yr) until First Capital Finance attests a figure.

Owner: Michael Torres (CFO) · confidence: low · sensitivity impact: high · source: Modeled proxy — seed gap (Finance attestation pending)

- fraud_loss_takeout

The detection-model enhancement closes card fraud losses from $2.1M toward the $1.2M peer median — a $0.9M/yr loss-avoidance ceiling.

Owner: James Park (CRO) · confidence: medium · sensitivity impact: high · source: KPI fc-kpi-012 committed target

- realtime_payment_expansion

Expanding fraud detection from card to real-time payment fraud after FedNow go-live roughly doubles the addressable fraud-loss surface.

Owner: Patricia Huang (CIO) · confidence: medium · sensitivity impact: medium · source: Program inventory FC-FRAUD-2026 next-gate

- rate_card

Blended delivery rate card reflects market rates for the ML and risk-technology roles in the estimate.

Owner: Patricia Huang (CIO) · confidence: medium · sensitivity impact: low · source: Benchmark rate card

## Stop / kill criteria

- kill_downside_negative: Net return is negative in the conservative case (-1312023.13). Kill or re-shape if the downside cannot be lifted above zero.

- kill_monetisation_unresolved: The baseline seed gap that blocks monetisation is not closed before the gate — without it the return is unverifiable.

- kill_baseline_unclosed: Baseline coverage stays below acceptable level — 3 seed gap(s) remain unresolved at the gate.

- kill_fraud_loss_floor: Card fraud losses stall above the $1.8M Q1 run-rate — the detection model has stopped converging on the $1.2M peer-median target.

- kill_realtime_expansion_blocked: FedNow go-live slips far enough that the real-time payment fraud expansion — the larger value pool — cannot be reached in horizon.

## What Tower will measure

- Card fraud annualized losses: baseline 2100000 → target 1200000 usd_per_year. Measurable now from the fraud-loss ledger; the current run-rate is $1.8M (fc-kpi-022). The committed loss-avoidance target.

- AML automated disposition rate: baseline 34 → target 60 percent. Measurable from the case-management system. Carry the caveat that this metric is shared with the adjacent FC-AML-2026 program.

- SAR filings past deadline: baseline 8 → target 0 percent. Measurable from the BSA/AML filing log; no gap.

- Fraud-analyst FTE cost basis: baseline Not recorded — seed gap → target Not recorded — seed gap usd_per_fte_per_year. SEED GAP — manual-review-cost takeout cannot be verified in dollars until First Capital Finance attests a fully-loaded fraud-analyst FTE cost. Tower cannot confirm that value component before then.

Every figure in this document is produced by the Moves Expert Kernel from the tenant’s audited substrate. Absent data is declared a seed gap, never invented. Effort rests on a researched planning rate card — a market range, not a quote. Generated by AbarVa · Moves.