ABARVA · MOVES · EXPERT KERNEL

Mobilize & go-decision packet

Fraud Detection Enhancement — First Capital Financial

Tenant key first-capital · Move ref first-capital:move:FC-FRAUD-2026

Generated 2026-05-20

The mobilization plan, adoption & change approach, the value-measurement model handed to Tower and the go-decision pack.

# Mobilize & Handoff — adoption, measurement, go-decision

Move: Fraud Detection Enhancement (first-capital)

Go-decision: NO GO

No-go: 2 Mobilize kill trigger(s) fired (measurement_unwired, business_case_blocker_open). The Move is not ready to leave Moves. See the fix-conditions for what must change before it is reconsidered.

## Mobilize readiness

| Owned (named operating-model owner) | Yes |
| --- | --- |
| Adoptable (change approach supports the curve) | Yes |
| Measurable (value loop closes to Tower) | NO |
| Operating-model owner | David Chen (Risk Technology, Program Manager) |
| Overall change load | high |
| Adoption confidence | 0.6 |
| Hypercare window | 6 week(s) |

## Fired kill triggers — verbatim

- measurement_unwired: 1 committed value metric(s) cannot be wired to a recorded baseline: Fraud-analyst FTE cost basis.

Fix-condition: Revisit when every committed metric is wired to a Discover baseline value or an owned, dated plan to capture one.

- business_case_blocker_open: The business-case critic has 1 open blocker(s): cfo_monetisation_blocked.

Fix-condition: Revisit when the business-case critic reports no open blocker.

## Conditions to clear

- measurement_unwired: Revisit when every committed metric is wired to a Discover baseline value or an owned, dated plan to capture one.

- business_case_blocker_open: Revisit when the business-case critic reports no open blocker.

## Adoption & change approach — seven dimensions

| Dimension | Magnitude | Recommendation | Owner |
| --- | --- | --- | --- |
| impacted_roles | high | Three roles change; the fraud-analyst role changes most. Stage the rollout by alert segment, leading with card fraud. | Program Manager |
| process_variance | high | Disposition logic varies case handling materially; the process-redesign workstream must land before the change rollout (it is budgeted in the Design & Plan estimate). | Program Manager |
| training_load | moderate | Role-based training: a model-output-interpretation curriculum for analysts, a lighter curriculum for managers and BSA staff. | Enablement Lead |
| incentive_change | moderate | Re-point analyst performance metrics away from raw case throughput toward disposition accuracy and confirmed-fraud catch rate. | Fraud Operations |
| manager_adoption | high | Manager reinforcement is the highest-risk layer. A dedicated manager-enablement track with explicit reinforcement in the hypercare window. | Fraud Operations |
| communications | moderate | Address the analyst narrative directly — the model triages and prioritises; it augments analyst judgement under model-risk governance, it does not replace the analyst. | Program Manager |
| hypercare | moderate | A 6-week hypercare window with elevated model-monitoring support and a daily disposition-quality review; exit when the automated disposition rate and catch rate hold for two consecutive weeks. | Program Manager |

## Impacted roles

| Role | Headcount | Change | What changes |
| --- | --- | --- | --- |
| Fraud analyst | Not recorded — seed gap | high | Analysts move from manually dispositioning a high-false-positive alert queue to reviewing model-prioritised, auto-dispositioned cases. |
| Fraud operations manager | Not recorded — seed gap | moderate | Managers coach to the new disposition-automation metrics and monitor the model-decision queue. |
| BSA / AML compliance officer | Not recorded — seed gap | moderate | SAR filing workflow re-baselined around the faster, model-prioritised case flow under continued OCC MRA scrutiny. |

## Adoption risks — surfaced

- [concern] adoption_manager_layer_heavy: Manager adoption is a high-magnitude change. Adoption fails at the manager layer more than anywhere else — manager reinforcement must be explicitly resourced, not assumed.

- [note] adoption_headcount_gap_fraud_analyst: Impacted headcount for 'Fraud analyst' is not recorded — training load and communications scale cannot be sized precisely.

- [note] adoption_headcount_gap_fraud_operations_manager: Impacted headcount for 'Fraud operations manager' is not recorded — training load and communications scale cannot be sized precisely.

- [note] adoption_headcount_gap_bsa_aml_compliance_officer: Impacted headcount for 'BSA / AML compliance officer' is not recorded — training load and communications scale cannot be sized precisely.

- [note] adoption_seed_gap_impacted_roles: The 'Impacted roles' assessment rests on a benchmark proxy / seed gap, not tenant data — validate it before the gate.

- [note] adoption_seed_gap_training_load: The 'Training load' assessment rests on a benchmark proxy / seed gap, not tenant data — validate it before the gate.

## Value-measurement model — handed to Tower

3 of 4 metric(s) wired to a recorded baseline (coverage 75%). Value loop closes: NO.

| Metric | Baseline | Target | Cadence | Owner |
| --- | --- | --- | --- | --- |
| Card fraud annualized losses | 2100000 | 1200000 | monthly | CRO |
| AML automated disposition rate | 34 | 60 | monthly | Fraud Operations |
| SAR filings past deadline | 8 | 0 | monthly | BSA Officer |
| Fraud-analyst FTE cost basis | Not recorded — seed gap | Not recorded — seed gap | quarterly | CFO |

## Critic findings — surfaced, not hidden

- [blocker / cfo] cfo_monetisation_blocked: Value cannot be monetised to a hard dollar figure — the gross value range rests on a seed-gap proxy. The CFO will not approve a fabricated return; the case must close the baseline gap first.

- [concern / cfo] cfo_downside_underwater: Downside net value (1302840) is below conservative effort (2614863.13) — in the pessimistic case the Move does not pay back. The CFO will ask what protects the floor.

- [concern / data] data_baseline_seed_gaps: 3 baseline metric(s) are seed gaps (coverage 73%): Fraud-analyst FTE cost basis, Fraud alert volume / cost-per-alert, False-positive operational cost. The case is grounded only on what is recorded.

- [concern / data] data_top_mover_is_proxy: 3 of the top-3 case-moving assumptions stand in for absent tenant data (alert_volume, false_positive_cost, fraud_analyst_fte_cost). Validating these is the highest-leverage next step.

Every figure in this document is produced by the Moves Expert Kernel from the tenant’s audited substrate. Absent data is declared a seed gap, never invented. Effort rests on a researched planning rate card — a market range, not a quote. Generated by AbarVa · Moves.