## Risk + Compliance Register
risk_id | risk_title | risk_type | control_id | policy_id | owner | severity | likelihood | status | linked_ci_ids | linked_vendor_ids | remediation_due_date | evidence_required | source_system | source_record_id | source_owner | last_validated_date | confidence | evidence_usable | notes_gaps
RISK-MH-0001 | Epic AMS transition knowledge gap 001 | Compliance | CTRL-MH-002 | POL-MH-002 | CDAO | Medium | Possible | Mitigating | CI-APP-EPIC-CABOODLE¦CI-HCM-WORKDAY | VEN-AMS-EPIC¦VEN-WORKDAY | 2026-05-02 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0001 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0002 | Data analytics AMS scope ambiguity 002 | Financial | CTRL-MH-003 | POL-MH-003 | CTO | Critical | Unlikely | Accepted with controls | CI-APP-EPIC-CLARITY¦CI-LEGACY-VM-003 | VEN-AMS-DATA¦VEN-COLLIBRA | 2026-05-03 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0002 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0003 | PHI control evidence missing after migration 003 | Clinical Safety | CTRL-MH-004 | POL-MH-004 | CFO | High | Likely | Open | CI-APP-EPIC-MYCHART¦CI-LEGACY-VM-012 | VEN-AWS¦VEN-MH-016 | 2026-05-04 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0003 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0004 | Cloud run cost exceeds baseline 004 | Sourcing | CTRL-MH-005 | POL-MH-005 | AI Governance Council | Medium | Possible | Mitigating | CI-APP-EPIC-RESOLUTE-HB¦CI-LEGACY-VM-021 | VEN-ORACLE¦VEN-MH-021 | 2026-05-05 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0004 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0005 | Integration backlog affects clinical continuity 005 | Operational | CTRL-MH-006 | POL-MH-006 | CISO | Critical | Unlikely | Accepted with controls | CI-APP-EPIC-RESOLUTE-PB¦CI-LEGACY-VM-030 | VEN-WORKDAY¦VEN-MH-026 | 2026-05-06 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0005 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0006 | CDAO stewardship capacity constraint 006 | Compliance | CTRL-MH-007 | POL-MH-007 | CDAO | High | Likely | Open | CI-INT-RHAPSODY¦CI-LEGACY-VM-039 | VEN-SNOW¦VEN-MH-031 | 2026-05-07 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0006 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0007 | BAA chain incomplete for AI workflow 007 | Financial | CTRL-MH-008 | POL-MH-008 | CTO | Medium | Possible | Mitigating | CI-API-FHIR-GATEWAY¦CI-LEGACY-VM-048 | VEN-DATABRICKS¦VEN-MH-036 | 2026-05-08 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0007 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0008 | AWS-hosted workload not modernized 008 | Clinical Safety | CTRL-MH-009 | POL-MH-009 | CFO | Critical | Unlikely | Accepted with controls | CI-ERP-ORACLE¦CI-LEGACY-VM-057 | VEN-MICROSOFT¦VEN-MH-041 | 2026-05-09 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0008 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0009 | Epic AMS transition knowledge gap 009 | Sourcing | CTRL-MH-010 | POL-MH-010 | AI Governance Council | High | Likely | Open | CI-HCM-WORKDAY¦CI-LEGACY-VM-066 | VEN-RHAPSODY¦VEN-MH-046 | 2026-05-10 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0009 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0010 | Data analytics AMS scope ambiguity 010 | Operational | CTRL-MH-011 | POL-MH-011 | CISO | Medium | Possible | Mitigating | CI-ITSM-SERVICENOW¦CI-LEGACY-VM-075 | VEN-COLLIBRA¦VEN-MH-051 | 2026-05-11 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0010 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0011 | PHI control evidence missing after migration 011 | Compliance | CTRL-MH-012 | POL-MH-012 | CDAO | Critical | Unlikely | Accepted with controls | CI-DATA-DATABRICKS¦CI-LEGACY-VM-084 | VEN-CROWDSTRIKE¦VEN-MH-056 | 2026-05-12 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0011 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0012 | Cloud run cost exceeds baseline 012 | Financial | CTRL-MH-013 | POL-MH-013 | CTO | High | Likely | Open | CI-DATA-COLLIBRA¦CI-LEGACY-VM-093 | VEN-MH-013¦VEN-MH-061 | 2026-05-13 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0012 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0013 | Integration backlog affects clinical continuity 013 | Clinical Safety | CTRL-MH-014 | POL-MH-014 | CFO | Medium | Possible | Mitigating | CI-IAM-ENTRA¦CI-LEGACY-VM-102 | VEN-MH-014¦VEN-MH-066 | 2026-05-14 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0013 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0014 | CDAO stewardship capacity constraint 014 | Sourcing | CTRL-MH-015 | POL-MH-015 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-SEC-CROWDSTRIKE¦CI-LEGACY-VM-111 | VEN-MH-015¦VEN-MH-071 | 2026-05-15 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0014 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0015 | BAA chain incomplete for AI workflow 015 | Operational | CTRL-MH-016 | POL-MH-016 | CISO | High | Likely | Open | CI-AWS-LANDING-ZONE¦CI-LEGACY-VM-120 | VEN-MH-016¦VEN-MH-076 | 2026-05-16 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0015 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0016 | AWS-hosted workload not modernized 016 | Compliance | CTRL-MH-017 | POL-MH-017 | CDAO | Medium | Possible | Mitigating | CI-LEGACY-VM-001¦CI-LEGACY-VM-129 | VEN-MH-017¦VEN-MH-081 | 2026-05-17 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0016 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0017 | Epic AMS transition knowledge gap 017 | Financial | CTRL-MH-018 | POL-MH-018 | CTO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-002¦CI-SVC-138 | VEN-MH-018¦VEN-MH-086 | 2026-05-18 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0017 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0018 | Data analytics AMS scope ambiguity 018 | Clinical Safety | CTRL-MH-019 | POL-MH-019 | CFO | High | Likely | Open | CI-LEGACY-VM-003¦CI-SVC-147 | VEN-MH-019¦VEN-MH-091 | 2026-05-19 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0018 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0019 | PHI control evidence missing after migration 019 | Sourcing | CTRL-MH-020 | POL-MH-020 | AI Governance Council | Medium | Possible | Mitigating | CI-LEGACY-VM-004¦CI-SVC-156 | VEN-MH-020¦VEN-MH-096 | 2026-05-20 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0019 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0020 | Cloud run cost exceeds baseline 020 | Operational | CTRL-MH-021 | POL-MH-021 | CISO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-005¦CI-SVC-165 | VEN-MH-021¦VEN-MH-101 | 2026-05-21 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0020 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0021 | Integration backlog affects clinical continuity 021 | Compliance | CTRL-MH-022 | POL-MH-022 | CDAO | High | Likely | Open | CI-LEGACY-VM-006¦CI-SVC-174 | VEN-MH-022¦VEN-MH-106 | 2026-05-22 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0021 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0022 | CDAO stewardship capacity constraint 022 | Financial | CTRL-MH-023 | POL-MH-023 | CTO | Medium | Possible | Mitigating | CI-LEGACY-VM-007¦CI-SVC-183 | VEN-MH-023¦VEN-EPIC | 2026-05-23 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0022 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0023 | BAA chain incomplete for AI workflow 023 | Clinical Safety | CTRL-MH-024 | POL-MH-024 | CFO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-008¦CI-SVC-192 | VEN-MH-024¦VEN-WORKDAY | 2026-05-24 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0023 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0024 | AWS-hosted workload not modernized 024 | Sourcing | CTRL-MH-025 | POL-MH-025 | AI Governance Council | High | Likely | Open | CI-LEGACY-VM-009¦CI-SVC-201 | VEN-MH-025¦VEN-COLLIBRA | 2026-05-25 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0024 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0025 | Epic AMS transition knowledge gap 025 | Operational | CTRL-MH-026 | POL-MH-026 | CISO | Medium | Possible | Mitigating | CI-LEGACY-VM-010¦CI-SVC-210 | VEN-MH-026¦VEN-MH-016 | 2026-05-26 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0025 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0026 | Data analytics AMS scope ambiguity 026 | Compliance | CTRL-MH-027 | POL-MH-027 | CDAO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-011¦CI-SVC-219 | VEN-MH-027¦VEN-MH-021 | 2026-05-27 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0026 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0027 | PHI control evidence missing after migration 027 | Financial | CTRL-MH-028 | POL-MH-028 | CTO | High | Likely | Open | CI-LEGACY-VM-012¦CI-APP-EPIC-MYCHART | VEN-MH-028¦VEN-MH-026 | 2026-05-28 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0027 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0028 | Cloud run cost exceeds baseline 028 | Clinical Safety | CTRL-MH-029 | POL-MH-029 | CFO | Medium | Possible | Mitigating | CI-LEGACY-VM-013¦CI-DATA-COLLIBRA | VEN-MH-029¦VEN-MH-031 | 2026-05-29 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0028 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0029 | Integration backlog affects clinical continuity 029 | Sourcing | CTRL-MH-030 | POL-MH-030 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-014¦CI-LEGACY-VM-006 | VEN-MH-030¦VEN-MH-036 | 2026-05-30 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0029 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0030 | CDAO stewardship capacity constraint 030 | Operational | CTRL-MH-031 | POL-MH-031 | CISO | High | Likely | Open | CI-LEGACY-VM-015¦CI-LEGACY-VM-015 | VEN-MH-031¦VEN-MH-041 | 2026-05-31 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0030 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0031 | BAA chain incomplete for AI workflow 031 | Compliance | CTRL-MH-032 | POL-MH-032 | CDAO | Medium | Possible | Mitigating | CI-LEGACY-VM-016¦CI-LEGACY-VM-024 | VEN-MH-032¦VEN-MH-046 | 2026-06-01 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0031 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0032 | AWS-hosted workload not modernized 032 | Financial | CTRL-MH-033 | POL-MH-033 | CTO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-017¦CI-LEGACY-VM-033 | VEN-MH-033¦VEN-MH-051 | 2026-06-02 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0032 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0033 | Epic AMS transition knowledge gap 033 | Clinical Safety | CTRL-MH-034 | POL-MH-034 | CFO | High | Likely | Open | CI-LEGACY-VM-018¦CI-LEGACY-VM-042 | VEN-MH-034¦VEN-MH-056 | 2026-06-03 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0033 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0034 | Data analytics AMS scope ambiguity 034 | Sourcing | CTRL-MH-035 | POL-MH-035 | AI Governance Council | Medium | Possible | Mitigating | CI-LEGACY-VM-019¦CI-LEGACY-VM-051 | VEN-MH-035¦VEN-MH-061 | 2026-06-04 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0034 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0035 | PHI control evidence missing after migration 035 | Operational | CTRL-MH-036 | POL-MH-036 | CISO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-020¦CI-LEGACY-VM-060 | VEN-MH-036¦VEN-MH-066 | 2026-06-05 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0035 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0036 | Cloud run cost exceeds baseline 036 | Compliance | CTRL-MH-037 | POL-MH-037 | CDAO | High | Likely | Open | CI-LEGACY-VM-021¦CI-LEGACY-VM-069 | VEN-MH-037¦VEN-MH-071 | 2026-06-06 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0036 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0037 | Integration backlog affects clinical continuity 037 | Financial | CTRL-MH-038 | POL-MH-038 | CTO | Medium | Possible | Mitigating | CI-LEGACY-VM-022¦CI-LEGACY-VM-078 | VEN-MH-038¦VEN-MH-076 | 2026-06-07 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0037 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0038 | CDAO stewardship capacity constraint 038 | Clinical Safety | CTRL-MH-039 | POL-MH-039 | CFO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-023¦CI-LEGACY-VM-087 | VEN-MH-039¦VEN-MH-081 | 2026-06-08 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0038 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0039 | BAA chain incomplete for AI workflow 039 | Sourcing | CTRL-MH-040 | POL-MH-040 | AI Governance Council | High | Likely | Open | CI-LEGACY-VM-024¦CI-LEGACY-VM-096 | VEN-MH-040¦VEN-MH-086 | 2026-06-09 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0039 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0040 | AWS-hosted workload not modernized 040 | Operational | CTRL-MH-041 | POL-MH-041 | CISO | Medium | Possible | Mitigating | CI-LEGACY-VM-025¦CI-LEGACY-VM-105 | VEN-MH-041¦VEN-MH-091 | 2026-06-10 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0040 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0041 | Epic AMS transition knowledge gap 041 | Compliance | CTRL-MH-042 | POL-MH-042 | CDAO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-026¦CI-LEGACY-VM-114 | VEN-MH-042¦VEN-MH-096 | 2026-06-11 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0041 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0042 | Data analytics AMS scope ambiguity 042 | Financial | CTRL-MH-043 | POL-MH-043 | CTO | High | Likely | Open | CI-LEGACY-VM-027¦CI-LEGACY-VM-123 | VEN-MH-043¦VEN-MH-101 | 2026-06-12 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0042 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0043 | PHI control evidence missing after migration 043 | Clinical Safety | CTRL-MH-044 | POL-MH-044 | CFO | Medium | Possible | Mitigating | CI-LEGACY-VM-028¦CI-SVC-132 | VEN-MH-044¦VEN-MH-106 | 2026-06-13 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0043 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0044 | Cloud run cost exceeds baseline 044 | Sourcing | CTRL-MH-045 | POL-MH-045 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-029¦CI-SVC-141 | VEN-MH-045¦VEN-EPIC | 2026-06-14 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0044 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0045 | Integration backlog affects clinical continuity 045 | Operational | CTRL-MH-046 | POL-MH-046 | CISO | High | Likely | Open | CI-LEGACY-VM-030¦CI-SVC-150 | VEN-MH-046¦VEN-WORKDAY | 2026-06-15 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0045 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0046 | CDAO stewardship capacity constraint 046 | Compliance | CTRL-MH-047 | POL-MH-047 | CDAO | Medium | Possible | Mitigating | CI-LEGACY-VM-031¦CI-SVC-159 | VEN-MH-047¦VEN-COLLIBRA | 2026-06-16 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0046 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0047 | BAA chain incomplete for AI workflow 047 | Financial | CTRL-MH-048 | POL-MH-048 | CTO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-032¦CI-SVC-168 | VEN-MH-048¦VEN-MH-016 | 2026-06-17 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0047 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0048 | AWS-hosted workload not modernized 048 | Clinical Safety | CTRL-MH-049 | POL-MH-049 | CFO | High | Likely | Open | CI-LEGACY-VM-033¦CI-SVC-177 | VEN-MH-049¦VEN-MH-021 | 2026-06-18 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0048 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0049 | Epic AMS transition knowledge gap 049 | Sourcing | CTRL-MH-050 | POL-MH-050 | AI Governance Council | Medium | Possible | Mitigating | CI-LEGACY-VM-034¦CI-SVC-186 | VEN-MH-050¦VEN-MH-026 | 2026-06-19 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0049 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0050 | Data analytics AMS scope ambiguity 050 | Operational | CTRL-MH-051 | POL-MH-051 | CISO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-035¦CI-SVC-195 | VEN-MH-051¦VEN-MH-031 | 2026-06-20 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0050 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0051 | PHI control evidence missing after migration 051 | Compliance | CTRL-MH-052 | POL-MH-052 | CDAO | High | Likely | Open | CI-LEGACY-VM-036¦CI-SVC-204 | VEN-MH-052¦VEN-MH-036 | 2026-06-21 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0051 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0052 | Cloud run cost exceeds baseline 052 | Financial | CTRL-MH-053 | POL-MH-053 | CTO | Medium | Possible | Mitigating | CI-LEGACY-VM-037¦CI-SVC-213 | VEN-MH-053¦VEN-MH-041 | 2026-06-22 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0052 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0053 | Integration backlog affects clinical continuity 053 | Clinical Safety | CTRL-MH-054 | POL-MH-054 | CFO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-038¦CI-SVC-222 | VEN-MH-054¦VEN-MH-046 | 2026-06-23 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0053 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0054 | CDAO stewardship capacity constraint 054 | Sourcing | CTRL-MH-055 | POL-MH-055 | AI Governance Council | High | Likely | Open | CI-LEGACY-VM-039¦CI-INT-RHAPSODY | VEN-MH-055¦VEN-MH-051 | 2026-06-24 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0054 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0055 | BAA chain incomplete for AI workflow 055 | Operational | CTRL-MH-056 | POL-MH-056 | CISO | Medium | Possible | Mitigating | CI-LEGACY-VM-040¦CI-AWS-LANDING-ZONE | VEN-MH-056¦VEN-MH-056 | 2026-06-25 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0055 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0056 | AWS-hosted workload not modernized 056 | Compliance | CTRL-MH-057 | POL-MH-057 | CDAO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-041¦CI-LEGACY-VM-009 | VEN-MH-057¦VEN-MH-061 | 2026-06-26 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0056 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0057 | Epic AMS transition knowledge gap 057 | Financial | CTRL-MH-058 | POL-MH-058 | CTO | High | Likely | Open | CI-LEGACY-VM-042¦CI-LEGACY-VM-018 | VEN-MH-058¦VEN-MH-066 | 2026-06-27 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0057 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0058 | Data analytics AMS scope ambiguity 058 | Clinical Safety | CTRL-MH-059 | POL-MH-059 | CFO | Medium | Possible | Mitigating | CI-LEGACY-VM-043¦CI-LEGACY-VM-027 | VEN-MH-059¦VEN-MH-071 | 2026-06-28 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0058 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0059 | PHI control evidence missing after migration 059 | Sourcing | CTRL-MH-060 | POL-MH-060 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-044¦CI-LEGACY-VM-036 | VEN-MH-060¦VEN-MH-076 | 2026-06-29 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0059 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0060 | Cloud run cost exceeds baseline 060 | Operational | CTRL-MH-061 | POL-MH-061 | CISO | High | Likely | Open | CI-LEGACY-VM-045¦CI-LEGACY-VM-045 | VEN-MH-061¦VEN-MH-081 | 2026-06-30 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0060 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0061 | Integration backlog affects clinical continuity 061 | Compliance | CTRL-MH-062 | POL-MH-062 | CDAO | Medium | Possible | Mitigating | CI-LEGACY-VM-046¦CI-LEGACY-VM-054 | VEN-MH-062¦VEN-MH-086 | 2026-07-01 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0061 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0062 | CDAO stewardship capacity constraint 062 | Financial | CTRL-MH-063 | POL-MH-063 | CTO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-047¦CI-LEGACY-VM-063 | VEN-MH-063¦VEN-MH-091 | 2026-07-02 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0062 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0063 | BAA chain incomplete for AI workflow 063 | Clinical Safety | CTRL-MH-064 | POL-MH-064 | CFO | High | Likely | Open | CI-LEGACY-VM-048¦CI-LEGACY-VM-072 | VEN-MH-064¦VEN-MH-096 | 2026-07-03 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0063 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0064 | AWS-hosted workload not modernized 064 | Sourcing | CTRL-MH-065 | POL-MH-065 | AI Governance Council | Medium | Possible | Mitigating | CI-LEGACY-VM-049¦CI-LEGACY-VM-081 | VEN-MH-065¦VEN-MH-101 | 2026-07-04 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0064 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0065 | Epic AMS transition knowledge gap 065 | Operational | CTRL-MH-066 | POL-MH-066 | CISO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-050¦CI-LEGACY-VM-090 | VEN-MH-066¦VEN-MH-106 | 2026-07-05 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0065 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0066 | Data analytics AMS scope ambiguity 066 | Compliance | CTRL-MH-067 | POL-MH-067 | CDAO | High | Likely | Open | CI-LEGACY-VM-051¦CI-LEGACY-VM-099 | VEN-MH-067¦VEN-EPIC | 2026-07-06 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0066 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0067 | PHI control evidence missing after migration 067 | Financial | CTRL-MH-068 | POL-MH-068 | CTO | Medium | Possible | Mitigating | CI-LEGACY-VM-052¦CI-LEGACY-VM-108 | VEN-MH-068¦VEN-WORKDAY | 2026-07-07 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0067 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0068 | Cloud run cost exceeds baseline 068 | Clinical Safety | CTRL-MH-069 | POL-MH-069 | CFO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-053¦CI-LEGACY-VM-117 | VEN-MH-069¦VEN-COLLIBRA | 2026-07-08 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0068 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0069 | Integration backlog affects clinical continuity 069 | Sourcing | CTRL-MH-070 | POL-MH-070 | AI Governance Council | High | Likely | Open | CI-LEGACY-VM-054¦CI-LEGACY-VM-126 | VEN-MH-070¦VEN-MH-016 | 2026-07-09 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0069 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0070 | CDAO stewardship capacity constraint 070 | Operational | CTRL-MH-071 | POL-MH-071 | CISO | Medium | Possible | Mitigating | CI-LEGACY-VM-055¦CI-SVC-135 | VEN-MH-071¦VEN-MH-021 | 2026-07-10 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0070 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0071 | BAA chain incomplete for AI workflow 071 | Compliance | CTRL-MH-072 | POL-MH-072 | CDAO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-056¦CI-SVC-144 | VEN-MH-072¦VEN-MH-026 | 2026-07-11 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0071 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0072 | AWS-hosted workload not modernized 072 | Financial | CTRL-MH-073 | POL-MH-073 | CTO | High | Likely | Open | CI-LEGACY-VM-057¦CI-SVC-153 | VEN-MH-073¦VEN-MH-031 | 2026-07-12 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0072 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0073 | Epic AMS transition knowledge gap 073 | Clinical Safety | CTRL-MH-074 | POL-MH-074 | CFO | Medium | Possible | Mitigating | CI-LEGACY-VM-058¦CI-SVC-162 | VEN-MH-074¦VEN-MH-036 | 2026-07-13 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0073 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0074 | Data analytics AMS scope ambiguity 074 | Sourcing | CTRL-MH-075 | POL-MH-075 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-059¦CI-SVC-171 | VEN-MH-075¦VEN-MH-041 | 2026-07-14 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0074 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0075 | PHI control evidence missing after migration 075 | Operational | CTRL-MH-001 | POL-MH-001 | CISO | High | Likely | Open | CI-LEGACY-VM-060¦CI-SVC-180 | VEN-MH-076¦VEN-MH-046 | 2026-07-15 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0075 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0076 | Cloud run cost exceeds baseline 076 | Compliance | CTRL-MH-002 | POL-MH-002 | CDAO | Medium | Possible | Mitigating | CI-LEGACY-VM-061¦CI-SVC-189 | VEN-MH-077¦VEN-MH-051 | 2026-07-16 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0076 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0077 | Integration backlog affects clinical continuity 077 | Financial | CTRL-MH-003 | POL-MH-003 | CTO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-062¦CI-SVC-198 | VEN-MH-078¦VEN-MH-056 | 2026-07-17 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0077 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0078 | CDAO stewardship capacity constraint 078 | Clinical Safety | CTRL-MH-004 | POL-MH-004 | CFO | High | Likely | Open | CI-LEGACY-VM-063¦CI-SVC-207 | VEN-MH-079¦VEN-MH-061 | 2026-07-18 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0078 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0079 | BAA chain incomplete for AI workflow 079 | Sourcing | CTRL-MH-005 | POL-MH-005 | AI Governance Council | Medium | Possible | Mitigating | CI-LEGACY-VM-064¦CI-SVC-216 | VEN-MH-080¦VEN-MH-066 | 2026-07-19 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0079 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0080 | AWS-hosted workload not modernized 080 | Operational | CTRL-MH-006 | POL-MH-006 | CISO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-065¦CI-APP-EPIC-HYPERSPACE | VEN-MH-081¦VEN-MH-071 | 2026-07-20 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0080 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0081 | Epic AMS transition knowledge gap 081 | Compliance | CTRL-MH-007 | POL-MH-007 | CDAO | High | Likely | Open | CI-LEGACY-VM-066¦CI-HCM-WORKDAY | VEN-MH-082¦VEN-MH-076 | 2026-07-21 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0081 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0082 | Data analytics AMS scope ambiguity 082 | Financial | CTRL-MH-008 | POL-MH-008 | CTO | Medium | Possible | Mitigating | CI-LEGACY-VM-067¦CI-LEGACY-VM-003 | VEN-MH-083¦VEN-MH-081 | 2026-07-22 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0082 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0083 | PHI control evidence missing after migration 083 | Clinical Safety | CTRL-MH-009 | POL-MH-009 | CFO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-068¦CI-LEGACY-VM-012 | VEN-MH-084¦VEN-MH-086 | 2026-07-23 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0083 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0084 | Cloud run cost exceeds baseline 084 | Sourcing | CTRL-MH-010 | POL-MH-010 | AI Governance Council | High | Likely | Open | CI-LEGACY-VM-069¦CI-LEGACY-VM-021 | VEN-MH-085¦VEN-MH-091 | 2026-07-24 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0084 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0085 | Integration backlog affects clinical continuity 085 | Operational | CTRL-MH-011 | POL-MH-011 | CISO | Medium | Possible | Mitigating | CI-LEGACY-VM-070¦CI-LEGACY-VM-030 | VEN-MH-086¦VEN-MH-096 | 2026-07-25 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0085 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0086 | CDAO stewardship capacity constraint 086 | Compliance | CTRL-MH-012 | POL-MH-012 | CDAO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-071¦CI-LEGACY-VM-039 | VEN-MH-087¦VEN-MH-101 | 2026-07-26 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0086 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0087 | BAA chain incomplete for AI workflow 087 | Financial | CTRL-MH-013 | POL-MH-013 | CTO | High | Likely | Open | CI-LEGACY-VM-072¦CI-LEGACY-VM-048 | VEN-MH-088¦VEN-MH-106 | 2026-07-27 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0087 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0088 | AWS-hosted workload not modernized 088 | Clinical Safety | CTRL-MH-014 | POL-MH-014 | CFO | Medium | Possible | Mitigating | CI-LEGACY-VM-073¦CI-LEGACY-VM-057 | VEN-MH-089¦VEN-EPIC | 2026-07-28 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0088 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0089 | Epic AMS transition knowledge gap 089 | Sourcing | CTRL-MH-015 | POL-MH-015 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-074¦CI-LEGACY-VM-066 | VEN-MH-090¦VEN-WORKDAY | 2026-07-29 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0089 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0090 | Data analytics AMS scope ambiguity 090 | Operational | CTRL-MH-016 | POL-MH-016 | CISO | High | Likely | Open | CI-LEGACY-VM-075¦CI-LEGACY-VM-075 | VEN-MH-091¦VEN-COLLIBRA | 2026-07-30 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0090 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0091 | PHI control evidence missing after migration 091 | Compliance | CTRL-MH-017 | POL-MH-017 | CDAO | Medium | Possible | Mitigating | CI-LEGACY-VM-076¦CI-LEGACY-VM-084 | VEN-MH-092¦VEN-MH-016 | 2026-07-31 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0091 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0092 | Cloud run cost exceeds baseline 092 | Financial | CTRL-MH-018 | POL-MH-018 | CTO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-077¦CI-LEGACY-VM-093 | VEN-MH-093¦VEN-MH-021 | 2026-08-01 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0092 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0093 | Integration backlog affects clinical continuity 093 | Clinical Safety | CTRL-MH-019 | POL-MH-019 | CFO | High | Likely | Open | CI-LEGACY-VM-078¦CI-LEGACY-VM-102 | VEN-MH-094¦VEN-MH-026 | 2026-08-02 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0093 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0094 | CDAO stewardship capacity constraint 094 | Sourcing | CTRL-MH-020 | POL-MH-020 | AI Governance Council | Medium | Possible | Mitigating | CI-LEGACY-VM-079¦CI-LEGACY-VM-111 | VEN-MH-095¦VEN-MH-031 | 2026-08-03 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0094 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0095 | BAA chain incomplete for AI workflow 095 | Operational | CTRL-MH-021 | POL-MH-021 | CISO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-080¦CI-LEGACY-VM-120 | VEN-MH-096¦VEN-MH-036 | 2026-08-04 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0095 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0096 | AWS-hosted workload not modernized 096 | Compliance | CTRL-MH-022 | POL-MH-022 | CDAO | High | Likely | Open | CI-LEGACY-VM-081¦CI-LEGACY-VM-129 | VEN-MH-097¦VEN-MH-041 | 2026-08-05 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0096 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0097 | Epic AMS transition knowledge gap 097 | Financial | CTRL-MH-023 | POL-MH-023 | CTO | Medium | Possible | Mitigating | CI-LEGACY-VM-082¦CI-SVC-138 | VEN-MH-098¦VEN-MH-046 | 2026-08-06 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0097 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0098 | Data analytics AMS scope ambiguity 098 | Clinical Safety | CTRL-MH-024 | POL-MH-024 | CFO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-083¦CI-SVC-147 | VEN-MH-099¦VEN-MH-051 | 2026-08-07 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0098 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0099 | PHI control evidence missing after migration 099 | Sourcing | CTRL-MH-025 | POL-MH-025 | AI Governance Council | High | Likely | Open | CI-LEGACY-VM-084¦CI-SVC-156 | VEN-MH-100¦VEN-MH-056 | 2026-08-08 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0099 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0100 | Cloud run cost exceeds baseline 100 | Operational | CTRL-MH-026 | POL-MH-026 | CISO | Medium | Possible | Mitigating | CI-LEGACY-VM-085¦CI-SVC-165 | VEN-MH-101¦VEN-MH-061 | 2026-08-09 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0100 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0101 | Integration backlog affects clinical continuity 101 | Compliance | CTRL-MH-027 | POL-MH-027 | CDAO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-086¦CI-SVC-174 | VEN-MH-102¦VEN-MH-066 | 2026-08-10 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0101 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0102 | CDAO stewardship capacity constraint 102 | Financial | CTRL-MH-028 | POL-MH-028 | CTO | High | Likely | Open | CI-LEGACY-VM-087¦CI-SVC-183 | VEN-MH-103¦VEN-MH-071 | 2026-08-11 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0102 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0103 | BAA chain incomplete for AI workflow 103 | Clinical Safety | CTRL-MH-029 | POL-MH-029 | CFO | Medium | Possible | Mitigating | CI-LEGACY-VM-088¦CI-SVC-192 | VEN-MH-104¦VEN-MH-076 | 2026-08-12 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0103 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0104 | AWS-hosted workload not modernized 104 | Sourcing | CTRL-MH-030 | POL-MH-030 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-089¦CI-SVC-201 | VEN-MH-105¦VEN-MH-081 | 2026-08-13 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0104 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0105 | Epic AMS transition knowledge gap 105 | Operational | CTRL-MH-031 | POL-MH-031 | CISO | High | Likely | Open | CI-LEGACY-VM-090¦CI-SVC-210 | VEN-MH-106¦VEN-MH-086 | 2026-08-14 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0105 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0106 | Data analytics AMS scope ambiguity 106 | Compliance | CTRL-MH-032 | POL-MH-032 | CDAO | Medium | Possible | Mitigating | CI-LEGACY-VM-091¦CI-SVC-219 | VEN-MH-107¦VEN-MH-091 | 2026-08-15 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0106 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0107 | PHI control evidence missing after migration 107 | Financial | CTRL-MH-033 | POL-MH-033 | CTO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-092¦CI-APP-EPIC-MYCHART | VEN-MH-108¦VEN-MH-096 | 2026-08-16 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0107 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0108 | Cloud run cost exceeds baseline 108 | Clinical Safety | CTRL-MH-034 | POL-MH-034 | CFO | High | Likely | Open | CI-LEGACY-VM-093¦CI-DATA-COLLIBRA | VEN-MH-109¦VEN-MH-101 | 2026-08-17 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0108 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0109 | Integration backlog affects clinical continuity 109 | Sourcing | CTRL-MH-035 | POL-MH-035 | AI Governance Council | Medium | Possible | Mitigating | CI-LEGACY-VM-094¦CI-LEGACY-VM-006 | VEN-MH-110¦VEN-MH-106 | 2026-08-18 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0109 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0110 | CDAO stewardship capacity constraint 110 | Operational | CTRL-MH-036 | POL-MH-036 | CISO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-095¦CI-LEGACY-VM-015 | VEN-EPIC¦VEN-EPIC | 2026-08-19 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0110 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0111 | BAA chain incomplete for AI workflow 111 | Compliance | CTRL-MH-037 | POL-MH-037 | CDAO | High | Likely | Open | CI-LEGACY-VM-096¦CI-LEGACY-VM-024 | VEN-AMS-EPIC¦VEN-WORKDAY | 2026-08-20 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0111 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0112 | AWS-hosted workload not modernized 112 | Financial | CTRL-MH-038 | POL-MH-038 | CTO | Medium | Possible | Mitigating | CI-LEGACY-VM-097¦CI-LEGACY-VM-033 | VEN-AMS-DATA¦VEN-COLLIBRA | 2026-08-21 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0112 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0113 | Epic AMS transition knowledge gap 113 | Clinical Safety | CTRL-MH-039 | POL-MH-039 | CFO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-098¦CI-LEGACY-VM-042 | VEN-AWS¦VEN-MH-016 | 2026-08-22 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0113 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0114 | Data analytics AMS scope ambiguity 114 | Sourcing | CTRL-MH-040 | POL-MH-040 | AI Governance Council | High | Likely | Open | CI-LEGACY-VM-099¦CI-LEGACY-VM-051 | VEN-ORACLE¦VEN-MH-021 | 2026-08-23 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0114 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0115 | PHI control evidence missing after migration 115 | Operational | CTRL-MH-041 | POL-MH-041 | CISO | Medium | Possible | Mitigating | CI-LEGACY-VM-100¦CI-LEGACY-VM-060 | VEN-WORKDAY¦VEN-MH-026 | 2026-08-24 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0115 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0116 | Cloud run cost exceeds baseline 116 | Compliance | CTRL-MH-042 | POL-MH-042 | CDAO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-101¦CI-LEGACY-VM-069 | VEN-SNOW¦VEN-MH-031 | 2026-08-25 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0116 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0117 | Integration backlog affects clinical continuity 117 | Financial | CTRL-MH-043 | POL-MH-043 | CTO | High | Likely | Open | CI-LEGACY-VM-102¦CI-LEGACY-VM-078 | VEN-DATABRICKS¦VEN-MH-036 | 2026-08-26 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0117 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0118 | CDAO stewardship capacity constraint 118 | Clinical Safety | CTRL-MH-044 | POL-MH-044 | CFO | Medium | Possible | Mitigating | CI-LEGACY-VM-103¦CI-LEGACY-VM-087 | VEN-MICROSOFT¦VEN-MH-041 | 2026-08-27 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0118 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0119 | BAA chain incomplete for AI workflow 119 | Sourcing | CTRL-MH-045 | POL-MH-045 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-104¦CI-LEGACY-VM-096 | VEN-RHAPSODY¦VEN-MH-046 | 2026-08-28 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0119 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0120 | AWS-hosted workload not modernized 120 | Operational | CTRL-MH-046 | POL-MH-046 | CISO | High | Likely | Open | CI-LEGACY-VM-105¦CI-LEGACY-VM-105 | VEN-COLLIBRA¦VEN-MH-051 | 2026-08-29 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0120 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0121 | Epic AMS transition knowledge gap 121 | Compliance | CTRL-MH-047 | POL-MH-047 | CDAO | Medium | Possible | Mitigating | CI-LEGACY-VM-106¦CI-LEGACY-VM-114 | VEN-CROWDSTRIKE¦VEN-MH-056 | 2026-08-30 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0121 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0122 | Data analytics AMS scope ambiguity 122 | Financial | CTRL-MH-048 | POL-MH-048 | CTO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-107¦CI-LEGACY-VM-123 | VEN-MH-013¦VEN-MH-061 | 2026-08-31 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0122 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0123 | PHI control evidence missing after migration 123 | Clinical Safety | CTRL-MH-049 | POL-MH-049 | CFO | High | Likely | Open | CI-LEGACY-VM-108¦CI-SVC-132 | VEN-MH-014¦VEN-MH-066 | 2026-09-01 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0123 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0124 | Cloud run cost exceeds baseline 124 | Sourcing | CTRL-MH-050 | POL-MH-050 | AI Governance Council | Medium | Possible | Mitigating | CI-LEGACY-VM-109¦CI-SVC-141 | VEN-MH-015¦VEN-MH-071 | 2026-09-02 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0124 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0125 | Integration backlog affects clinical continuity 125 | Operational | CTRL-MH-051 | POL-MH-051 | CISO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-110¦CI-SVC-150 | VEN-MH-016¦VEN-MH-076 | 2026-09-03 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0125 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0126 | CDAO stewardship capacity constraint 126 | Compliance | CTRL-MH-052 | POL-MH-052 | CDAO | High | Likely | Open | CI-LEGACY-VM-111¦CI-SVC-159 | VEN-MH-017¦VEN-MH-081 | 2026-09-04 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0126 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0127 | BAA chain incomplete for AI workflow 127 | Financial | CTRL-MH-053 | POL-MH-053 | CTO | Medium | Possible | Mitigating | CI-LEGACY-VM-112¦CI-SVC-168 | VEN-MH-018¦VEN-MH-086 | 2026-09-05 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0127 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0128 | AWS-hosted workload not modernized 128 | Clinical Safety | CTRL-MH-054 | POL-MH-054 | CFO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-113¦CI-SVC-177 | VEN-MH-019¦VEN-MH-091 | 2026-09-06 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0128 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0129 | Epic AMS transition knowledge gap 129 | Sourcing | CTRL-MH-055 | POL-MH-055 | AI Governance Council | High | Likely | Open | CI-LEGACY-VM-114¦CI-SVC-186 | VEN-MH-020¦VEN-MH-096 | 2026-09-07 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0129 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0130 | Data analytics AMS scope ambiguity 130 | Operational | CTRL-MH-056 | POL-MH-056 | CISO | Medium | Possible | Mitigating | CI-LEGACY-VM-115¦CI-SVC-195 | VEN-MH-021¦VEN-MH-101 | 2026-09-08 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0130 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0131 | PHI control evidence missing after migration 131 | Compliance | CTRL-MH-057 | POL-MH-057 | CDAO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-116¦CI-SVC-204 | VEN-MH-022¦VEN-MH-106 | 2026-09-09 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0131 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0132 | Cloud run cost exceeds baseline 132 | Financial | CTRL-MH-058 | POL-MH-058 | CTO | High | Likely | Open | CI-LEGACY-VM-117¦CI-SVC-213 | VEN-MH-023¦VEN-EPIC | 2026-09-10 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0132 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0133 | Integration backlog affects clinical continuity 133 | Clinical Safety | CTRL-MH-059 | POL-MH-059 | CFO | Medium | Possible | Mitigating | CI-LEGACY-VM-118¦CI-SVC-222 | VEN-MH-024¦VEN-WORKDAY | 2026-09-11 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0133 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0134 | CDAO stewardship capacity constraint 134 | Sourcing | CTRL-MH-060 | POL-MH-060 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-119¦CI-INT-RHAPSODY | VEN-MH-025¦VEN-COLLIBRA | 2026-09-12 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0134 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0135 | BAA chain incomplete for AI workflow 135 | Operational | CTRL-MH-061 | POL-MH-061 | CISO | High | Likely | Open | CI-LEGACY-VM-120¦CI-AWS-LANDING-ZONE | VEN-MH-026¦VEN-MH-016 | 2026-09-13 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0135 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0136 | AWS-hosted workload not modernized 136 | Compliance | CTRL-MH-062 | POL-MH-062 | CDAO | Medium | Possible | Mitigating | CI-LEGACY-VM-121¦CI-LEGACY-VM-009 | VEN-MH-027¦VEN-MH-021 | 2026-09-14 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0136 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0137 | Epic AMS transition knowledge gap 137 | Financial | CTRL-MH-063 | POL-MH-063 | CTO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-122¦CI-LEGACY-VM-018 | VEN-MH-028¦VEN-MH-026 | 2026-09-15 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0137 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0138 | Data analytics AMS scope ambiguity 138 | Clinical Safety | CTRL-MH-064 | POL-MH-064 | CFO | High | Likely | Open | CI-LEGACY-VM-123¦CI-LEGACY-VM-027 | VEN-MH-029¦VEN-MH-031 | 2026-09-16 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0138 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0139 | PHI control evidence missing after migration 139 | Sourcing | CTRL-MH-065 | POL-MH-065 | AI Governance Council | Medium | Possible | Mitigating | CI-LEGACY-VM-124¦CI-LEGACY-VM-036 | VEN-MH-030¦VEN-MH-036 | 2026-09-17 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0139 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0140 | Cloud run cost exceeds baseline 140 | Operational | CTRL-MH-066 | POL-MH-066 | CISO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-125¦CI-LEGACY-VM-045 | VEN-MH-031¦VEN-MH-041 | 2026-09-18 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0140 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0141 | Integration backlog affects clinical continuity 141 | Compliance | CTRL-MH-067 | POL-MH-067 | CDAO | High | Likely | Open | CI-LEGACY-VM-126¦CI-LEGACY-VM-054 | VEN-MH-032¦VEN-MH-046 | 2026-09-19 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0141 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0142 | CDAO stewardship capacity constraint 142 | Financial | CTRL-MH-068 | POL-MH-068 | CTO | Medium | Possible | Mitigating | CI-LEGACY-VM-127¦CI-LEGACY-VM-063 | VEN-MH-033¦VEN-MH-051 | 2026-09-20 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0142 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0143 | BAA chain incomplete for AI workflow 143 | Clinical Safety | CTRL-MH-069 | POL-MH-069 | CFO | Critical | Unlikely | Accepted with controls | CI-LEGACY-VM-128¦CI-LEGACY-VM-072 | VEN-MH-034¦VEN-MH-056 | 2026-09-21 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0143 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0144 | AWS-hosted workload not modernized 144 | Sourcing | CTRL-MH-070 | POL-MH-070 | AI Governance Council | High | Likely | Open | CI-LEGACY-VM-129¦CI-LEGACY-VM-081 | VEN-MH-035¦VEN-MH-061 | 2026-09-22 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0144 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0145 | Epic AMS transition knowledge gap 145 | Operational | CTRL-MH-071 | POL-MH-071 | CISO | Medium | Possible | Mitigating | CI-LEGACY-VM-130¦CI-LEGACY-VM-090 | VEN-MH-036¦VEN-MH-066 | 2026-09-23 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0145 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0146 | Data analytics AMS scope ambiguity 146 | Compliance | CTRL-MH-072 | POL-MH-072 | CDAO | Critical | Unlikely | Accepted with controls | CI-SVC-131¦CI-LEGACY-VM-099 | VEN-MH-037¦VEN-MH-071 | 2026-09-24 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0146 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0147 | PHI control evidence missing after migration 147 | Financial | CTRL-MH-073 | POL-MH-073 | CTO | High | Likely | Open | CI-SVC-132¦CI-LEGACY-VM-108 | VEN-MH-038¦VEN-MH-076 | 2026-09-25 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0147 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0148 | Cloud run cost exceeds baseline 148 | Clinical Safety | CTRL-MH-074 | POL-MH-074 | CFO | Medium | Possible | Mitigating | CI-SVC-133¦CI-LEGACY-VM-117 | VEN-MH-039¦VEN-MH-081 | 2026-09-26 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0148 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0149 | Integration backlog affects clinical continuity 149 | Sourcing | CTRL-MH-075 | POL-MH-075 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-SVC-134¦CI-LEGACY-VM-126 | VEN-MH-040¦VEN-MH-086 | 2026-09-27 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0149 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0150 | CDAO stewardship capacity constraint 150 | Operational | CTRL-MH-001 | POL-MH-001 | CISO | High | Likely | Open | CI-SVC-135¦CI-SVC-135 | VEN-MH-041¦VEN-MH-091 | 2026-09-28 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0150 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0151 | BAA chain incomplete for AI workflow 151 | Compliance | CTRL-MH-002 | POL-MH-002 | CDAO | Medium | Possible | Mitigating | CI-SVC-136¦CI-SVC-144 | VEN-MH-042¦VEN-MH-096 | 2026-09-29 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0151 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0152 | AWS-hosted workload not modernized 152 | Financial | CTRL-MH-003 | POL-MH-003 | CTO | Critical | Unlikely | Accepted with controls | CI-SVC-137¦CI-SVC-153 | VEN-MH-043¦VEN-MH-101 | 2026-09-30 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0152 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0153 | Epic AMS transition knowledge gap 153 | Clinical Safety | CTRL-MH-004 | POL-MH-004 | CFO | High | Likely | Open | CI-SVC-138¦CI-SVC-162 | VEN-MH-044¦VEN-MH-106 | 2026-10-01 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0153 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0154 | Data analytics AMS scope ambiguity 154 | Sourcing | CTRL-MH-005 | POL-MH-005 | AI Governance Council | Medium | Possible | Mitigating | CI-SVC-139¦CI-SVC-171 | VEN-MH-045¦VEN-EPIC | 2026-10-02 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0154 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0155 | PHI control evidence missing after migration 155 | Operational | CTRL-MH-006 | POL-MH-006 | CISO | Critical | Unlikely | Accepted with controls | CI-SVC-140¦CI-SVC-180 | VEN-MH-046¦VEN-WORKDAY | 2026-10-03 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0155 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0156 | Cloud run cost exceeds baseline 156 | Compliance | CTRL-MH-007 | POL-MH-007 | CDAO | High | Likely | Open | CI-SVC-141¦CI-SVC-189 | VEN-MH-047¦VEN-COLLIBRA | 2026-10-04 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0156 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0157 | Integration backlog affects clinical continuity 157 | Financial | CTRL-MH-008 | POL-MH-008 | CTO | Medium | Possible | Mitigating | CI-SVC-142¦CI-SVC-198 | VEN-MH-048¦VEN-MH-016 | 2026-10-05 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0157 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0158 | CDAO stewardship capacity constraint 158 | Clinical Safety | CTRL-MH-009 | POL-MH-009 | CFO | Critical | Unlikely | Accepted with controls | CI-SVC-143¦CI-SVC-207 | VEN-MH-049¦VEN-MH-021 | 2026-10-06 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0158 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0159 | BAA chain incomplete for AI workflow 159 | Sourcing | CTRL-MH-010 | POL-MH-010 | AI Governance Council | High | Likely | Open | CI-SVC-144¦CI-SVC-216 | VEN-MH-050¦VEN-MH-026 | 2026-10-07 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0159 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0160 | AWS-hosted workload not modernized 160 | Operational | CTRL-MH-011 | POL-MH-011 | CISO | Medium | Possible | Mitigating | CI-SVC-145¦CI-APP-EPIC-HYPERSPACE | VEN-MH-051¦VEN-MH-031 | 2026-10-08 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0160 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0161 | Epic AMS transition knowledge gap 161 | Compliance | CTRL-MH-012 | POL-MH-012 | CDAO | Critical | Unlikely | Accepted with controls | CI-SVC-146¦CI-HCM-WORKDAY | VEN-MH-052¦VEN-MH-036 | 2026-10-09 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0161 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0162 | Data analytics AMS scope ambiguity 162 | Financial | CTRL-MH-013 | POL-MH-013 | CTO | High | Likely | Open | CI-SVC-147¦CI-LEGACY-VM-003 | VEN-MH-053¦VEN-MH-041 | 2026-10-10 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0162 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0163 | PHI control evidence missing after migration 163 | Clinical Safety | CTRL-MH-014 | POL-MH-014 | CFO | Medium | Possible | Mitigating | CI-SVC-148¦CI-LEGACY-VM-012 | VEN-MH-054¦VEN-MH-046 | 2026-10-11 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0163 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0164 | Cloud run cost exceeds baseline 164 | Sourcing | CTRL-MH-015 | POL-MH-015 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-SVC-149¦CI-LEGACY-VM-021 | VEN-MH-055¦VEN-MH-051 | 2026-10-12 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0164 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0165 | Integration backlog affects clinical continuity 165 | Operational | CTRL-MH-016 | POL-MH-016 | CISO | High | Likely | Open | CI-SVC-150¦CI-LEGACY-VM-030 | VEN-MH-056¦VEN-MH-056 | 2026-10-13 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0165 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0166 | CDAO stewardship capacity constraint 166 | Compliance | CTRL-MH-017 | POL-MH-017 | CDAO | Medium | Possible | Mitigating | CI-SVC-151¦CI-LEGACY-VM-039 | VEN-MH-057¦VEN-MH-061 | 2026-10-14 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0166 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0167 | BAA chain incomplete for AI workflow 167 | Financial | CTRL-MH-018 | POL-MH-018 | CTO | Critical | Unlikely | Accepted with controls | CI-SVC-152¦CI-LEGACY-VM-048 | VEN-MH-058¦VEN-MH-066 | 2026-10-15 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0167 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0168 | AWS-hosted workload not modernized 168 | Clinical Safety | CTRL-MH-019 | POL-MH-019 | CFO | High | Likely | Open | CI-SVC-153¦CI-LEGACY-VM-057 | VEN-MH-059¦VEN-MH-071 | 2026-10-16 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0168 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0169 | Epic AMS transition knowledge gap 169 | Sourcing | CTRL-MH-020 | POL-MH-020 | AI Governance Council | Medium | Possible | Mitigating | CI-SVC-154¦CI-LEGACY-VM-066 | VEN-MH-060¦VEN-MH-076 | 2026-10-17 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0169 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0170 | Data analytics AMS scope ambiguity 170 | Operational | CTRL-MH-021 | POL-MH-021 | CISO | Critical | Unlikely | Accepted with controls | CI-SVC-155¦CI-LEGACY-VM-075 | VEN-MH-061¦VEN-MH-081 | 2026-10-18 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0170 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0171 | PHI control evidence missing after migration 171 | Compliance | CTRL-MH-022 | POL-MH-022 | CDAO | High | Likely | Open | CI-SVC-156¦CI-LEGACY-VM-084 | VEN-MH-062¦VEN-MH-086 | 2026-10-19 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0171 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0172 | Cloud run cost exceeds baseline 172 | Financial | CTRL-MH-023 | POL-MH-023 | CTO | Medium | Possible | Mitigating | CI-SVC-157¦CI-LEGACY-VM-093 | VEN-MH-063¦VEN-MH-091 | 2026-10-20 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0172 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0173 | Integration backlog affects clinical continuity 173 | Clinical Safety | CTRL-MH-024 | POL-MH-024 | CFO | Critical | Unlikely | Accepted with controls | CI-SVC-158¦CI-LEGACY-VM-102 | VEN-MH-064¦VEN-MH-096 | 2026-10-21 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0173 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0174 | CDAO stewardship capacity constraint 174 | Sourcing | CTRL-MH-025 | POL-MH-025 | AI Governance Council | High | Likely | Open | CI-SVC-159¦CI-LEGACY-VM-111 | VEN-MH-065¦VEN-MH-101 | 2026-10-22 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0174 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0175 | BAA chain incomplete for AI workflow 175 | Operational | CTRL-MH-026 | POL-MH-026 | CISO | Medium | Possible | Mitigating | CI-SVC-160¦CI-LEGACY-VM-120 | VEN-MH-066¦VEN-MH-106 | 2026-10-23 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0175 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0176 | AWS-hosted workload not modernized 176 | Compliance | CTRL-MH-027 | POL-MH-027 | CDAO | Critical | Unlikely | Accepted with controls | CI-SVC-161¦CI-LEGACY-VM-129 | VEN-MH-067¦VEN-EPIC | 2026-10-24 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0176 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0177 | Epic AMS transition knowledge gap 177 | Financial | CTRL-MH-028 | POL-MH-028 | CTO | High | Likely | Open | CI-SVC-162¦CI-SVC-138 | VEN-MH-068¦VEN-WORKDAY | 2026-10-25 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0177 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0178 | Data analytics AMS scope ambiguity 178 | Clinical Safety | CTRL-MH-029 | POL-MH-029 | CFO | Medium | Possible | Mitigating | CI-SVC-163¦CI-SVC-147 | VEN-MH-069¦VEN-COLLIBRA | 2026-10-26 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0178 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0179 | PHI control evidence missing after migration 179 | Sourcing | CTRL-MH-030 | POL-MH-030 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-SVC-164¦CI-SVC-156 | VEN-MH-070¦VEN-MH-016 | 2026-10-27 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0179 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0180 | Cloud run cost exceeds baseline 180 | Operational | CTRL-MH-031 | POL-MH-031 | CISO | High | Likely | Open | CI-SVC-165¦CI-SVC-165 | VEN-MH-071¦VEN-MH-021 | 2026-10-28 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0180 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0181 | Integration backlog affects clinical continuity 181 | Compliance | CTRL-MH-032 | POL-MH-032 | CDAO | Medium | Possible | Mitigating | CI-SVC-166¦CI-SVC-174 | VEN-MH-072¦VEN-MH-026 | 2026-10-29 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0181 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0182 | CDAO stewardship capacity constraint 182 | Financial | CTRL-MH-033 | POL-MH-033 | CTO | Critical | Unlikely | Accepted with controls | CI-SVC-167¦CI-SVC-183 | VEN-MH-073¦VEN-MH-031 | 2026-10-30 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0182 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0183 | BAA chain incomplete for AI workflow 183 | Clinical Safety | CTRL-MH-034 | POL-MH-034 | CFO | High | Likely | Open | CI-SVC-168¦CI-SVC-192 | VEN-MH-074¦VEN-MH-036 | 2026-10-31 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0183 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0184 | AWS-hosted workload not modernized 184 | Sourcing | CTRL-MH-035 | POL-MH-035 | AI Governance Council | Medium | Possible | Mitigating | CI-SVC-169¦CI-SVC-201 | VEN-MH-075¦VEN-MH-041 | 2026-11-01 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0184 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0185 | Epic AMS transition knowledge gap 185 | Operational | CTRL-MH-036 | POL-MH-036 | CISO | Critical | Unlikely | Accepted with controls | CI-SVC-170¦CI-SVC-210 | VEN-MH-076¦VEN-MH-046 | 2026-11-02 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0185 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0186 | Data analytics AMS scope ambiguity 186 | Compliance | CTRL-MH-037 | POL-MH-037 | CDAO | High | Likely | Open | CI-SVC-171¦CI-SVC-219 | VEN-MH-077¦VEN-MH-051 | 2026-11-03 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0186 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0187 | PHI control evidence missing after migration 187 | Financial | CTRL-MH-038 | POL-MH-038 | CTO | Medium | Possible | Mitigating | CI-SVC-172¦CI-APP-EPIC-MYCHART | VEN-MH-078¦VEN-MH-056 | 2026-11-04 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0187 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0188 | Cloud run cost exceeds baseline 188 | Clinical Safety | CTRL-MH-039 | POL-MH-039 | CFO | Critical | Unlikely | Accepted with controls | CI-SVC-173¦CI-DATA-COLLIBRA | VEN-MH-079¦VEN-MH-061 | 2026-11-05 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0188 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0189 | Integration backlog affects clinical continuity 189 | Sourcing | CTRL-MH-040 | POL-MH-040 | AI Governance Council | High | Likely | Open | CI-SVC-174¦CI-LEGACY-VM-006 | VEN-MH-080¦VEN-MH-066 | 2026-11-06 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0189 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0190 | CDAO stewardship capacity constraint 190 | Operational | CTRL-MH-041 | POL-MH-041 | CISO | Medium | Possible | Mitigating | CI-SVC-175¦CI-LEGACY-VM-015 | VEN-MH-081¦VEN-MH-071 | 2026-11-07 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0190 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0191 | BAA chain incomplete for AI workflow 191 | Compliance | CTRL-MH-042 | POL-MH-042 | CDAO | Critical | Unlikely | Accepted with controls | CI-SVC-176¦CI-LEGACY-VM-024 | VEN-MH-082¦VEN-MH-076 | 2026-11-08 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0191 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0192 | AWS-hosted workload not modernized 192 | Financial | CTRL-MH-043 | POL-MH-043 | CTO | High | Likely | Open | CI-SVC-177¦CI-LEGACY-VM-033 | VEN-MH-083¦VEN-MH-081 | 2026-11-09 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0192 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0193 | Epic AMS transition knowledge gap 193 | Clinical Safety | CTRL-MH-044 | POL-MH-044 | CFO | Medium | Possible | Mitigating | CI-SVC-178¦CI-LEGACY-VM-042 | VEN-MH-084¦VEN-MH-086 | 2026-11-10 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0193 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0194 | Data analytics AMS scope ambiguity 194 | Sourcing | CTRL-MH-045 | POL-MH-045 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-SVC-179¦CI-LEGACY-VM-051 | VEN-MH-085¦VEN-MH-091 | 2026-11-11 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0194 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0195 | PHI control evidence missing after migration 195 | Operational | CTRL-MH-046 | POL-MH-046 | CISO | High | Likely | Open | CI-SVC-180¦CI-LEGACY-VM-060 | VEN-MH-086¦VEN-MH-096 | 2026-11-12 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0195 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0196 | Cloud run cost exceeds baseline 196 | Compliance | CTRL-MH-047 | POL-MH-047 | CDAO | Medium | Possible | Mitigating | CI-SVC-181¦CI-LEGACY-VM-069 | VEN-MH-087¦VEN-MH-101 | 2026-11-13 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0196 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0197 | Integration backlog affects clinical continuity 197 | Financial | CTRL-MH-048 | POL-MH-048 | CTO | Critical | Unlikely | Accepted with controls | CI-SVC-182¦CI-LEGACY-VM-078 | VEN-MH-088¦VEN-MH-106 | 2026-11-14 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0197 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0198 | CDAO stewardship capacity constraint 198 | Clinical Safety | CTRL-MH-049 | POL-MH-049 | CFO | High | Likely | Open | CI-SVC-183¦CI-LEGACY-VM-087 | VEN-MH-089¦VEN-EPIC | 2026-11-15 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0198 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0199 | BAA chain incomplete for AI workflow 199 | Sourcing | CTRL-MH-050 | POL-MH-050 | AI Governance Council | Medium | Possible | Mitigating | CI-SVC-184¦CI-LEGACY-VM-096 | VEN-MH-090¦VEN-WORKDAY | 2026-11-16 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0199 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0200 | AWS-hosted workload not modernized 200 | Operational | CTRL-MH-051 | POL-MH-051 | CISO | Critical | Unlikely | Accepted with controls | CI-SVC-185¦CI-LEGACY-VM-105 | VEN-MH-091¦VEN-COLLIBRA | 2026-11-17 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0200 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0201 | Epic AMS transition knowledge gap 201 | Compliance | CTRL-MH-052 | POL-MH-052 | CDAO | High | Likely | Open | CI-SVC-186¦CI-LEGACY-VM-114 | VEN-MH-092¦VEN-MH-016 | 2026-11-18 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0201 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0202 | Data analytics AMS scope ambiguity 202 | Financial | CTRL-MH-053 | POL-MH-053 | CTO | Medium | Possible | Mitigating | CI-SVC-187¦CI-LEGACY-VM-123 | VEN-MH-093¦VEN-MH-021 | 2026-11-19 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0202 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0203 | PHI control evidence missing after migration 203 | Clinical Safety | CTRL-MH-054 | POL-MH-054 | CFO | Critical | Unlikely | Accepted with controls | CI-SVC-188¦CI-SVC-132 | VEN-MH-094¦VEN-MH-026 | 2026-11-20 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0203 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0204 | Cloud run cost exceeds baseline 204 | Sourcing | CTRL-MH-055 | POL-MH-055 | AI Governance Council | High | Likely | Open | CI-SVC-189¦CI-SVC-141 | VEN-MH-095¦VEN-MH-031 | 2026-11-21 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0204 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0205 | Integration backlog affects clinical continuity 205 | Operational | CTRL-MH-056 | POL-MH-056 | CISO | Medium | Possible | Mitigating | CI-SVC-190¦CI-SVC-150 | VEN-MH-096¦VEN-MH-036 | 2026-11-22 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0205 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0206 | CDAO stewardship capacity constraint 206 | Compliance | CTRL-MH-057 | POL-MH-057 | CDAO | Critical | Unlikely | Accepted with controls | CI-SVC-191¦CI-SVC-159 | VEN-MH-097¦VEN-MH-041 | 2026-11-23 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0206 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0207 | BAA chain incomplete for AI workflow 207 | Financial | CTRL-MH-058 | POL-MH-058 | CTO | High | Likely | Open | CI-SVC-192¦CI-SVC-168 | VEN-MH-098¦VEN-MH-046 | 2026-11-24 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0207 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0208 | AWS-hosted workload not modernized 208 | Clinical Safety | CTRL-MH-059 | POL-MH-059 | CFO | Medium | Possible | Mitigating | CI-SVC-193¦CI-SVC-177 | VEN-MH-099¦VEN-MH-051 | 2026-11-25 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0208 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0209 | Epic AMS transition knowledge gap 209 | Sourcing | CTRL-MH-060 | POL-MH-060 | AI Governance Council | Critical | Unlikely | Accepted with controls | CI-SVC-194¦CI-SVC-186 | VEN-MH-100¦VEN-MH-056 | 2026-11-26 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0209 | Risk and Compliance | 2026-06-04 | 0.83 | true
RISK-MH-0210 | Data analytics AMS scope ambiguity 210 | Operational | CTRL-MH-061 | POL-MH-061 | CISO | High | Likely | Open | CI-SVC-195¦CI-SVC-195 | VEN-MH-101¦VEN-MH-061 | 2026-11-27 | Control evidence, owner attestation, run-cost and continuity proof | Risk register | RISK-MH-0210 | Risk and Compliance | 2026-06-04 | 0.83 | true