# Lakeshore Enterprise Finance & Treasury Modernization: Kyriba Rollout, Corporate Controls, Reporting Rationalization, Vendor Optimization & Value Realization

# Lakeshore Enterprise Finance & Treasury Modernization: Kyriba Rollout, Corporate Controls, Reporting Rationalization, Vendor Optimization & Value Realization

A board-grade Mobilize & Go-Decision Packet produced by the Moves Expert Kernel for this Move. The mobilization-plan structure is inherited from the curated Domain Function Pack; every figure is the kernel’s, and the go-decision is the kernel’s real verdict — never an invented `go`.

# NO-GO — the Move does not pay back on current assumptions; do not mobilize.

Base-case net return is not positive — the Move does not pay back on current assumptions.

Value cannot be monetised to a hard dollar figure — the gross value range rests on a seed-gap proxy. The CFO will not approve a fabricated return; the case must close the baseline gap first.

8 baseline metric(s) are seed gaps (coverage 33%): Net interest margin (NIM), Liquidity coverage ratio (LCR), Net stable funding ratio (NSFR), Economic-value-of-equity rate sensitivity, Net-interest-income rate sensitivity, Loan-to-deposit ratio, Deposit beta, Common equity tier 1 (CET1) capital ratio. The case is grounded only on what is recorded.

# This packet inherits the curated Finance, treasury & ALM mobilization outline — 8 sections, the plan structure is not improvised.

This Mobilize & Go-Decision Packet inherits the curated Finance, treasury &amp; ALM mobilization-plan outline from the bound Domain Function Pack. The agent does not improvise the plan — every section below is a curated, function-calibrated heading.

| # | Section heading | Curated guidance |
| --- | --- | --- |
| 1 | Executive answer | State the funding ask, the headline value separated into margin and return, capital and funding efficiency, and finance productivity, the time-to-value band, and the go / hold recommendation in one read. |
| 2 | Baseline model | Anchor every value claim to a measured baseline operating metric — NIM, cost of funds, forecast accuracy, cycle time, buffer levels, return on equity. Where a baseline is a seed gap, say so and state what closing it requires before funding. |
| 3 | Scenario-conditional value forecast and haircuts | Build the forecast from the value-model benchmark ranges, then apply each dominant haircut factor — rate-environment contingency, regulatory floors and risk-appetite ceilings, data and model readiness, governance and adoption — explicitly and show the haircut math. Present rate-dependent gains as scenario-conditional, never certain. |
| 4 | Cost and effort | Cost the build, the integration to the ALM, general-ledger, FP&A, treasury, and liquidity systems, the model risk-management and validation overhead, and the operating-model change in the finance and treasury organisation. |
| 5 | Sensitivity and downside | Show how the case moves under an adverse rate scenario, tighter regulatory constraints, and partial adoption. State the downside the CFO and board are underwriting. |
| 6 | Model governance posture | State how any ALM, capital, forecasting, or behavioural model is governed under the model risk-management framework, validated, and made explainable to the board and examiners. |
| 7 | Kill criteria and conditions to proceed | Name the conditions under which the Move should not be funded and the evidence — data lineage, model validation, governance sign-off — that must be in hand before the gate. |
| 8 | Tower measurement plan | State exactly which operating metrics Tower will track to prove the forecast and the measurement cadence, including the rate-cycle-dependent margin and buffer measures. |

# The value to mobilize is a planning range built on curated benchmark proxies — the kernel honestly blocks a claimable dollar payback.

Net 3-year value is carried as a planning range — point $113. It rests on the Function Pack's curated benchmark proxies, so the kernel honestly blocks a claimable dollar payback until the tenant's own metrics land.

These foundational and governance lanes are the first money the launch funds — they stand up the operating spine before any pilot value is claimed.

| Workstream | Base cost | Headcount | Duration |
| --- | --- | --- | --- |
| Integration | $776K | 4 | 6 mo |
| Data | $716K | 4.5 | 5 mo |
| Foundational | $163K | 1 | 4 mo |
| Data governance | $397K | 2 | 6 mo |

# The readiness gates below are scored from the kernel state — the blocked gates are exactly what hold the go-decision.

5 readiness gates are scored from the kernel state. 2 are blocked — and the blocked gates are exactly what hold the go-decision. The heatmap makes the launch pre-conditions explicit, not assumed.

A blocked gate is a hard pre-condition — the launch gate stays held until every blocked row is cleared.

# 4 of 12 metrics are wired to a recorded baseline — the rest are honest seed gaps.

Tower will measure 12 committed value metrics — 4 are wired to a recorded baseline. The remaining 8 are honest seed gaps, carried with a capture plan, never dropped.

The value loop does not yet close — seed-gapped baselines remain.

| Metric | Baseline |
| --- | --- |
| Net interest margin (NIM) Seed gap | SEED GAP — not recorded |
| SEED GAP — not measurable until the baseline for "Net interest margin (NIM)" is captured (expected source: The general ledger and the ALM system, reconciling interest income and expense against average earning-asset balances.). Tower cannot verify movement on this metric before the gap is closed. |  |
| Cost of funds Wired | 4.6 percent (blended) |
| Measurable now from the tenant baseline (Debt & FX exposure (treasury_kyriba)). The improvement target is set with the tenant — the Function Pack benchmark (0.5–3.5 % annualised on average funding, planning-range) frames the range, it is not a committed target. |  |
| Liquidity coverage ratio (LCR) Seed gap | SEED GAP — not recorded |
| SEED GAP — not measurable until the baseline for "Liquidity coverage ratio (LCR)" is captured (expected source: The liquidity-risk and regulatory-reporting systems, computing HQLA and stressed outflows under the LCR rule.). Tower cannot verify movement on this metric before the gap is closed. |  |
| Net stable funding ratio (NSFR) Seed gap | SEED GAP — not recorded |
| SEED GAP — not measurable until the baseline for "Net stable funding ratio (NSFR)" is captured (expected source: The liquidity-risk and regulatory-reporting systems, computing available and required stable funding under the NSFR rule.). Tower cannot verify movement on this metric before the gap is closed. |  |
| Economic-value-of-equity rate sensitivity Seed gap | SEED GAP — not recorded |
| SEED GAP — not measurable until the baseline for "Economic-value-of-equity rate sensitivity" is captured (expected source: The ALM system, running the EVE measurement under the institution’s rate-shock scenario set.). Tower cannot verify movement on this metric before the gap is closed. |  |
| Net-interest-income rate sensitivity Seed gap | SEED GAP — not recorded |
| SEED GAP — not measurable until the baseline for "Net-interest-income rate sensitivity" is captured (expected source: The ALM system, running the net-interest-income simulation under the institution’s rate scenarios.). Tower cannot verify movement on this metric before the gap is closed. |  |
| Loan-to-deposit ratio Seed gap | SEED GAP — not recorded |
| SEED GAP — not measurable until the baseline for "Loan-to-deposit ratio" is captured (expected source: The general ledger and treasury systems, aggregating loan and deposit balances.). Tower cannot verify movement on this metric before the gap is closed. |  |
| Deposit beta Seed gap | SEED GAP — not recorded |
| SEED GAP — not measurable until the baseline for "Deposit beta" is captured (expected source: The ALM system and deposit-analytics models, comparing historical deposit-rate moves against benchmark-rate moves.). Tower cannot verify movement on this metric before the gap is closed. |  |
| Common equity tier 1 (CET1) capital ratio Seed gap | SEED GAP — not recorded |
| SEED GAP — not measurable until the baseline for "Common equity tier 1 (CET1) capital ratio" is captured (expected source: The capital and regulatory-reporting systems, computing CET1 capital and risk-weighted assets under the regulatory capital framework.). Tower cannot verify movement on this metric before the gap is closed. |  |
| Return on equity (ROE) Wired | 11.8 percent (EBITDA margin proxy) |
| Measurable now from the tenant baseline (Revenue & cost baseline (finance_performance)). The improvement target is set with the tenant — the Function Pack benchmark (8–15 % return on average equity, planning-range) frames the range, it is not a committed target. |  |
| Financial-forecast accuracy Wired | 78 percent (forecast vs actual) |
| Measurable now from the tenant baseline (FP&A reconciliation (Lakeshore enterprise context load V1)). The improvement target is set with the tenant — the Function Pack benchmark (2–10 % mean absolute forecast variance, planning-range) frames the range, it is not a committed target. |  |
| Planning and close cycle time Wired | 8.5 business days to close |
| Measurable now from the tenant baseline (Month-end close baseline (operations_business_process)). The improvement target is set with the tenant — the Function Pack benchmark (3–12 business days per cycle, planning-range) frames the range, it is not a committed target. |  |

# Every open action — kill criteria, critic blockers, and the precise seed gaps — is named, never blank.

Nothing that gates the launch is unowned. Every open action — the kill criteria, the open critic blockers, and the precise seed gaps — carries a named owner and an explicit gate impact.

The widest bars are the gate-blocking actions — the critical path to a clean go.

| Open action | Owner | Gate impact |
| --- | --- | --- |
| Hold against the kill criterion: Net return is negative in the conservative case (-8561340.29). Kill or re-shape if the downside cannot be lifted above zero. Blocks go-live | Move sponsor (to be confirmed with the tenant) | Kill criterion kill_downside_negative — the launch gate stays held while this condition could be tripped. |
| Hold against the kill criterion: The baseline seed gap that blocks monetisation is not closed before the gate — without it the return is unverifiable. Blocks go-live | Move sponsor (to be confirmed with the tenant) | Kill criterion kill_monetisation_unresolved — the launch gate stays held while this condition could be tripped. |
| Hold against the kill criterion: Baseline coverage stays below acceptable level — 8 seed gap(s) remain unresolved at the gate. Blocks go-live | Move sponsor (to be confirmed with the tenant) | Kill criterion kill_baseline_unclosed — the launch gate stays held while this condition could be tripped. |
| Resolve the open critic blocker: Value cannot be monetised to a hard dollar figure — the gross value range rests on a seed-gap proxy. The CFO will not approve a fabricated return; the case must close the baseline gap first. Blocks go-live | Move sponsor (to be confirmed with the tenant) | A critic blocker holds the launch gate until it is resolved. |
| Resolve the open critic blocker: 8 baseline metric(s) are seed gaps (coverage 33%): Net interest margin (NIM), Liquidity coverage ratio (LCR), Net stable funding ratio (NSFR), Economic-value-of-equity rate sensitivity, Net-interest-income rate sensitivity, Loan-to-deposit ratio, Deposit beta, Common equity tier 1 (CET1) capital ratio. The case is grounded only on what is recorded. Blocks go-live | Move sponsor (to be confirmed with the tenant) | A critic blocker holds the launch gate until it is resolved. |
| Capture "Net interest margin (NIM)" — "Net interest margin (NIM)" is not recorded — this function expects it; it is sourced from The general ledger and the ALM system, reconciling interest income and expense against average earning-asset balances.; its absence blocks the baseline and the value forecast. Pre-launch | Move sponsor (to be confirmed with the tenant) · expected source: The general ledger and the ALM system, reconciling interest income and expense against average earning-asset balances. | A seed gap weakens the baseline — close it before the value loop is locked. |
| Capture "Liquidity coverage ratio (LCR)" — "Liquidity coverage ratio (LCR)" is not recorded — this function expects it; it is sourced from The liquidity-risk and regulatory-reporting systems, computing HQLA and stressed outflows under the LCR rule.; its absence blocks the baseline and the value forecast. Pre-launch | Move sponsor (to be confirmed with the tenant) · expected source: The liquidity-risk and regulatory-reporting systems, computing HQLA and stressed outflows under the LCR rule. | A seed gap weakens the baseline — close it before the value loop is locked. |
| Capture "Net stable funding ratio (NSFR)" — "Net stable funding ratio (NSFR)" is not recorded — this function expects it; it is sourced from The liquidity-risk and regulatory-reporting systems, computing available and required stable funding under the NSFR rule.; its absence blocks the baseline and the value forecast. Pre-launch | Move sponsor (to be confirmed with the tenant) · expected source: The liquidity-risk and regulatory-reporting systems, computing available and required stable funding under the NSFR rule. | A seed gap weakens the baseline — close it before the value loop is locked. |
| Capture "Economic-value-of-equity rate sensitivity" — "Economic-value-of-equity rate sensitivity" is not recorded — this function expects it; it is sourced from The ALM system, running the EVE measurement under the institution’s rate-shock scenario set.; its absence blocks the baseline and the value forecast. Pre-launch | Move sponsor (to be confirmed with the tenant) · expected source: The ALM system, running the EVE measurement under the institution’s rate-shock scenario set. | A seed gap weakens the baseline — close it before the value loop is locked. |
| Capture "Net-interest-income rate sensitivity" — "Net-interest-income rate sensitivity" is not recorded — this function expects it; it is sourced from The ALM system, running the net-interest-income simulation under the institution’s rate scenarios.; its absence blocks the baseline and the value forecast. Pre-launch | Move sponsor (to be confirmed with the tenant) · expected source: The ALM system, running the net-interest-income simulation under the institution’s rate scenarios. | A seed gap weakens the baseline — close it before the value loop is locked. |
| Capture "Loan-to-deposit ratio" — "Loan-to-deposit ratio" is not recorded — this function expects it; it is sourced from The general ledger and treasury systems, aggregating loan and deposit balances.; its absence blocks the baseline and the value forecast. Pre-launch | Move sponsor (to be confirmed with the tenant) · expected source: The general ledger and treasury systems, aggregating loan and deposit balances. | A seed gap weakens the baseline — close it before the value loop is locked. |
| Capture "Deposit beta" — "Deposit beta" is not recorded — this function expects it; it is sourced from The ALM system and deposit-analytics models, comparing historical deposit-rate moves against benchmark-rate moves.; its absence blocks the baseline and the value forecast. Pre-launch | Move sponsor (to be confirmed with the tenant) · expected source: The ALM system and deposit-analytics models, comparing historical deposit-rate moves against benchmark-rate moves. | A seed gap weakens the baseline — close it before the value loop is locked. |
| Capture "Common equity tier 1 (CET1) capital ratio" — "Common equity tier 1 (CET1) capital ratio" is not recorded — this function expects it; it is sourced from The capital and regulatory-reporting systems, computing CET1 capital and risk-weighted assets under the regulatory capital framework.; its absence blocks the baseline and the value forecast. Pre-launch | Move sponsor (to be confirmed with the tenant) · expected source: The capital and regulatory-reporting systems, computing CET1 capital and risk-weighted assets under the regulatory capital framework. | A seed gap weakens the baseline — close it before the value loop is locked. |