## Epic Optimization Roadmap
Meridian Health System — Epic Optimization Roadmap (58→80/100)
Module | Current Score | Target Score | Current Adoption % | Target Adoption % | Config Changes Required | Training Required | Wave | Score Impact | Value $M
Epic Prior Auth Automation | 8 | 85 | 8% | 80% | Activate Epic Prior Auth module. Configure payer-specific rules for top 8 payers. Connect to Cohere Health via FHIR R4. | All prior auth staff (142 FTE). Physician workflow for prior auth requests. | 1 | +8 points | $37.6M — CMS mandate Jan 2027
Epic Healthy Planet (Pop Health) | 22 | 75 | 22% | 65% | Activate care gap workflows. Configure quality measure tracking for MA Star Rating. Enable patient outreach templates. | Care management team (84 FTE). Population health nurses. | 1 | +6 points | $24M MA Star Rating revenue
Epic Tapestry (Health Plan) | 44 | 80 | 44% | 75% | Configure MA plan benefit structures. Enable quality measure automated tracking. Connect to CMS reporting API. | Health plan operations team (48 FTE). | 1 | +5 points | $24M — MA Star Rating composite
Epic Cogito (Analytics) | 28 | 70 | 28% | 65% | Activate Cogito dashboards for service line leaders. Configure automated daily operational reports. Replace manual Clarity queries. | Service line directors (42 FTE). Finance team (36 FTE). | 1 | +5 points | $1.8M manual analytics cost
Epic GPT / Ambient Documentation | 12 | 60 | 12% | 55% | Configure ambient documentation for 3 specialties. Integrate with physician workflow. Set up review and approval process. | All physicians (732 FTE). Physician IT champions (24 FTE). | 1 | +4 points | $42M physician productivity
Epic Cheers (CRM Patient Outreach) | 18 | 65 | 18% | 55% | Configure care gap outreach campaigns. Enable appointment reminder automation. Set up readmission prevention workflows. | Patient access team (68 FTE). Care managers (42 FTE). | 2 | +4 points | $4.2M outreach efficiency
MyChart Patient Portal | 34 | 65 | 34% | 60% | Simplify MyChart enrollment at registration. Enable MyChart Bedside for inpatients. Configure self-scheduling for 8 specialties. | Registration staff (284 FTE). Patient experience team (18 FTE). | 1 | +4 points | $4.2M patient engagement
Epic Beacon (Oncology) | 52 | 85 | 52% | 80% | Complete oncology workflow templates. Configure chemotherapy administration protocols. Enable treatment plan documentation. | Oncology nurses and physicians (68 FTE). | 2 | +3 points | $1.4M oncology efficiency
Epic Welcome (Self Check-In) | 42 | 80 | 42% | 72% | Update kiosk software. Add Spanish language option. Integrate with Epic scheduling for real-time wait time display. | Front desk staff (124 FTE). Patients — communication campaign. | 2 | +2 points | $0.6M registration cost
Epic Rover (Mobile Nursing) | 52 | 82 | 52% | 78% | Expand device availability (currently 1 device per 3 nurses). Configure nursing-specific workflows per unit. | All nursing staff (8,400 FTE). Nurse managers (284 FTE). | 2 | +2 points | $0.7M nursing efficiency
Epic Radiant (Radiology) | 82 | 92 | 82% | 90% | Activate AI-assisted report prioritization. Enable critical result auto-notification. | Radiologists (24 FTE). Radiology techs (68 FTE). | 3 | +2 points | $0.3M radiology efficiency
Epic Willow (Pharmacy) | 76 | 90 | 76% | 88% | Activate clinical decision support alerts tier 2. Enable automated refill management. | Pharmacists (142 FTE). Pharmacy techs (84 FTE). | 3 | +2 points | $0.8M pharmacy efficiency
Epic Scheduling AI | 0 | 50 | 0% | 40% | License activation. Configure no-show prediction model. Set up automated recall for no-show patients. | Scheduling staff (186 FTE). Department coordinators (48 FTE). | 2 | +3 points | $1.1M no-show reduction
Epic Care Everywhere (HIE) | 61 | 82 | 61% | 78% | Enable automated external record retrieval. Configure reconciliation workflow for incoming records. | All clinicians who receive referrals (284 FTE). | 3 | +2 points | $0.9M care coordination

## Score Projection
Meridian — Epic Optimization Score Projection by Wave
Milestone | Epic Score | MyChart % | Modules Activated | Annual Value Unlocked $M | Timeline
Current state | 58 | 34% | 4 | 0 | Today
Wave 1 complete (6 modules activated) | 72 | 55% | 10 | 114 | Month 6
Wave 2 complete (4 more modules) | 80 | 65% | 14 | 124 | Month 12
Wave 3 complete (full optimization) | 88 | 72% | 22 | 128 | Month 18
Benchmark (peer health systems) | 80 | 60% | 18 | N/A | N/A