## Integration Enhancement Plan
Meridian Health System — Integration Enhancement Plan (CMS Mandate Jan 2027)
Integration | Current State | Enhancement Required | Standard | Effort (Weeks) | Cost $M | CMS Mandate? | Priority
Epic → Cohere Health (Prior Auth AI) | Pilot — 60% complete. 3 payers only. | Complete FHIR R4 integration for all 8 priority payers. Configure automated auth request workflow. Enable real-time decision return. | FHIR R4 | 8 | 0.4 | Yes — CMS mandate Jan 2027 | Critical
Epic → Medicare FFS (CMS Direct) | Manual claim submission via intermediary. | Activate CMS electronic prior auth API (Da Vinci standard). Direct submission for Medicare prior auth. | FHIR R4 / Da Vinci | 6 | 0.3 | Yes — primary mandate | Critical
Epic → UnitedHealthcare MA | Manual portal submission. 18% denial rate. | Electronic prior auth via UHC API. Automated denial reason capture. | FHIR R4 | 4 | 0.2 | Yes — MA plans included | Critical
Epic → Humana MA | Manual. 19.8% denial rate. | Electronic prior auth via Humana API. Real-time decision for 80% of request types. | FHIR R4 | 4 | 0.2 | Yes | Critical
Epic → Aetna | 31% electronic currently. | Expand electronic coverage to 95%. Enable automated appeal submission for denied auths. | FHIR R4 | 3 | 0.1 | Yes | High
Epic → Cigna | 28% electronic currently. | Activate Cigna real-time prior auth API for outpatient procedures. | FHIR R4 | 3 | 0.1 | Yes | High
Epic → Medicaid NC (MMIS) | 12% electronic. Most manual. | Connect to NC MMIS electronic prior auth gateway. High volume — 1,440 requests/month. | NC MMIS API | 6 | 0.3 | Yes — state mandate | High
Epic → Ensemble Health Partners | Claims outbound feed. No prior auth feedback loop. | Add prior auth status feed from Ensemble back to Epic. Real-time denial reason capture. | HL7 v2.3 enhanced | 4 | 0.2 | Indirect | High
Epic → 3M HIS Coding AI | Daily batch. Partial integration. | Real-time coding suggestion feed. Automated coding accuracy tracking dashboard. | FHIR R4 | 4 | 0.2 | No | Medium
Epic → Nuance DAX / AWS Bedrock | Pilot only — 10 physicians. | Enterprise rollout configuration. Connect to all physician workflows. Approval and review workflow. | Epic Open API | 6 | 0.3 | No | High
Epic Cerner → Epic (2 hospitals) | ADT feed only. Records not shared. | Data migration programme. Patient record merge. Medication history reconciliation. | HL7 ADT + FHIR | 52 | 2.8 | No — migration | Critical — Q4 2026
Epic → CMS Quality Reporting | Monthly manual submission. | Automated HEDIS and quality measure reporting. MA Star Rating data submission automated. | CMS API / FHIR | 6 | 0.3 | Yes — quality reporting | High
TOTAL INTEGRATION PROGRAMME |  |  |  | 106 | 5.4