## Promotion Matrix
module | schema_table | provisional_canonical_object_family | mapping_confidence | current_authority | identity_map_required | publication_trigger | required_evidence | historical_backfill | dual_run_requirement | reconciliation_rule | cutover_dependency | rollback_path | status
Source | public.evidence | knowledge.evidence | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; evidence_type; confidence_level; evidence_payload | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.home_knowledge_evidence_sources | knowledge.evidence | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; source_name; source_date; source_owner; source_status; lineage; source_payload | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_artifact_chunks | knowledge.evidence_chunk | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | artifact_id; source_event_id; provenance; confidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_artifact_facts | knowledge.fact | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | artifact_id; source_event_id; provenance; confidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_contract_evidence_manifests | knowledge.evidence_manifest | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id; source_artifact_id; evidence_pack_name; source_type | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_contract_evidence_metrics | knowledge.metric_observation | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id; evidence_family; confidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_contract_evidence_rows | knowledge.evidence_fragment_or_contract_fact_assertion | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id; source_artifact_id; evidence_family; source_sheet; source_row_number; confidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_contract_optimization_findings | knowledge.contract_finding | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id; confidence; evidence_refs | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_contract_optimization_levers | knowledge.value_driver_or_commercial_lever | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_contract_optimization_profiles | knowledge.contract_profile | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id; source_type; evidence_artifact_ids; evidence_refs | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_event_facts | knowledge.fact | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id; source_method; source_citation; confidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_meeting_outcomes | to_be_mapped_after_live_profile | unresolved | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | artifact_id; source_event_id; provenance; confidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_value_chain | knowledge.value_flow_step | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_value_levers | knowledge.value_driver_or_lever | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id; confidence; evidence_refs; insufficient_evidence; missing_evidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_value_lines | to_be_mapped_after_live_profile | unresolved | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | evidence_artifact_id | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_value_states | knowledge.value_state_or_readiness | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id; evidence_ledger_ids | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_vendor_commitments | knowledge.commercial_commitment | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | artifact_id; source_event_id; provenance; confidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.source_vendor_proposal_facts | knowledge.proposal_fact_assertion | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_event_id; proposal_artifact_id; source_quote; source_pointer; confidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Source | public.vendor_contracts | knowledge.contract | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | No parsed lineage fields; inspect write path before promotion | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | cio_tower.measures | knowledge.metric_definition | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | artifact_default | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | cio_tower.tool_identity_aliases | to_be_mapped_after_live_profile | unresolved | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_actions | knowledge.action_or_decision | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | evidence_state | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_agent_outcomes | knowledge.outcome | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; evidence_state | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_benefit_realization | knowledge.metric_observation | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; confidence; evidence_state | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_context_facts | knowledge.fact_assertion | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | confidence; evidence_state; evidence_keys | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_context_relationships | knowledge.relationship_assertion | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | No parsed lineage fields; inspect write path before promotion | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_dora_metrics | knowledge.metric_observation | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; evidence_state | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_evidence_items | knowledge.evidence | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | evidence_key; evidence_type; citation_label; citation_locator; evidence_pointer; evidence_state; confidence | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_initiatives | knowledge.program | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_persona_productivity | knowledge.metric_observation | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; confidence; evidence_state | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_risk_governance | knowledge.risk_control | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; evidence_state | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_spend_contracts | knowledge.contract | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; evidence_state | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.ai_control_tool_usage_monthly | knowledge.metric_observation | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; evidence_state | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.application_portfolio | knowledge.application | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | No parsed lineage fields; inspect write path before promotion | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.enterprise_context_records | to_be_mapped_after_live_profile | unresolved | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_id; source_file_id; source_system; source_record_id; source_file; source_sheet; source_row_number; confidence; evidence_pointer | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.tower_cmdb_cis | knowledge.application | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source_system | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.tower_read_model_vendors | knowledge.vendor | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | evidence_ids; citations; lineage | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized
Tower | public.use_cases | knowledge.program | provisional | Candidate/domain-derived; not canonical until promoted | governance.object_identity_map | accepted/reviewed/published row state plus tenant and lineage validation | source; source_engagement_id; source_file_id | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Healthcare publication/consumption framework certified first | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | candidate_not_authorized