ABARVA · MOVES · EXPERT KERNEL

Mobilize & go-decision packet

Contact Center AI Routing — Apex Retail

Tenant key apex-retail · Move ref apex:move:contact-center-ai-routing

Generated 2026-05-20

The mobilization plan, adoption & change approach, the value-measurement model handed to Tower and the go-decision pack.

# Mobilize & Handoff — adoption, measurement, go-decision

Move: Contact Center AI Routing (apex-retail)

Go-decision: NO GO

No-go: 2 Mobilize kill trigger(s) fired (measurement_unwired, business_case_blocker_open). The Move is not ready to leave Moves. See the fix-conditions for what must change before it is reconsidered.

## Mobilize readiness

| Owned (named operating-model owner) | Yes |
| --- | --- |
| Adoptable (change approach supports the curve) | Yes |
| Measurable (value loop closes to Tower) | NO |
| Operating-model owner | Mariana Rojas (WFM Lead, Customer Care Operations) |
| Overall change load | high |
| Adoption confidence | 0.6 |
| Hypercare window | 6 week(s) |

## Fired kill triggers — verbatim

- measurement_unwired: 1 committed value metric(s) cannot be wired to a recorded baseline: Cost per contact (labour).

Fix-condition: Revisit when every committed metric is wired to a Discover baseline value or an owned, dated plan to capture one.

- business_case_blocker_open: The business-case critic has 1 open blocker(s): cfo_monetisation_blocked.

Fix-condition: Revisit when the business-case critic reports no open blocker.

## Conditions to clear

- measurement_unwired: Revisit when every committed metric is wired to a Discover baseline value or an owned, dated plan to capture one.

- business_case_blocker_open: Revisit when the business-case critic reports no open blocker.

## Adoption & change approach — seven dimensions

| Dimension | Magnitude | Recommendation | Owner |
| --- | --- | --- | --- |
| impacted_roles | high | Three roles change; the agent role changes most. Stage the rollout by team rather than flipping the floor at once. | WFM Lead |
| process_variance | high | Routing logic varies handling materially; recommend a process redesign workstream lands before the change rollout (it is budgeted in the Design & Plan estimate). | Program Lead |
| training_load | moderate | Role-based training: a heavier curriculum for agents (assist tooling), a lighter one for managers and WFM analysts. | Enablement Lead |
| incentive_change | moderate | Re-point agent performance incentives away from raw handle time toward resolution quality, so the new routing is not fought by the old scorecard. | Customer Care Operations |
| manager_adoption | high | Manager reinforcement is the highest-risk layer. Recommend a dedicated manager-enablement track and explicit reinforcement in the hypercare window. | WFM Lead |
| communications | moderate | Address the agent narrative directly — AI routing augments agents, it does not replace them; the WFM lead is on record preferring agent-assist over IVR replacement. | Program Lead |
| hypercare | moderate | A 6-week hypercare window with elevated floor support and a daily routing-quality review; exit when adoption and CSAT hold for two consecutive weeks. | WFM Lead |

## Impacted roles

| Role | Headcount | Change | What changes |
| --- | --- | --- | --- |
| Customer Care agent | Not recorded — seed gap | high | Agents move from manual call handling to AI-routed, assist-augmented handling; harder calls now reach them. |
| Customer Care team manager | Not recorded — seed gap | moderate | Managers coach to new routing/assist metrics and reinforce the changed handling pattern daily. |
| Workforce-management analyst | Not recorded — seed gap | moderate | Capacity planning re-baselined around the new containment and AHT mix. |

## Adoption risks — surfaced

- [concern] adoption_manager_layer_heavy: Manager adoption is a high-magnitude change. Adoption fails at the manager layer more than anywhere else — manager reinforcement must be explicitly resourced, not assumed.

- [note] adoption_headcount_gap_customer_care_agent: Impacted headcount for 'Customer Care agent' is not recorded — training load and communications scale cannot be sized precisely.

- [note] adoption_headcount_gap_customer_care_team_manager: Impacted headcount for 'Customer Care team manager' is not recorded — training load and communications scale cannot be sized precisely.

- [note] adoption_headcount_gap_workforce_management_analyst: Impacted headcount for 'Workforce-management analyst' is not recorded — training load and communications scale cannot be sized precisely.

- [note] adoption_seed_gap_impacted_roles: The 'Impacted roles' assessment rests on a benchmark proxy / seed gap, not tenant data — validate it before the gate.

- [note] adoption_seed_gap_training_load: The 'Training load' assessment rests on a benchmark proxy / seed gap, not tenant data — validate it before the gate.

## Value-measurement model — handed to Tower

3 of 4 metric(s) wired to a recorded baseline (coverage 75%). Value loop closes: NO.

| Metric | Baseline | Target | Cadence | Owner |
| --- | --- | --- | --- | --- |
| Contact Center Containment | 28 | 40 | monthly | WFM Lead |
| Average Handle Time | 7.2 | 6.5 | monthly | WFM Lead |
| CSAT (post-interaction) | 4.1 | 4.4 | quarterly | Customer Care Operations |
| Cost per contact (labour) | Not recorded — seed gap | Not recorded — seed gap | monthly | CS Ops |

## Critic findings — surfaced, not hidden

- [blocker / cfo] cfo_monetisation_blocked: Value cannot be monetised to a hard dollar figure — the gross value range rests on a seed-gap proxy. The CFO will not approve a fabricated return; the case must close the baseline gap first.

- [concern / data] data_baseline_seed_gaps: 4 baseline metric(s) are seed gaps (coverage 60%): Cost per contact (labour), Annual contact volume, Channel mix (voice/chat/IVR split), QA error rate. The case is grounded only on what is recorded.

- [concern / data] data_top_mover_is_proxy: 2 of the top-3 case-moving assumptions stand in for absent tenant data (annual_contact_volume, cost_per_contact). Validating these is the highest-leverage next step.

Every figure in this document is produced by the Moves Expert Kernel from the tenant’s audited substrate. Absent data is declared a seed gap, never invented. Effort rests on a researched planning rate card — a market range, not a quote. Generated by AbarVa · Moves.