ABARVA · MOVES · EXPERT KERNEL

Costed business-case pack

Ambient Clinical Value Chain Activation — Meridian Health System

Tenant key meridian-health · Move ref meridian:move:ambient-clinical-value-chain-activation

Generated 2026-05-20

The full Design & Plan business case: costed roadmap, value-and-effort profile and the human+agent RACI, in CFO-readable prose.

# Design & Plan — costed business-case pack

Move: Ambient Clinical Value Chain Activation (meridian-health)

Verdict: SHAPE — do not fund as-is

The critic raised 1 blocker(s) — fund only once they are resolved. Re-shape the Move to close them.

## Investment & return

| Investment (costed roadmap) | $2,481,455 – $4,087,102 (base $2,919,358) |
| --- | --- |
| Net return | $3,460,898 – $10,727,545 (base $7,459,142) |
| Payback | Not monetisable — the value rests on a baseline seed gap, so the kernel returns no payback rather than a fabricated one. |

## AI-build vs. business-change effort

| AI-build effort | $2,136,525 |
| --- | --- |
| Business-change effort | $782,833 |
| Business-change share | 27% |

Business change is 27% of effort — a credible build-vs-change balance for an AI Move where value depends on people changing how they work.

## Costed roadmap — per-phase investment & value

| Phase | Investment | Cumulative | Annual value unlocked | Foundational |
| --- | --- | --- | --- | --- |
| Phase 0 — Unified ambient telemetry foundation | $265,350 | $265,350 | $0 | Yes — enablement only |
| Phase 1 — CDI integration + HCC feedback loop | $1,481,283 | $1,746,633 | $1,210,825 | No |
| Phase 2 — Template governance + consolidation pilot | $404,125 | $2,150,758 | $1,210,825 | No |
| Phase 3 — Adoption + run | $768,600 | $2,919,358 | $1,037,850 | No |

## Three-scenario sensitivity

| Scenario | Investment | Net value | Net return | ROI |
| --- | --- | --- | --- | --- |
| Base | $2,919,358 | $10,378,500 | $7,459,142 | Not recorded — seed gap |
| Conservative | $4,087,102 | $7,548,000 | $3,460,898 | Not recorded — seed gap |
| Upside | $2,481,455 | $13,209,000 | $10,727,545 | Not recorded — seed gap |

What breaks the case: The case breaks if the baseline seed gap is not closed — without the missing unit economics the value range is a proxy, not a forecast.

Downside read: The conservative case cannot be expressed in hard dollars — the value rests on a seed-gap proxy. Close the baseline gap before reading the downside as a number.

## Human + agent RACI — decision rights

The RACI matrix passes every honesty rule — it is governable as drawn.

| Decision | Kind | Accountable | Responsible |
| --- | --- | --- | --- |
| Approve funding for the Move | governance | Sarah Chen (CIO, Executive Sponsor) | Dr. Morales (CMIO) |
| Select the ambient-to-CDI integration architecture | design | Solution Architect | Solution-Design Agent |
| Clear the HIPAA BAA / 42 CFR Part 2 / Info Blocking review | governance | Privacy & Compliance Office | Dr. Morales (CMIO) |
| Execute the CDI integration + HCC feedback-loop build | delivery | Dr. Morales (CMIO) | Build Agent |
| Approve the 18-site ambient consolidation pilot go-live | governance | Dr. Larsson (CMO, Clinical Sponsor) | Dr. Morales (CMIO) |
| Own the Phase 5 vendor-rationalisation ratification | governance | Dr. Morales (CMIO) | Sarah Chen (CIO, Executive Sponsor) |

## Surfaced flags — roadmap, RACI, critic

- [critic/blocker] Value cannot be monetised to a hard dollar figure — the gross value range rests on a seed-gap proxy. The CFO will not approve a fabricated return; the case must close the baseline gap first.

- [critic/concern] 3 baseline metric(s) are seed gaps (coverage 75%): Cost-per-clinician-hour conversion coefficient, RAF-to-revenue conversion coefficient, Locum-avoidance dollar basis. The case is grounded only on what is recorded.

- [critic/concern] 3 of the top-3 case-moving assumptions stand in for absent tenant data (cost_per_clinician_hour, locum_avoidance, raf_to_revenue). Validating these is the highest-leverage next step.

## Named assumptions

Every estimate rests on assumptions; the kernel makes them first-class. The three flagged TOP MOVERS move roughly 80% of the case.

- cost_per_clinician_hour  [TOP MOVER · SEED-GAP PROXY]

Fully-loaded cost per clinician hour is a modeled proxy (~$190/hr for attending physicians) until Meridian Finance attests a figure.

Owner: Priya Raman (VP Revenue Cycle) · confidence: low · sensitivity impact: high · source: Modeled proxy — seed gap (Finance attestation pending)

- locum_avoidance  [TOP MOVER · SEED-GAP PROXY]

Cognitive-load recovery avoids a modeled ~$1.2M/yr of locum spend via reduced burnout-driven attrition — no locum-spend baseline is seeded.

Owner: Dr. Larsson (CMO) · confidence: low · sensitivity impact: high · source: Modeled proxy — seed gap

- raf_to_revenue  [TOP MOVER · SEED-GAP PROXY]

Each RAF point recaptured on the MA panel is worth a modeled ~$430/yr per member; the HCC recapture range $3.2–5.1M/yr rests on this.

Owner: Priya Raman (VP Revenue Cycle) · confidence: low · sensitivity impact: high · source: Revenue-Cycle estimate — seed gap

- cdi_queue_uplift

Ambient-to-CDI integration lifts HCC-relevant query volume from ~40/wk toward the 140–180/wk pattern envelope (E25/E47).

Owner: Dr. Morales (CMIO) · confidence: medium · sensitivity impact: high · source: Evidence base E47 — D15 lever outcome envelope

- portfolio_compounding

Parallel-track execution of the three levers produces +25–35% faster outcome realisation than sequential; the low scenario assumes zero.

Owner: Sarah Chen (CIO) · confidence: medium · sensitivity impact: medium · source: Evidence base E32 — pattern-library lever-interaction model

- vendor_council_commissioning

All three ambient vendor councils commission their HCC/DRG feedback loops on the G3 timeline (Abridge priority, DAX trailing 30 days).

Owner: Dr. Morales (CMIO) · confidence: medium · sensitivity impact: medium · source: Evidence base E59 — D18 Risk Register R11

- rate_card

Blended delivery rate card reflects market rates for the integration-engineering and clinical-informatics roles in the estimate.

Owner: Sarah Chen (CIO) · confidence: medium · sensitivity impact: low · source: Benchmark rate card

## Stop / kill criteria

- kill_downside_negative: Net return is negative in the conservative case (3460898.34). Kill or re-shape if the downside cannot be lifted above zero.

- kill_monetisation_unresolved: The baseline seed gap that blocks monetisation is not closed before the gate — without it the return is unverifiable.

- kill_baseline_unclosed: Baseline coverage stays below acceptable level — 3 seed gap(s) remain unresolved at the gate.

- kill_cdi_queue_undershoot: CDI-queue routing stays below 55/week at the G2 gate — the ambient-to-CDI integration, the program's core mechanism, has failed (E45).

- kill_vendor_council_blocked: HCC feedback-loop commissioning is blocked on more than one vendor council — the documentation-quality value component cannot land (E45).

## What Tower will measure

- Primary-care pajama time: baseline 129 → target 100 minutes_per_day. Measurable now from the Epic Signal 18-month trace; no gap. Target is a 25–35 min/day reduction (E47).

- CDI HCC-relevant query volume: baseline 40 → target 160 queries_per_week. Measurable from the CDI queue; the leading indicator of integration health. Target 140–180/wk (E47).

- HCC capture on the MA panel: baseline 58 → target 63 percent. Measurable, but carry the cohort-position caveat. Financial value is NOT verifiable until the RAF-to-revenue coefficient is attested.

- Cost-per-clinician-hour conversion coefficient: baseline Not recorded — seed gap → target Not recorded — seed gap usd_per_hour. SEED GAP — the cognitive-load recovery value cannot be verified in dollars until Meridian Finance attests a fully-loaded clinician-hour cost. Tower cannot confirm financial value before then.

Every figure in this document is produced by the Moves Expert Kernel from the tenant’s audited substrate. Absent data is declared a seed gap, never invented. Effort rests on a researched planning rate card — a market range, not a quote. Generated by AbarVa · Moves.