ABARVA · MOVES · EXPERT KERNEL

Charter business-case skeleton

Ambient Clinical Value Chain Activation — Meridian Health System

Tenant key meridian-health · Move ref meridian:move:ambient-clinical-value-chain-activation

Generated 2026-05-20

The quantified value hypothesis, the CFO-readable business-case skeleton and the stop/kill criteria.

# Charter — quantified value hypothesis & business-case skeleton

Move: Ambient Clinical Value Chain Activation (meridian-health)

## Recommendation

Verdict: SHAPE — do not fund as-is

The critic raised 1 blocker(s) — fund only after they are resolved (see critic findings). Re-shape the Move to close them, do not fund as-is.

| Investment (effort) | $2,481,455 – $4,087,102 (base $2,919,358) |
| --- | --- |
| Net return | $3,460,898 – $10,727,545 (base $7,459,142) |
| Net value (post-haircut, 3yr) | $7,548,000 – $13,209,000 (base $10,378,500) |
| Payback | Not monetisable — the value rests on a baseline seed gap, so the kernel returns no payback rather than a fabricated one. |
| Monetisable | No |

## Current-state baseline

Coverage: 75% of metrics are recorded; 3 declared seed gap(s). Every recorded figure carries its source.

| Metric | Value | Source | Quality / confidence | As of |
| --- | --- | --- | --- | --- |
| Primary-care pajama time (after-hours Epic) | 129 minutes_per_day | Evidence base E17 (D06 Documentation-Time Baseline · specialty decomposition) | measured / high | 2026-04-23 |
| MBI-HSS emotional-exhaustion burnout (elevated band) | 54 percent | Evidence base E2 (D06 · MBI-HSS burnout survey wave, n=1,240) | measured / high | 2026-01-12 |
| HCC capture rate on the MA panel | 58 percent | Evidence base E28 (D10 Benchmark Comparison · cohort scorecard) | measured / medium | 2026-02-26 |
| Note turnaround (sign-to-close) | 11.4 hours | Evidence base E8 (D03 Success Metric Tree · supporting metric) | measured / medium | 2026-04-23 |
| CDI query resolution cycle time | 38 hours | Evidence base E8 (D03 Success Metric Tree · CDI cycle-time metric) | measured / medium | 2026-04-23 |
| CDI HCC-relevant query volume | 40 queries_per_week | Evidence base E25 (D08/D10 · CDI-queue routing volume benchmark) | measured / medium | 2026-04-23 |
| Quality-measure documentation capture (HEDIS + Stars) | 34 percent | Evidence base E47 (D15 Intervention Portfolio · lever outcome envelope) | measured / medium | 2026-03-18 |
| Clinician retention (annual) | 88 percent | Evidence base E9 (D16 Business Case · cognitive-load recovery component) | stated / medium | 2026-04-23 |
| Ambulatory visits per clinician | 84 visits_per_clinician_per_week | Evidence base E19 (D04 Intake · chief ambulatory officer field shadow) | stated / medium | 2026-04-23 |
| Cost-per-clinician-hour conversion coefficient | Not recorded — seed gap | seed gap | absent / low | 2026-05-19 |
| RAF-to-revenue conversion coefficient | Not recorded — seed gap | seed gap | absent / low | 2026-05-19 |
| Locum-avoidance dollar basis | Not recorded — seed gap | seed gap | absent / low | 2026-05-19 |

## Named assumptions

Every estimate rests on assumptions; the kernel makes them first-class. The three flagged TOP MOVERS move roughly 80% of the case.

- cost_per_clinician_hour  [TOP MOVER · SEED-GAP PROXY]

Fully-loaded cost per clinician hour is a modeled proxy (~$190/hr for attending physicians) until Meridian Finance attests a figure.

Owner: Priya Raman (VP Revenue Cycle) · confidence: low · sensitivity impact: high · source: Modeled proxy — seed gap (Finance attestation pending)

- locum_avoidance  [TOP MOVER · SEED-GAP PROXY]

Cognitive-load recovery avoids a modeled ~$1.2M/yr of locum spend via reduced burnout-driven attrition — no locum-spend baseline is seeded.

Owner: Dr. Larsson (CMO) · confidence: low · sensitivity impact: high · source: Modeled proxy — seed gap

- raf_to_revenue  [TOP MOVER · SEED-GAP PROXY]

Each RAF point recaptured on the MA panel is worth a modeled ~$430/yr per member; the HCC recapture range $3.2–5.1M/yr rests on this.

Owner: Priya Raman (VP Revenue Cycle) · confidence: low · sensitivity impact: high · source: Revenue-Cycle estimate — seed gap

- cdi_queue_uplift

Ambient-to-CDI integration lifts HCC-relevant query volume from ~40/wk toward the 140–180/wk pattern envelope (E25/E47).

Owner: Dr. Morales (CMIO) · confidence: medium · sensitivity impact: high · source: Evidence base E47 — D15 lever outcome envelope

- portfolio_compounding

Parallel-track execution of the three levers produces +25–35% faster outcome realisation than sequential; the low scenario assumes zero.

Owner: Sarah Chen (CIO) · confidence: medium · sensitivity impact: medium · source: Evidence base E32 — pattern-library lever-interaction model

- vendor_council_commissioning

All three ambient vendor councils commission their HCC/DRG feedback loops on the G3 timeline (Abridge priority, DAX trailing 30 days).

Owner: Dr. Morales (CMIO) · confidence: medium · sensitivity impact: medium · source: Evidence base E59 — D18 Risk Register R11

- rate_card

Blended delivery rate card reflects market rates for the integration-engineering and clinical-informatics roles in the estimate.

Owner: Sarah Chen (CIO) · confidence: medium · sensitivity impact: low · source: Benchmark rate card

## Sensitivity — base, conservative, upside

| Base net return | $7,459,142 |
| --- | --- |
| Conservative net return | $3,460,898 |
| Upside net return | $10,727,545 |

What breaks the case: The case breaks if the baseline seed gap is not closed — without the missing unit economics the value range is a proxy, not a forecast.

## Stop / kill criteria

- kill_downside_negative: Net return is negative in the conservative case (3460898.34). Kill or re-shape if the downside cannot be lifted above zero.

- kill_monetisation_unresolved: The baseline seed gap that blocks monetisation is not closed before the gate — without it the return is unverifiable.

- kill_baseline_unclosed: Baseline coverage stays below acceptable level — 3 seed gap(s) remain unresolved at the gate.

- kill_cdi_queue_undershoot: CDI-queue routing stays below 55/week at the G2 gate — the ambient-to-CDI integration, the program's core mechanism, has failed (E45).

- kill_vendor_council_blocked: HCC feedback-loop commissioning is blocked on more than one vendor council — the documentation-quality value component cannot land (E45).

## Critic findings — surfaced, not hidden

- [blocker / cfo] cfo_monetisation_blocked: Value cannot be monetised to a hard dollar figure — the gross value range rests on a seed-gap proxy. The CFO will not approve a fabricated return; the case must close the baseline gap first.

- [concern / data] data_baseline_seed_gaps: 3 baseline metric(s) are seed gaps (coverage 75%): Cost-per-clinician-hour conversion coefficient, RAF-to-revenue conversion coefficient, Locum-avoidance dollar basis. The case is grounded only on what is recorded.

- [concern / data] data_top_mover_is_proxy: 3 of the top-3 case-moving assumptions stand in for absent tenant data (cost_per_clinician_hour, locum_avoidance, raf_to_revenue). Validating these is the highest-leverage next step.

## What Tower will measure

- Primary-care pajama time: baseline 129 → target 100 minutes_per_day. Measurable now from the Epic Signal 18-month trace; no gap. Target is a 25–35 min/day reduction (E47).

- CDI HCC-relevant query volume: baseline 40 → target 160 queries_per_week. Measurable from the CDI queue; the leading indicator of integration health. Target 140–180/wk (E47).

- HCC capture on the MA panel: baseline 58 → target 63 percent. Measurable, but carry the cohort-position caveat. Financial value is NOT verifiable until the RAF-to-revenue coefficient is attested.

- Cost-per-clinician-hour conversion coefficient: baseline Not recorded — seed gap → target Not recorded — seed gap usd_per_hour. SEED GAP — the cognitive-load recovery value cannot be verified in dollars until Meridian Finance attests a fully-loaded clinician-hour cost. Tower cannot confirm financial value before then.

Every figure in this document is produced by the Moves Expert Kernel from the tenant’s audited substrate. Absent data is declared a seed gap, never invented. Effort rests on a researched planning rate card — a market range, not a quote. Generated by AbarVa · Moves.