ABARVA · MOVES · EXPERT KERNEL

Mobilize & go-decision packet

Ambient Clinical Value Chain Activation — Meridian Health System

Tenant key meridian-health · Move ref meridian:move:ambient-clinical-value-chain-activation

Generated 2026-05-20

The mobilization plan, adoption & change approach, the value-measurement model handed to Tower and the go-decision pack.

# Mobilize & Handoff — adoption, measurement, go-decision

Move: Ambient Clinical Value Chain Activation (meridian-health)

Go-decision: NO GO

No-go: 2 Mobilize kill trigger(s) fired (measurement_unwired, business_case_blocker_open). The Move is not ready to leave Moves. See the fix-conditions for what must change before it is reconsidered.

## Mobilize readiness

| Owned (named operating-model owner) | Yes |
| --- | --- |
| Adoptable (change approach supports the curve) | Yes |
| Measurable (value loop closes to Tower) | NO |
| Operating-model owner | Dr. Morales (CMIO, Clinical Informatics) |
| Overall change load | high |
| Adoption confidence | 0.6 |
| Hypercare window | 8 week(s) |

## Fired kill triggers — verbatim

- measurement_unwired: 1 committed value metric(s) cannot be wired to a recorded baseline: Cost-per-clinician-hour conversion coefficient.

Fix-condition: Revisit when every committed metric is wired to a Discover baseline value or an owned, dated plan to capture one.

- business_case_blocker_open: The business-case critic has 1 open blocker(s): cfo_monetisation_blocked.

Fix-condition: Revisit when the business-case critic reports no open blocker.

## Conditions to clear

- measurement_unwired: Revisit when every committed metric is wired to a Discover baseline value or an owned, dated plan to capture one.

- business_case_blocker_open: Revisit when the business-case critic reports no open blocker.

## Adoption & change approach — seven dimensions

| Dimension | Magnitude | Recommendation | Owner |
| --- | --- | --- | --- |
| impacted_roles | high | Three roles change; the clinician role changes most. Stage the rollout by specialty, leading with primary care where pajama time is highest. | CMIO |
| process_variance | high | Specialty template governance varies documentation materially; the process-redesign workstream must land before the change rollout (it is budgeted in the Design & Plan estimate). | Program Lead |
| training_load | moderate | Role-based training: ambient-tooling curriculum for clinicians, a queue-triage curriculum for CDI specialists. | Enablement Lead |
| incentive_change | moderate | Re-point clinician scorecards away from raw note volume toward documentation quality and recovered capacity. | CMO |
| manager_adoption | high | Manager reinforcement is the highest-risk layer. A dedicated clinic-manager enablement track with explicit reinforcement in the hypercare window. | CMIO |
| communications | moderate | Address the clinician narrative directly — ambient documentation recovers cognitive load and after-hours time; it is not a surveillance layer. | Program Lead |
| hypercare | moderate | An 8-week hypercare window with elevated informatics support and a weekly documentation-quality review; exit when pajama time and CDI volume hold for two consecutive weeks. | CMIO |

## Impacted roles

| Role | Headcount | Change | What changes |
| --- | --- | --- | --- |
| Primary-care clinician | Not recorded — seed gap | high | Clinicians move from manual after-hours documentation to ambient-captured notes reviewed and signed in-visit. |
| CDI specialist | 42 | high | CDI specialists work an ambient-routed HCC query queue rather than a starved, manually-built one. |
| Clinic operations manager | Not recorded — seed gap | moderate | Managers coach to the new documentation pattern and the recovered-capacity visit targets. |

## Adoption risks — surfaced

- [concern] adoption_manager_layer_heavy: Manager adoption is a high-magnitude change. Adoption fails at the manager layer more than anywhere else — manager reinforcement must be explicitly resourced, not assumed.

- [note] adoption_headcount_gap_primary_care_clinician: Impacted headcount for 'Primary-care clinician' is not recorded — training load and communications scale cannot be sized precisely.

- [note] adoption_headcount_gap_clinic_operations_manager: Impacted headcount for 'Clinic operations manager' is not recorded — training load and communications scale cannot be sized precisely.

- [note] adoption_seed_gap_impacted_roles: The 'Impacted roles' assessment rests on a benchmark proxy / seed gap, not tenant data — validate it before the gate.

- [note] adoption_seed_gap_training_load: The 'Training load' assessment rests on a benchmark proxy / seed gap, not tenant data — validate it before the gate.

## Value-measurement model — handed to Tower

3 of 4 metric(s) wired to a recorded baseline (coverage 75%). Value loop closes: NO.

| Metric | Baseline | Target | Cadence | Owner |
| --- | --- | --- | --- | --- |
| Primary-care pajama time | 129 | 100 | monthly | CMIO |
| CDI HCC-relevant query volume | 40 | 160 | weekly | CDI Director |
| HCC capture on the MA panel | 58 | 63 | quarterly | VP Revenue Cycle |
| Cost-per-clinician-hour conversion coefficient | Not recorded — seed gap | Not recorded — seed gap | quarterly | VP Revenue Cycle |

## Critic findings — surfaced, not hidden

- [blocker / cfo] cfo_monetisation_blocked: Value cannot be monetised to a hard dollar figure — the gross value range rests on a seed-gap proxy. The CFO will not approve a fabricated return; the case must close the baseline gap first.

- [concern / data] data_baseline_seed_gaps: 3 baseline metric(s) are seed gaps (coverage 75%): Cost-per-clinician-hour conversion coefficient, RAF-to-revenue conversion coefficient, Locum-avoidance dollar basis. The case is grounded only on what is recorded.

- [concern / data] data_top_mover_is_proxy: 3 of the top-3 case-moving assumptions stand in for absent tenant data (cost_per_clinician_hour, locum_avoidance, raf_to_revenue). Validating these is the highest-leverage next step.

Every figure in this document is produced by the Moves Expert Kernel from the tenant’s audited substrate. Absent data is declared a seed gap, never invented. Effort rests on a researched planning rate card — a market range, not a quote. Generated by AbarVa · Moves.