## Sprint Velocity
Arcturus Financial Group — Sprint Velocity & DORA Metrics (Apr 2025–Mar 2026)
Squad | Quarter | Planned Pts | Completed Pts | Velocity % | Unplanned % | Carryover % | Deployments | Incidents | Vendor Blocked | CDO Blocked | RAG | Notes
OMS Core Engineering | Q1 2025 | 42 | 31 |  | 28% | 22% | 0 | 3 | 4 | 0 | Red | 2 sprints blocked by Bloomberg release freeze. Emergency AIM-OMS sync patch.
OMS Core Engineering | Q2 2025 | 40 | 28 |  | 31% | 28% | 0 | 4 | 5 | 0 | Red | Bloomberg upgrade required 6-week regression. Zero feature delivery.
OMS Core Engineering | Q3 2025 | 44 | 32 |  | 26% | 24% | 1 | 2 | 4 | 0 | Amber | 1 deployment — hotfix only. Vendor controls all change windows.
OMS Core Engineering | Q4 2025 | 42 | 29 |  | 30% | 25% | 0 | 3 | 5 | 0 | Red | Year-end freeze. Bloomberg governs all windows. Squad in maintenance mode.
Portfolio Analytics | Q1 2025 | 65 | 61 |  | 8% | 5% | 8 | 1 | 0 | 0 | Green | Strong. 8 production deployments. Factor model updated.
Portfolio Analytics | Q2 2025 | 68 | 64 |  | 7% | 4% | 9 | 1 | 0 | 1 | Green | CDO vacancy blocked 1 AI feature. Otherwise excellent.
Portfolio Analytics | Q3 2025 | 66 | 63 |  | 9% | 6% | 10 | 0 | 0 | 0 | Green | Best quarter. ESG data integration delivered.
Portfolio Analytics | Q4 2025 | 64 | 60 |  | 10% | 7% | 8 | 1 | 0 | 2 | Green | 2 items awaiting AI governance (CDO vacant).
AI/ML Platform | Q1 2025 | 30 | 18 |  | 45% | 40% | 0 | 0 | 0 | 6 | Red | 6 features blocked by absent CDO sponsor. Zero production deployments.
AI/ML Platform | Q2 2025 | 28 | 14 |  | 48% | 44% | 0 | 0 | 0 | 8 | Red | Google PSO engagement ended. Knowledge transfer incomplete.
AI/ML Platform | Q3 2025 | 25 | 12 |  | 52% | 48% | 0 | 0 | 0 | 9 | Red | 9 items require CDO approval. Interim CDO refuses to sign off.
AI/ML Platform | Q4 2025 | 22 | 10 |  | 55% | 50% | 0 | 0 | 0 | 11 | Red | 11 CDO-blocked items. 0 deliveries in 12 months. 3 engineers interviewing elsewhere.
Client Data Platform | Q1 2025 | 35 | 22 |  | 38% | 34% | 0 | 2 | 0 | 0 | Red | Team lead vacancy month 2. Wipro PM running squad.
Client Data Platform | Q2 2025 | 32 | 19 |  | 40% | 36% | 0 | 3 | 0 | 0 | Red | Golden record stalled. Wipro scope change added cost without delivery.
Client Data Platform | Q3 2025 | 30 | 18 |  | 42% | 38% | 0 | 2 | 0 | 0 | Red | Data pipeline POC attempted. Wipro delivered incomplete.
Client Data Platform | Q4 2025 | 28 | 16 |  | 44% | 40% | 0 | 4 | 0 | 0 | Red | 3-day reporting lag unresolved. Same root cause as Q1. No progress.
Compliance & Regulatory | Q1 2025 | 20 | 14 |  | 22% | 18% | 0 | 1 | 0 | 0 | Amber | MAS FEAT gap analysis delivered (Deloitte). No implementation started.
Compliance & Regulatory | Q2 2025 | 18 | 12 |  | 24% | 20% | 0 | 1 | 0 | 0 | Red | MAS deadline Dec 2025 confirmed. Deloitte 180-page requirements doc.
Compliance & Regulatory | Q3 2025 | 22 | 15 |  | 20% | 16% | 0 | 0 | 0 | 0 | Red | Implementation sprint started. 8 weeks behind plan.
Compliance & Regulatory | Q4 2025 | 20 | 13 |  | 26% | 22% | 0 | 1 | 0 | 0 | Red | MAS deadline MISSED. Dec 2025. Regulatory notice received.
Risk Technology | Q1 2025 | 48 | 42 |  | 14% | 10% | 4 | 1 | 0 | 2 | Green | Solid. 2 CDO-dependent AI features blocked.
Risk Technology | Q2 2025 | 50 | 44 |  | 12% | 8% | 5 | 1 | 0 | 3 | Amber | Model validation backlog growing.
Risk Technology | Q3 2025 | 46 | 40 |  | 15% | 12% | 4 | 2 | 0 | 4 | Amber | 4 AI risk overlays blocked pending CDO.
Risk Technology | Q4 2025 | 48 | 41 |  | 14% | 11% | 5 | 1 | 0 | 5 | Amber | 5 features awaiting CDO. Regulatory model validation deadline Q1 2026 at risk.