## Consulting Audit
Arcturus Financial Group — Consulting Output vs Promise Audit (All Active Engagements)
Vendor | Engagement | Promised | Delivered? | Quality /10 | KT Score /100 | Annual Cost £M | Value Rating | Recoverable £M pa | Maestro Replacement?
Bloomberg LP | OMS Core Maintenance | 24/7 support, 99.9% uptime, quarterly features | Partial — SLA met, features delayed | 6 | 8 | 8.4 | Poor — trapped dependency | 6.3 | Yes — API wrapper + internal OMS team (18mo)
Infosys | Risk Tech & Analytics | 90% sprint velocity, knowledge wiki, upskilling | No — 71% velocity, wiki incomplete | 5 | 22 | 3.6 | Below expectations | 1.8 | Yes — 2 Maestros replace 12 Infosys (Wave 1)
Wipro | Client Portal + Data Platform | 85% velocity, full KT, golden record | No — 58% velocity, KT 15%, golden record not started | 3 | 15 | 4.8 | Poor — knowledge hostage | 3.2 | Yes — exit plan + 2 Maestros
Deloitte | MAS FEAT Compliance | Compliance by Dec 2025, internal capability | No — deadline missed, team not capable | 4 | 45 | 2.6 | Below expectations | 0.8 | Partial — keep advisory, Maestro for execution
TCS | APAC Technology Operations | 96% SLA, KT, documentation | Yes for SLA, partial KT | 6 | 38 | 0.9 | Adequate | 0 | No — retain, value for APAC ops
Google PSO | AI/ML Platform Setup | Full MLOps infrastructure delivered | No — 22% delivered, engagement ended | 2 | 5 | 0 | Failed | 0 | Yes — internal ML engineering with Maestro
AWS ProServe | Infrastructure Modernisation | Runbook delivery, team training | Mostly — 88% complete | 7 | 62 | 1.4 | Good | 0 | No — continue with internal support
Salesforce PS | FSC Customisation | Feature delivery, internal admin capability | Partial — 71% features, no admin capability | 5 | 28 | 1.6 | Below expectations | 0.8 | Yes — internal Salesforce admin team
Contractors | Enterprise Architecture | Architecture decisions, documentation | No — no documentation, no KT | 1 | 0 | 1.8 | Critical risk | 1.8 | Yes — permanent EA hire immediately
TOTAL RECOVERABLE CONSULTING SPEND | [5 empty] | 25.1 |  | 14.7