## Knowledge Risk
Arcturus Financial Group — Knowledge Retention Risk Register
Knowledge Domain | Current Owner | Type | If Lost — Impact | Retention Plan? | Risk Score | Mitigation
Bloomberg AIM customisation logic (14 rules) | Bloomberg LP engineers | Vendor-owned | Cannot maintain or modify OMS. Entire trading operation at vendor mercy. | No | 98 | AIM API wrapper + internal capability build. 12-month programme.
Wipro FSC customisation code | Wipro developers | Vendor-owned | Cannot deploy or maintain Salesforce FSC. Client portal frozen. | No | 88 | Code escrow clause + internal Salesforce admin hire immediately.
Google PSO MLOps design (22% complete) | Google PSO (ended) | Departed vendor | AI/ML platform design knowledge walked out. Starting from zero. | No | 95 | Reconstruct from artefacts. Hire ML engineer. Use AbarVa MLOps playbook.
MAS FEAT compliance process | Deloitte consultants | Vendor-dependent | Regulatory process not documented internally. Next audit will fail. | Partial | 72 | Internal compliance team documentation sprint. Deloitte exit plan.
Enterprise architecture decisions | Contractor (rolling) | Contractor-owned | Architecture logic undocumented. No permanent owner. | No | 91 | Permanent EA hire. Documentation retrospective. Architecture decision records.
Data pipeline logic (14 integrations) | Wipro + contractors | Mixed | Manual processes undocumented. Loss of any operator causes outage. | No | 85 | Runbook creation sprint. All manual processes documented.
Risk model logic (Aladdin config) | Head of Risk + vendor | Internal + vendor | Risk model config not fully documented. Vendor changes break models. | Partial | 61 | Model documentation programme. Internal model risk function.
Client mandate rules (93 Bloomberg rules) | Bloomberg LP | Vendor-owned | Compliance rule logic inaccessible without Bloomberg. Mandate breaches undetected. | No | 94 | Compliance rule extraction and documentation. Internal rules engine assessment.
Portfolio Analytics squad IP | Internal team (Rachel Kim) | Internal | Best internal team. Knowledge concentrated in 3 people. Attrition risk. | Partial | 55 | Knowledge sharing programme. Documentation. Succession planning.
CDO-sponsored initiative context | (VACANT — 11 months) | Departed employee | 14 initiatives orphaned. Context and rationale lost. | No | 89 | Initiative documentation retrospective. CIO assumes interim.