## MLOps Assessment
Arcturus Financial Group — MLOps Infrastructure Assessment
MLOps Capability | Current State | Maturity 0-5 | Initiatives Blocked | Effort to Fix | Unblock Sequence | Recommendation
Model Registry | No registry. Models tracked in spreadsheets. | 0 | 28 | Medium — 2mo | Step 1 | MLflow on AWS SageMaker. Link to Bedrock model catalog.
Feature Store | No feature store. Each model rebuilds features. | 0 | 22 | High — 4mo | Step 3 | Start with position and client data features — highest demand.
ML CI/CD Pipeline | No ML CI-CD. Infrastructure pipeline not extended to ML. | 0 | 28 | Medium — 2mo | Step 2 | Extend AWS CodePipeline. Add model validation gate.
Model Serving | No serving. Models run ad-hoc on analyst laptops. | 0 | 28 | Medium — 2mo | Step 2 | Deploy SageMaker Endpoints. AI-023 and AI-026 first.
Model Monitoring | No monitoring. No drift detection. | 0 | 18 | Medium — 2mo | Step 4 | CloudWatch + Evidently AI. After first production deployments.
Experiment Tracking | Partial — 2 scientists use MLflow locally. No shared server. | 1 | 20 | Low — 3wks | Step 1 | Deploy shared MLflow server. Quick win.
Data Versioning | No data versioning. Reproducibility impossible. | 0 | 24 | Medium — 2mo | Step 3 | DVC. Version training datasets. Link to model registry.
Model Validation Framework | No validation. No independent review. CDO sign-off required but vacant. | 0 | 14 | High — requires CDO | CDO prerequisite | Establish model risk framework. Interim model risk officer.
Automated Retraining | No automated retraining. All models static. | 0 | 18 | Medium — 4mo | Step 5 | Implement after serving layer. AI-005 MAS model will drift.
Data Pipeline for ML | Manual extraction. No automated feature pipeline. 3-day lag. | 0 | 26 | High — 6mo (golden record dep) | Blocked by golden record | Golden record must precede ML pipeline automation.
Security & Compliance | No model governance. No GDPR-compliant AI data handling. | 0 | 12 | High — requires CDO + Legal | CDO prerequisite | GDPR and MAS AI compliance framework. CDO prerequisite.