## Modernisation Options
Arcturus Financial Group — Technology Modernisation Options Scorecard
System | Option | Vendor | Total Cost £M | Duration | Risk Level | Internal Capability | Genome Score | Recommended? | Rationale
Bloomberg AIM | Option A: Full OMS replacement | SS&C Eze / Fidessa | 28 | 36 | Critical | Very Low | 28 | No | 3 previous failures. Same root causes unaddressed. No internal capability to govern.
Bloomberg AIM | Option B: API wrapper + internal build | Internal (Maestro-led) | 8 | 24 | High | Medium (builds over 24mo) | 64 | CONDITIONAL | Reduces dependency without ripping out. Internal capability builds in parallel. Conditional on CDO hire.
Bloomberg AIM | Option C: Phased modernisation with ION | ION Trading | 18 | 30 | High | Low → Medium | 58 | Alternative | ION has better asset management focus than prior attempts. Still requires executive sponsor.
Bloomberg AIM | Option D: Stay + cost renegotiation | Bloomberg LP | 2 | 3 | Low | High | 42 | Short-term | Renegotiate 2027 contract now. Exit penalty £4.2M. Use Options B/C as leverage.
SQL Server 2017 DW | Option A: Migrate to Azure SQL | Microsoft Azure | 1.2 | 4 | Medium | High | 78 | RECOMMENDED | EOL passed. Azure SQL migration straightforward. Internal team capable. 4-month project.
SQL Server 2017 DW | Option B: Migrate to Snowflake | Snowflake | 2.8 | 6 | Medium | Medium | 72 | Alternative | Better analytics capability but longer migration. Azure SQL simpler given existing Microsoft estate.
Salesforce FSC | Option A: Optimise existing deployment | Maestro-led | 2.4 | 12 | Low | Low → High | 81 | RECOMMENDED | 44% → 70%+ adoption. Wipro exit. Internal admin. Highest ROI option.
Salesforce FSC | Option B: Replace with Dynamics 365 | Microsoft | 8 | 18 | High | Medium | 44 | Not recommended | Migration cost and disruption not justified given FSC capability.
BlackRock Aladdin | Option A: Enhance daily risk | BlackRock + internal | 1.8 | 6 | Low | Medium | 74 | RECOMMENDED | Daily stress testing regulatory requirement. Internal data feed automation. Low risk.
BlackRock Aladdin | Option B: Replace with Axioma | Qontigo / Axioma | 6 | 18 | High | Low | 48 | Not recommended | Aladdin well-embedded. Replacement cost not justified.

## MAS FEAT Compliance Gap
MAS FEAT Compliance Assessment — Overdue 4 months
FEAT Principle | Category | Status | Gap Description | Risk | Remediation
F1 — Fairness | Fairness | Partial | AI decision audit trail incomplete for 14 AI initiatives. | High | Implement full audit logging for all AI model decisions.
F2 — Ethics | Ethics | Not met | AI ethics review board not constituted. CDO vacancy. | Critical | Constitute AI ethics board. CDO appointment prerequisite.
F3 — Accountability | Accountability | Not met | No named accountable executive for AI decisions. CDO vacant. | Critical | CDO appointment. Model risk committee with clear accountability.
F4 — Transparency | Transparency | Partial | Model explainability documented for only 3 of 28 initiatives. | High | Explainability documentation programme across all 28 initiatives.
F1-F4 — Data & Model Governance | Governance | Not met | No model registry. No validation framework. No data governance board. | Critical | MLOps foundation + model risk framework. CDO-led.
F5 — Risk Management | Risk | Not met | AI risk not integrated into enterprise risk framework. | High | AI risk taxonomy + OpenPages integration.
F6 — Human Oversight | Human oversight | Partial | Some models have human override. Not systematic. | High | Systematic human-in-the-loop for all high-risk AI decisions.
Singapore Data Residency | Data residency | Not met | £2.4B Singapore AUM data not segregated from global data lake. | Critical | Data residency programme. Singapore data lake separation. 6-month programme.