## Consulting Contracts
Meridian Health System — Consulting & Vendor Contract Register
Vendor | Scope | Annual $M | Contract End | Notice Period | KT Obligation | KT Compliance % | Exit Penalty $M | Performance | Risk
Ensemble Health Partners | Full RCM outsourcing — billing, denials, collections, AR management | 14.2 | 2026-06-30 | 6 months | Full process documentation required | 18% | 8 | UNDERPERFORMING — 18.2% denial rate vs 12% benchmark. $8M SLA penalties enforceable now. | Critical
Epic Systems (PS) | Epic implementation support, upgrades, training | 4.2 | 2026-12-31 | 3 months | Epic-controlled documentation | 62% | 1.2 | Good — Epic responsive. Upgrade quality high. Training completion our gap, not vendor. | Low
Wipro | Salesforce Health Cloud administration and development | 1.8 | 2025-12-31 | 2 months | Documentation and handover sessions required | 22% | 0.3 | Below expectations — 38% adoption. Internal team capability not built. | High
Cohere Health | Prior auth AI platform — pilot 3 payers | 0.4 | 2025-06-30 | 1 month | Platform documentation shared | 45% | 0 | Pilot positive — 94/100 Genome vendor score. Ready to expand. | Low
3M / Solventum | Clinical coding AI — pilot | 0.6 | 2025-09-30 | 1 month | Model documentation | 38% | 0 | In progress — 84% accuracy. Target 96%. Continue. | Low
AWS Professional Services | Cloud migration support — 60% complete | 1.2 | 2025-12-31 | 1 month | Runbook delivery required | 68% | 0.1 | Good — AWS ProServe adds value. Cloud migration on track. | Low
Deloitte | Regulatory advisory — HIPAA, CMS compliance | 0.8 | 2026-03-31 | 2 months | Policy documentation | 52% | 0.1 | Adequate for advisory. Execution should be internal. | Medium
Various contractors | Epic + data analyst contractors (12 FTE) | 2.4 | Rolling | 2 weeks | None required | 12% | 0 | Risk — contractors in critical roles. Knowledge walks out weekly. | High
TOTAL ANNUAL VENDOR SPEND |  | 25.6 |  |  |  |  | 9.7