## Consulting Audit
Meridian Health System — Consulting Output vs Promise Audit
Vendor | Engagement | Promised | Delivered? | Quality /10 | KT Score | Annual $M | Value Rating | Recoverable $M | Maestro Replacement?
Ensemble Health | Full RCM outsourcing | Denial rate to 12%, SLA compliance, KT | No — denial 18.2% vs 12%. SLA breached. KT 18% | 3 | 18 | 14.2 | Poor — $8M SLA penalties enforceable | 8 | Partial — prior auth AI (Cohere) replaces part. Renegotiate core contract.
Epic PS | Implementation + ongoing support | Epic best practices, training, 80% optimization | Partial — training low (41% completion). Score 58 vs 80. | 6 | 62 | 4.2 | Good for support. Training gap is Meridian's issue. | 0 | No — Epic PS value appropriate. Internal training programme needed.
Wipro | Salesforce Health Cloud | Platform admin, 80% adoption, internal capability | No — 38% adoption. No internal admin built. Wipro owns all customisations. | 3 | 22 | 1.8 | Poor — no internal capability built after 2 years | 0.8 | Yes — internal Salesforce Health Cloud admin with Maestro.
Various contractors | Epic + data analysts | Project delivery, knowledge transfer | No — knowledge walks out weekly. 12% KT score. | 2 | 12 | 2.4 | Critical risk | 1.8 | Yes — permanent Epic analysts. Contractor to FTE programme.
Deloitte | Regulatory advisory | CMS compliance guidance, HIPAA frameworks | Adequate — advisory quality good. Execution not included. | 6 | 52 | 0.8 | Adequate — advisory only. Cannot execute. | 0 | No — keep advisory. Build internal execution capability with Maestro.