## Cerner Migration Assessment
Meridian Health System — Cerner to Epic Migration Assessment (2 Hospitals)
Dimension | Current State | Target State | Complexity | Risk | Duration | Cost $M | Blocker
Hospitals on Cerner | 2 community hospitals — St. Andrews (420 beds), Valley Medical (280 beds) | Epic — same instance as main system | High | High | 18 months | 12.4 | Data migration planning not started. Go-live Q4 2026 target.
Patient data migration | 14 years of Cerner patient history. 284k patient records. Complex discrete data. | Full historical data in Epic | Very High | Critical | Concurrent with build | 4.2 | Cerner data model differs significantly from Epic. Custom mapping required.
Cerner interface decommission | 12 active HL7 interfaces on Cerner. ADT feed to main Epic instance. | All interfaces on Epic | High | High | Last 6 months | 1.8 | Dual-live period required. Complex ADT reconciliation.
Staff training | 1,400 clinical and administrative staff across 2 hospitals. | Epic-certified staff | Medium | Medium | 6 months pre-go-live | 2.8 | Training schedule not developed. Epic trainer capacity uncertain.
Downtime procedures | Cerner downtime procedures established. Epic downtime different. | Epic downtime procedures | Medium | Medium | 3 months | 0.4 | Downtime policy rewrite required.
Clinical workflow redesign | Current Cerner workflows embedded in clinical practice for 14 years. | Epic-optimized workflows | High | High | 12 months | 1.6 | Change management critical. Clinician workflow champions required.
Pharmacy system migration | Cerner PharmNet currently. Epic Willow target. | Epic Willow | High | High | 12 months | 1.4 | Medication history reconciliation critical for patient safety.
Revenue cycle migration | Cerner RevCycle in both hospitals. Different denial management process. | Epic revenue cycle | High | Critical | 12 months | 2.2 | Denial rate may temporarily increase during transition. Ensemble Health contract impact.
TOTAL MIGRATION PROGRAMME |  |  | Very High | High | Q4 2026 target | 26.8 | CDO hire supports governance. Maestro recommended for programme delivery.