## Cover
Moves financial model · Contact Center AI Routing
Tenant | Apex Retail
Event | Contact Center AI Routing
Event code | apex:move:contact-center-ai-routing
Issued by | AbarVa · Moves Expert Kernel
Generated at | 2026-05-19
Instructions
• Every figure is produced by the Moves Expert Kernel from the tenant’s audited substrate.
• "Not recorded — seed gap" marks an input that is not recorded — it is declared, never invented.
• Recommendation: SHAPE — do not fund as-is. The critic raised 1 blocker(s) — fund only after they are resolved (see critic findings). Re-shape the Move to close them, do not fund as-is.
• Payback: Not monetisable — the value rests on a baseline seed gap, so the kernel returns no payback rather than a fabricated one..
• Effort rests on a researched planning rate card — a market range, not a quote.
• Every figure in this document is produced by the Moves Expert Kernel from the tenant’s audited substrate. Absent data is declared a seed gap, never invented. Effort rests on a researched planning rate card — a market range, not a quote. Generated by AbarVa · Moves.

## Baseline
Current-state baseline
Metric | Value | Unit | Source | Source quality | Confidence | As of
Average Handle Time | 7.2 | minutes | KPI kpi:apex:019 (NICE CXone) | measured | high | 2026-04-30
Contact Center Containment | 28 | percent | KPI kpi:apex:018 (NICE CXone) | measured | medium | 2026-04-30
First Call Resolution | 68 | percent | KPI kpi:apex:020 (NICE CXone) | measured | medium | 2026-04-30
Agent Utilization | 84 | percent | KPI kpi:apex:021 (NICE CXone) | measured | high | 2026-04-30
CSAT (post-interaction) | 4.1 | score_out_of_5 | KPI kpi:apex:012 (Zendesk survey) | measured | medium | 2026-04-30
Repeat transfer rate | 18.4 | percent | Move P2 baseline deliverable (Genesys routing export) | measured | medium | 2026-05-03
Cost per contact (labour) | Not recorded — seed gap | usd | seed gap | absent | low | 2026-05-18
Annual contact volume | Not recorded — seed gap | contacts_per_year | seed gap | absent | low | 2026-05-18
Channel mix (voice/chat/IVR split) | Not recorded — seed gap | percent_split | seed gap | absent | low | 2026-05-18
QA error rate | Not recorded — seed gap | percent | seed gap | absent | low | 2026-05-18
Coverage | 60% | fraction recorded

## Effort
Effort estimate — workstream × role-mix
Workstream | Months | Headcount | Upside cost | Base cost | Conservative cost | Human cost | Agent cost
AI build | 9 | 5 | 679932 | 799920 | 1119888 | 519948 | 279972
Integration | 6 | 3 | 246840 | 290400 | 406560 | 232320 | 58080
Data | 5 | 3 | 164560 | 193600 | 271040 | 135520 | 58080
Foundational | 4 | 1 | 74800 | 88000 | 123200 | 74800 | 13200
Data governance | 6 | 1.5 | 103224 | 121440 | 170016 | 109296 | 12144
Process redesign | 5 | 2 | 111265 | 130900 | 183260 | 117810 | 13090
Change & adoption | 9 | 2 | 218790 | 257400 | 360360 | 244530 | 12870
Run (year-1 operations) | 12 | 2 | 273768 | 322080 | 450912 | 193248 | 128832
TOTAL |  |  | 1873179 | 2203740 | 3085236 | 1627472 | 576268
AI-build vs. business-change split
AI-build effort |  |  |  | 1694000
Business-change effort |  |  |  | 509740
Business-change share |  |  |  | 23%
Read | Business change is 23% of effort — a credible build-vs-change balance for an AI Move where value depends on people changing how they work.
Rate card | Apex Contact Center AI Routing comprehensive demo rate card — comprehensive rate card. Precedence: client rate card > vendor quote > internal team cost > loaded benchmark row > researched benchmark fallback. Planning input, not a quote.

## Value forecast
Value forecast — gross value, haircut, net value
Haircut dimension | Score (0..1) | Weight | Discount contribution
adoptionRisk | 0.6 | 0.28 | 0.112
dataReadiness | 0.45 | 0.2 | 0.11
processDependency | 0.55 | 0.16 | 0.072
integrationComplexity | 0.6 | 0.12 | 0.048
controlBurden | 0.5 | 0.12 | 0.06
sponsorStrength | 0.8 | 0.12 | 0.024
Total haircut | 42.6% | Retained | 57.4%
Year | Adoption fraction | Gross value (base) | Net value low | Net value (base) | Net value high
1 | 30% | 3195000 | 1343160 | 1833930 | 2324700
2 | 70% | 7455000 | 3134040 | 4279170 | 5424300
3 | 85% | 9052500 | 3805620 | 5196135 | 6586650
TOTAL |  | 19702500 | 8282820 | 11309235 | 14335650
Monetisation blocked — the gross value rests on a seed-gap proxy. The net value above is an illustrative ceiling, NOT a claimed return.

## Sensitivity
Three-scenario sensitivity
Scenario | Investment | Net value | Net return | ROI | Payback (months)
Base | 2203740 | 11309235 | 9105495 | Not recorded — seed gap | Not recorded — seed gap
Conservative | 3085236 | 8282820 | 5197584 | Not recorded — seed gap | Not recorded — seed gap
Upside | 1873179 | 14335650 | 12462471 | Not recorded — seed gap | Not recorded — seed gap
What breaks the case | The case breaks if the baseline seed gap is not closed — without the missing unit economics the value range is a proxy, not a forecast.
Downside read | The conservative case cannot be expressed in hard dollars — the value rests on a seed-gap proxy. Close the baseline gap before reading the downside as a number.
Top mover | Statement | Owner | Confidence | Seed-gap proxy
annual_contact_volume | Annual agent-handled contact volume is ~9.0M (benchmark for an $80B retailer) — used only to express value in operational hours. | Priya Iyer (Program Lead) | low | yes
cost_per_contact | Fully-loaded cost per contact is ~$6.50 (benchmark proxy) until the tenant baseline due 2026-05-15 lands. | Brendan Fox (CS Ops) | low | yes
containment_uplift | AI routing lifts containment ~12 points (28% → 40% target) — the KPI dictionary states this uplift target explicitly. | Priya Iyer (Program Lead) | medium | no

## Roadmap
Costed roadmap — per-phase investment & value
Phase | Investment | Cumulative investment | Annual value unlocked | Foundational | Value milestone
Phase 0 — Data & platform foundation | 281600 | 281600 | 0 | yes — enablement only | Intent / transcript data unified and a model gateway stood up — no customer-facing value yet; this is the precondition.
Phase 1 — Routing pilot on Customer Care queues | 1211760 | 1493360 | 942436.25 | no | AI routing live on pilot queues — containment +4 pts, AHT down ~0.3 min on piloted contacts.
Phase 2 — Scale-out + process redesign | 130900 | 1624260 | 1696385.25 | no | Routing scaled across Customer Care; agent-assist workflow redesigned — containment toward the 40% target.
Phase 3 — Adoption + run | 579480 | 2203740 | 1130923.5 | no | Steady-state adoption (~70%) reached; hypercare complete and the routing model in sustained operation.