## Instructions
Dataset | Apex Retail Group synthetic enterprise context
Workbook | Risk + Compliance Register
Rows | 30
Notice | Fictional internal enterprise context only. No PHI or patient-identifiable data.
Refresh use | Use as Week 0 baseline test data for ingestion, validation, quality issue, and retrieval workflows.

## Data Dictionary
column | required | type | description | example
risk_id | yes | string | Stable risk or finding identifier. | RISK-AI-003
risk_title | yes | string | Risk or finding title. | AI routing model lacks monthly drift attestation
risk_type | yes | enum | Risk type. | AI Governance
control_id | no | string | Linked control identifier. | CTRL-AI-MONITORING
policy_id | no | string | Linked policy identifier. | POL-AI-002
owner | yes | string | Risk owner. | AI Governance Council
severity | yes | enum | Risk severity. | High
likelihood | yes | enum | Likelihood. | Medium
status | yes | enum | Risk status. | Open
linked_ci_ids | no | list | Pipe-separated linked CI identifiers. | CI-SVC-CONTACT-CENTER¦CI-APP-CRM
linked_vendor_ids | no | list | Pipe-separated linked vendor identifiers. | VEN-GENESYS¦VEN-SALESFORCE
remediation_due_date | no | date | Remediation due date. | 2026-08-31
evidence_required | no | string | Evidence required to close or downgrade the risk. | Monthly model performance and drift report
source_system | yes | string | Originating system or template source, such as ServiceNow, Workday, Coupa, Epic, or manual attestation. | ServiceNow
source_record_id | yes | string | Stable source-system identifier. Keep this unchanged across weekly or monthly refreshes. | SYS-000123
source_owner | yes | string | Person or group accountable for the source extract or attestation. | IT Service Management
last_validated_date | yes | date | Date the row was last validated by the source owner, formatted YYYY-MM-DD. | 2026-05-01
confidence | yes | number | Confidence score from 0 to 1. Use lower values for manually estimated or partially reconciled records. | 0.86
evidence_usable | yes | boolean | Whether this row can be cited as evidence in Source, Moves, Tower, or Intelligence. | true
notes_gaps | no | string | Known gaps, caveats, stale fields, conflicts, or follow-up needed before this row is trusted. | Owner validated; renewal date needs Legal confirmation.

## Data
risk_id | risk_title | risk_type | control_id | policy_id | owner | severity | likelihood | status | linked_ci_ids | linked_vendor_ids | remediation_due_date | evidence_required | source_system | source_record_id | source_owner | last_validated_date | confidence | evidence_usable | notes_gaps
RISK-001 | Critical CI owner validation is stale | Operational | CTRL-100 | POL-001 | Commerce Platform Engineering | Critical | High | Mitigating | CI-APP-SAP-S4¦CI-DATA-CDP | VEN-SAP | 2026-07-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-1 | GRC Office | 2026-05-01 | 0.79 | FALSE
RISK-002 | Renewal decision date lacks sourcing owner | Security | CTRL-101 | POL-002 | Store Technology | Medium | Medium | Open | CI-APP-ORACLE-RETAIL¦CI-SVC-CONTACT-CENTER | VEN-ORACLE | 2026-08-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-2 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-003 | AI workflow lacks model monitoring evidence | Privacy | CTRL-102 | POL-003 | Supply Chain Technology | Medium | Medium | Open | CI-APP-NCR-POS¦CI-APP-BLUEYONDER | VEN-SALESFORCE | 2026-09-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-3 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-004 | Incident trend worsened for dependent service | Compliance | CTRL-103 | POL-004 | Customer Data Platform Office | High | Medium | Open | CI-SVC-ECOMMERCE¦CI-APP-MANHATTAN-WMS | VEN-SEGMENT | 2026-10-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-4 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-005 | Vendor security review due before renewal | Financial | CTRL-104 | POL-005 | Merchandising Analytics | Medium | Medium | Mitigating | CI-DATA-CDP¦CI-WH-SNOWFLAKE | VEN-BLUEYONDER | 2026-11-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-5 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-006 | Policy review date approaching without steward attestation | AI Governance | CTRL-105 | POL-006 | Contact Center Technology | Medium | High | Open | CI-SVC-CONTACT-CENTER¦CI-PLAT-DATABRICKS | VEN-MANHATTAN | 2026-12-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-6 | GRC Office | 2026-05-01 | 0.79 | FALSE
RISK-007 | Critical CI owner validation is stale | Vendor | CTRL-106 | POL-007 | Cloud Platform Services | High | Medium | Open | CI-APP-BLUEYONDER¦CI-APP-SERVICENOW | VEN-NCR | 2026-01-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-7 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-008 | Renewal decision date lacks sourcing owner | Operational | CTRL-107 | POL-008 | Cybersecurity Governance | Critical | Medium | Open | CI-APP-MANHATTAN-WMS¦CI-SEC-OKTA | VEN-ADOBE | 2026-02-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-8 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-009 | AI workflow lacks model monitoring evidence | Security | CTRL-108 | POL-009 | IT Sourcing | Medium | Medium | Mitigating | CI-WH-SNOWFLAKE¦CI-CLOUD-AWS-PROD | VEN-GENESYS | 2026-03-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-9 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-010 | Incident trend worsened for dependent service | Privacy | CTRL-109 | POL-010 | Finance Technology | High | Medium | Open | CI-PLAT-DATABRICKS¦CI-CLOUD-AZURE-PROD | VEN-DATABRICKS | 2026-04-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-10 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-011 | Vendor security review due before renewal | Compliance | CTRL-110 | POL-011 | Commerce Platform Engineering | Medium | High | Open | CI-APP-SERVICENOW¦CI-APP-WORKDAY-HCM | VEN-SNOW | 2026-05-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-11 | GRC Office | 2026-05-01 | 0.79 | FALSE
RISK-012 | Policy review date approaching without steward attestation | Financial | CTRL-111 | POL-012 | Store Technology | Medium | Medium | Open | CI-SEC-OKTA¦CI-APP-ADOBE-COMMERCE | VEN-MICROSOFT | 2026-06-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-12 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-013 | Critical CI owner validation is stale | AI Governance | CTRL-112 | POL-013 | Supply Chain Technology | High | Medium | Mitigating | CI-CLOUD-AWS-PROD¦CI-APP-001 | VEN-AWS | 2026-07-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-13 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-014 | Renewal decision date lacks sourcing owner | Vendor | CTRL-113 | POL-014 | Customer Data Platform Office | Medium | Medium | Open | CI-CLOUD-AZURE-PROD¦CI-SVC-002 | VEN-AZURE | 2026-08-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-14 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-015 | AI workflow lacks model monitoring evidence | Operational | CTRL-114 | POL-015 | Merchandising Analytics | Critical | Medium | Open | CI-APP-WORKDAY-HCM¦CI-DATA-003 | VEN-DATABRICKS | 2026-09-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-15 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-016 | Incident trend worsened for dependent service | Security | CTRL-115 | POL-016 | Contact Center Technology | High | High | Open | CI-APP-ADOBE-COMMERCE¦CI-APP-004 | VEN-SNOWFLAKE | 2026-10-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-16 | GRC Office | 2026-05-01 | 0.79 | FALSE
RISK-017 | Vendor security review due before renewal | Privacy | CTRL-116 | POL-017 | Cloud Platform Services | Medium | Medium | Mitigating | CI-APP-001¦CI-SVC-005 | VEN-OKTA | 2026-11-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-17 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-018 | Policy review date approaching without steward attestation | Compliance | CTRL-117 | POL-018 | Cybersecurity Governance | Medium | Medium | Open | CI-SVC-002¦CI-DATA-006 | VEN-CROWDSTRIKE | 2026-12-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-18 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-019 | Critical CI owner validation is stale | Financial | CTRL-118 | POL-019 | IT Sourcing | High | Medium | Open | CI-DATA-003¦CI-APP-007 | VEN-PALOALTO | 2026-01-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-19 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-020 | Renewal decision date lacks sourcing owner | AI Governance | CTRL-119 | POL-020 | Finance Technology | Medium | Medium | Open | CI-APP-004¦CI-SVC-008 | VEN-ZSCALER | 2026-02-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-20 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-021 | AI workflow lacks model monitoring evidence | Vendor | CTRL-120 | POL-021 | Commerce Platform Engineering | Medium | High | Mitigating | CI-SVC-005¦CI-DATA-009 | VEN-BROADCOM | 2026-03-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-21 | GRC Office | 2026-05-01 | 0.79 | FALSE
RISK-022 | Incident trend worsened for dependent service | Operational | CTRL-121 | POL-022 | Store Technology | Critical | Medium | Open | CI-DATA-006¦CI-APP-010 | VEN-CISCO | 2026-04-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-22 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-023 | Vendor security review due before renewal | Security | CTRL-122 | POL-023 | Supply Chain Technology | Medium | Medium | Open | CI-APP-007¦CI-SVC-011 | VEN-VEEAM | 2026-05-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-23 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-024 | Policy review date approaching without steward attestation | Privacy | CTRL-123 | POL-024 | Customer Data Platform Office | Medium | Medium | Open | CI-SVC-008¦CI-DATA-012 | VEN-HASHICORP | 2026-06-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-24 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-025 | Critical CI owner validation is stale | Compliance | CTRL-124 | POL-025 | Merchandising Analytics | High | Medium | Mitigating | CI-DATA-009¦CI-APP-013 | VEN-QLIK | 2026-07-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-25 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-026 | Renewal decision date lacks sourcing owner | Financial | CTRL-125 | POL-026 | Contact Center Technology | Medium | High | Open | CI-APP-010¦CI-SVC-014 | VEN-QUALTRICS | 2026-08-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-26 | GRC Office | 2026-05-01 | 0.79 | FALSE
RISK-027 | AI workflow lacks model monitoring evidence | AI Governance | CTRL-126 | POL-027 | Cloud Platform Services | Medium | Medium | Open | CI-SVC-011¦CI-DATA-015 | VEN-WORKDAY | 2026-09-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-27 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-028 | Incident trend worsened for dependent service | Vendor | CTRL-127 | POL-028 | Cybersecurity Governance | High | Medium | Open | CI-DATA-012¦CI-APP-016 | VEN-SAP | 2026-10-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-28 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-029 | Vendor security review due before renewal | Operational | CTRL-128 | POL-029 | IT Sourcing | Critical | Medium | Mitigating | CI-APP-013¦CI-SVC-017 | VEN-ORACLE | 2026-11-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-29 | GRC Office | 2026-05-01 | 0.79 | TRUE
RISK-030 | Policy review date approaching without steward attestation | Security | CTRL-129 | POL-030 | Finance Technology | Medium | Medium | Open | CI-SVC-014¦CI-DATA-018 | VEN-SALESFORCE | 2026-12-28 | Owner attestation, source extract, and control evidence are required. | GRC | RISK-30 | GRC Office | 2026-05-01 | 0.79 | TRUE