## Sunset Register
module | legacy_path | current_writers | current_readers | why_it_exists | convergence_problem | target_state | sunset_sequence | required_business_event_telemetry | read_only_observation_period | archive_requirement | drop_authorization | status
Moves | Golden-bar deliverables path -> deliverables_v2 -> deliverable_versions | Moves golden-bar generation/persistence path | Moves phase screens, export/review consumers to be verified live | Historical path for phase deliverable versions and structured output | Runs beside the orchestrator/generated-artifact path and can create two output truths for the same phase | One authoritative deliverable lifecycle and typed artifact contract | ACTIVE -> DUAL_RUN -> NEW_READ_PRIMARY -> LEGACY_READ_ONLY -> ARCHIVED -> DROPPED | moves.deliverable_signed_off; moves.gate_approved; moves.program_published | 60 days after new read primary | Archive historical versions with phase, tenant, move, artifact type, hash, signer, and source lineage | Explicit later approval after export and gate parity | path_level_candidate
Moves | Orchestrator deliverable path -> deliverable_runs -> generated_artifacts | Moves orchestration/generation path | Moves orchestration, review, and artifact display consumers to be verified live | Supports generated artifacts from automated phase execution | May write different structured_data shapes than golden-bar path | Both generation engines emit one typed artifact contract into one lifecycle | ACTIVE -> DUAL_RUN -> NEW_READ_PRIMARY -> LEGACY_READ_ONLY -> ARCHIVED -> DROPPED | moves.deliverable_signed_off; moves.gate_approved; moves.program_published | 60 days after typed contract parity | Retain run evidence and model/prompt lineage as audit history | Explicit later approval after historical artifact backfill | path_level_candidate
Source | Direct writeback into enterprise_context_records / enterprise_context_facts / governed_object_readiness | Source context promotion/writeback paths to be confirmed in live read/write audit | Context retrieval, aVa, Home/Knowledge, Source evidence views to be verified live | Publishes Source-derived facts into enterprise context for reuse | Writeback path is not yet proven to run through a common governance/publication adapter | Governed promotion adapter with identity map, review state, tenant fence, and evidence lineage | ACTIVE -> DUAL_RUN -> GOVERNED_WRITE_PRIMARY -> LEGACY_WRITE_BLOCKED -> ARCHIVED -> DROPPED | source.artifact_accepted; source.stage_advanced; source.decision_published | 60 days after governed write primary | Retain previous promoted rows as superseded evidence with source path and write timestamp | Explicit later approval after retrieval parity | path_level_candidate
Tower | Overlapping source input trees and derived folders consumed as source | Tower materialization/input generators to be verified live | Tower marts, Tower aVa, exports, and dashboards | Fast Tower demonstrations and deterministic marts were built from mixed inputs | Two input trees can disagree and derived outputs can be re-consumed as source | Registered source inputs only; derived outputs marked as projections, never source | ACTIVE -> DUAL_RUN -> REGISTERED_SOURCE_PRIMARY -> LEGACY_READ_ONLY -> ARCHIVED -> DROPPED | tower.metric_attested; tower.lineage_blocked; tower.decision_recorded | 90 days after registered-source mart parity | Archive old input snapshots and lineage reports with digest and materialization run id | Explicit later approval after headline metric reconciliation | path_level_candidate
Tower | Precedence-based merge and advisory lineage report | Tower mart builders and lineage report scripts to be verified live | Tower command center, answer packets, exports, and proof reports | Allows a complete mart when source inputs conflict or lineage is incomplete | Lineage warnings are advisory rather than blocking for material claims | Blocking lineage validation before metric publication and headline display | ACTIVE -> BLOCKING_SHADOW -> BLOCKING_PRIMARY -> LEGACY_READ_ONLY -> ARCHIVED -> DROPPED | tower.lineage_blocked; tower.metric_attested | 90 days after blocking validation primary | Keep advisory reports as historical quality evidence | Explicit later approval after all headline metrics reconcile | path_level_candidate
Cross-module | Duplicated local IDs and module-specific object identity | Moves, Source, Tower domain workflows | All module screens, aVa packets, exports, and reports | Each product evolved its own workflow model and local identifiers | Same enterprise object can appear as separate vendor, program, contract, metric, risk, or evidence object | Canonical identity map preserving local IDs while linking reviewed enterprise objects | ACTIVE -> IDENTITY_SHADOW -> CANONICAL_READ_PRIMARY -> LEGACY_READ_ONLY -> ARCHIVED -> DROPPED | module.object_published; module.identity_link_reviewed | 90 days after canonical read primary | Retain old local IDs and crosswalk history permanently | Explicit later approval; many local IDs may never be dropped | path_level_candidate
Cross-module | Duplicated reporting and metric logic in routes/components | Module-specific API routes, components, and report scripts | Module screens, exports, BI surfaces, aVa answer packets | Local products needed fast calculations before shared metrics existed | Same number can be calculated differently by different surfaces | Shared metric definitions plus consumption projections | ACTIVE -> DUAL_RUN -> SHARED_METRIC_PRIMARY -> LEGACY_READ_ONLY -> ARCHIVED -> DROPPED | metric.definition_published; metric.observation_attested | 60 days after shared metric primary | Keep old formula output as reconciliation evidence | Explicit later approval after formula parity | path_level_candidate
Cross-module | Telemetry limited to generic page/click events | Current analytics/telemetry instrumentation | Operational monitoring and product analytics | Captures broad product usage | Cannot prove whether business-critical legacy paths are dormant | Business-event telemetry before migration and sunset | ACTIVE -> BUSINESS_EVENTS_ADDED -> DUAL_RUN_OBSERVED -> LEGACY_READ_ONLY -> ARCHIVED | source.*, moves.*, tower.* events listed in telemetry catalog | At least 60 days with business-event coverage | Retain event stream snapshots for migration evidence | No destructive drop without event-backed dormancy proof | pre_migration_requirement