## Migration Backlog
wave | module | current_object_or_path | current_authority | current_writers | current_readers | target_operational_owner | canonical_promotion_target | target_consumption_projection | migration_method | historical_backfill | dual_run_requirement | reconciliation_rule | cutover_dependency | rollback_path | read_only_observation_period | archive_requirement | drop_authorization | status
Wave 0 shared foundation | Cross-module | canonical identity map | not yet authorized by audit | none | future canonical publications and projections | Governance | governance.object_identity_map |  | Design and approve before any module migration | none until identity policy is approved | Identity shadow mode before any read cutover | Every local object link has tenant, type, confidence, review state, and history | Healthcare certified Knowledge Baseline | Do not use canonical identity reads until approved | Not applicable | Identity map changes are append-only | Not applicable | foundation_required
Wave 0 shared foundation | Cross-module | module promotion outbox | not yet authorized by audit | none | future publication adapters | Governance | governance.module_publication_outbox |  | Implement after Healthcare publication lifecycle proves out | none before approved replay strategy | Required with old direct-write paths | Outbox event count equals accepted domain event count by tenant/module/object family | Business-event telemetry active | Stop outbox processing; retain domain workflow tables | 30 days before write primary | Outbox events retained as audit stream | Not applicable | foundation_required
Wave 0 shared foundation | Cross-module | shared metric definition contract | Tower/local module metric definitions | module-specific formula paths | Tower, Source, Moves, aVa, future BI | Governance + metric owner | knowledge.metric_definition | consumption.metric_observation_* | Separate definition from observation; publish formula versions before observations | Backfill current definitions first, then observations | Required for every headline number | Formula, period, unit, basis, source, and value parity | Metric owner attestation and lineage validation | Revert consumers to module-specific calculation while keeping shared definitions candidate | 60 days | Preserve old formula outputs for reconciliation | Explicit later approval | foundation_required
Module-specific workflow preservation | Moves | public.move_artifact_review_decisions | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Moves | public.move_artifacts | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Moves | public.move_dependencies | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/__tests__/repository.azure-read.test.ts; src/lib/tower/value-states/repository.ts | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Moves | public.move_instances | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/repository.ts | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Moves | public.move_template_artifacts | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Moves | public.move_template_gates | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Moves | public.move_template_review_state | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Moves | public.move_template_versions | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Moves | public.move_templates | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/repository.ts | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Moves | public.program_evidence_reviews | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/audit/moves-evidence-lifecycle.mjs | Moves |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.ai_control_sources | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.data_inventory_records | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/source/adapters/apex-retail-adapter.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.data_sources | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.enterprise_context_chunks | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/audit/demo-question-readiness.mjs; src/lib/source/adapters/apex-retail-adapter.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.enterprise_context_source_files | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.enterprise_context_sources | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.evidence | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/audit/build-data-intelligence-redesign-report.mjs; scripts/audit/meridian-data-state-reconciliation.mjs; scripts/tower/tower-data-trust-gate.mjs; src/lib/source/__tests__/gate-auto-assessment.test.ts; src/lib/source/agent-generation/prompt-registry.ts; src/lib/source/archetypes/registry.ts; src/lib/source/gate-auto-assessment-persist.ts; src/lib/source/gate-auto-assessment.ts | Source until publication | knowledge.evidence |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.external_sources | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.home_knowledge_evidence_sources | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source until publication | knowledge.evidence |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.knowledge_sources | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.person_client_memberships | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/source/load-skyharbor-contract-optimization.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.persons | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/source/load-skyharbor-contract-optimization.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_artifact_acceptances | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/source/artifact-acceptances.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_artifact_chunks | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/app/api/v1/source/[eventId]/nexus/ask/route.ts; src/lib/source/agent-generation/context-binder.ts; src/lib/source/artifact-registry/text-parser.ts | Source until publication | knowledge.evidence_chunk |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_artifact_facts | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/app/api/v1/source/[eventId]/nexus/ask/route.ts; src/lib/source/agent-generation/context-binder.ts; src/lib/source/artifact-registry/text-parser.ts | Source until publication | knowledge.fact |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_artifacts | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/audit/knowledge-layer-inventory.sql; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/accept/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/client-final/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/render/route.ts; src/app/api/v1/source/[eventId]/nexus/ask/route.ts; src/lib/source/agent-generation/context-binder.ts; src/lib/source/artifact-registry/index.ts; src/lib/source/contracts/upstream-satisfaction.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_commercial_exceptions | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_context_receipts | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_contract_evidence_manifests | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/contract-evidence/persistence.ts; src/lib/source/contract-evidence/read-model.ts | Source until publication | knowledge.contract |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_contract_evidence_metrics | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/contract-evidence/persistence.ts; src/lib/source/contract-evidence/read-model.ts | Source until publication | knowledge.contract |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_contract_evidence_rows | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/contract-evidence/persistence.ts; src/lib/source/contract-evidence/read-model.ts | Source until publication | knowledge.contract |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_contract_optimization_findings | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/source/load-skyharbor-contract-optimization.ts | Source until publication | knowledge.contract |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_contract_optimization_levers | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/source/load-skyharbor-contract-optimization.ts | Source until publication | knowledge.contract |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_contract_optimization_profiles | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/source/load-skyharbor-contract-optimization.ts | Source until publication | knowledge.contract |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_event_activity | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/source/activity-log.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_event_approvals | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/source/__tests__/approval-ledger.test.ts; src/lib/source/approval-ledger-model.ts; src/lib/source/approval-ledger.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_event_artifact_states | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/qa/lakeshore-ams-artifact-audit.mjs; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/accept/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/body/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/client-final/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/enqueue-worker/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/generate/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/safe-repair/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/status/route.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_event_code_backfill_audit | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_event_evidence_states | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/app/api/v1/source/[eventId]/evidence/[requirementId]/answer/route.ts; src/app/api/v1/source/[eventId]/gate-criteria/[criterionId]/state/route.ts; src/app/api/v1/source/[eventId]/stage/route.ts; src/app/api/v1/source/[eventId]/test-reset/route.ts; src/lib/source/canvas-substrate/upload-sync.ts; src/lib/source/queries.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_event_facts | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/door1/facts-reader.ts; src/lib/source/facts/evaluators/orchestrator.ts; src/lib/source/facts/event-facts-reader.ts | Source until publication | knowledge.fact |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_event_gate_criterion_states | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/app/api/v1/source/[eventId]/artifacts/upload/route.ts; src/app/api/v1/source/[eventId]/gate-criteria/[criterionId]/state/route.ts; src/app/api/v1/source/[eventId]/stage/route.ts; src/app/api/v1/source/[eventId]/test-reset/route.ts; src/lib/source/approvals-inbox.ts; src/lib/source/canvas-substrate/upload-sync.ts; src/lib/source/queries.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_event_participants | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/source/load-skyharbor-contract-optimization.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_event_pricing_submissions | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/source/pricing-submissions/__tests__/dao.azure-read.test.ts; src/lib/source/pricing-submissions/dao.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_events | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/audit/live-tenant-population-audit.mjs; scripts/qa/lakeshore-ams-artifact-audit.mjs; scripts/source/load-skyharbor-contract-optimization.ts; src/app/(maestro)/source/events/[eventId]/approval/page.tsx; src/app/(maestro)/source/events/[eventId]/page.tsx; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/accept/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/body/route.ts; src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/client-final/route.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_graph_edges | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_meeting_outcomes | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/artifact-registry/text-parser.ts | Source until publication | knowledge.metric |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_pricing_components | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/source/artifact-registry/text-parser.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_reasoning_envelopes | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/app/api/v1/source/[eventId]/artifacts/[artifactCode]/generate/route.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_requirements | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/source/artifact-registry/text-parser.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_stage_guidebooks | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/source/stage-guidebooks/repository.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_value_chain | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/value-chain.ts | Source until publication | knowledge.metric |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_value_levers | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/facts/evaluators/value-lever-write-adapter.ts | Source until publication | knowledge.metric |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_value_lines | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/__tests__/repository.azure-read.test.ts; src/lib/tower/value-states/repository.ts | Source until publication | knowledge.metric |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_value_states | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/value-chain.ts | Source until publication | knowledge.metric |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_vendor_commitments | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/artifact-registry/text-parser.ts | Source until publication | knowledge.vendor |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.source_vendor_proposal_fact_reviews | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/source/vendor-proposals/__tests__/vendor-proposal-facts.test.ts; src/lib/source/vendor-proposals/vendor-proposal-facts.ts | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.source_vendor_proposal_facts | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/source/vendor-proposals/vendor-proposal-facts.ts | Source until publication | knowledge.vendor |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Source | public.telemetry_sources | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Source |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Source | public.vendor_contracts | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/audit/demo-question-readiness.mjs; src/lib/source/exports/payloads/renewal-decision-payload.ts | Source until publication | knowledge.vendor |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | cio_tower.entities | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/tower/load-cio-tower-standardized-v1.mjs; scripts/tower/project-meridian-v3-to-cio-tower.mjs; scripts/tower/query-cio-tower-proof.mjs; scripts/tower/validate-cio-tower-quality.mjs; src/lib/cio-tower/answer.ts; src/lib/cio-tower/cxo-view-model.ts; src/lib/tower/tower-budget-rollups.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | cio_tower.facts | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/tower/load-cio-tower-standardized-v1.mjs; scripts/tower/project-meridian-v3-to-cio-tower.mjs; scripts/tower/query-cio-tower-proof.mjs; scripts/tower/validate-cio-tower-quality.mjs; src/lib/cio-tower/answer.ts; src/lib/cio-tower/cxo-view-model.ts; src/lib/cio-tower/mart-projection/merge-facts.ts; src/lib/tower/tower-budget-rollups.ts | Tower until publication |  | consumption.metric_facts | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | cio_tower.mart_ai_portfolio | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/tower/project-meridian-v3-to-cio-tower.mjs; src/lib/cio-tower/tower-mart-view-model.ts | Tower until publication |  | consumption.mart_ai_portfolio | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | cio_tower.mart_command_center | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/tower/project-meridian-v3-to-cio-tower.mjs; src/lib/cio-tower/tower-mart-view-model.ts | Tower until publication |  | consumption.mart_command_center | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | cio_tower.mart_cxo_actions | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/tower/project-meridian-v3-to-cio-tower.mjs; src/lib/cio-tower/tower-mart-view-model.ts | Tower until publication |  | consumption.mart_cxo_actions | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | cio_tower.mart_evidence_lineage | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/tower/project-meridian-v3-to-cio-tower.mjs; src/lib/cio-tower/tower-mart-view-model.ts | Tower until publication |  | consumption.evidence_mart_evidence_lineage | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | cio_tower.mart_program_decision_lanes | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/tower/project-meridian-v3-to-cio-tower.mjs; src/lib/cio-tower/tower-mart-view-model.ts | Tower until publication |  | consumption.program_mart_program_decision_lanes | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | cio_tower.mart_required_field_gaps | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/tower/project-meridian-v3-to-cio-tower.mjs; src/lib/cio-tower/tower-mart-view-model.ts | Tower until publication |  | consumption.mart_required_field_gaps | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | cio_tower.mart_value_funnel | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/tower/project-meridian-v3-to-cio-tower.mjs; src/lib/cio-tower/tower-mart-view-model.ts | Tower until publication |  | consumption.metric_mart_value_funnel | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | cio_tower.measure_results | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/qa/tower-answer-contract-server-runner.ts; scripts/tower/load-cio-tower-standardized-v1.mjs; scripts/tower/project-meridian-v3-to-cio-tower.mjs; scripts/tower/query-cio-tower-proof.mjs; scripts/tower/validate-cio-tower-quality.mjs; src/lib/cio-tower/answer.ts; src/lib/cio-tower/cxo-view-model.ts; src/lib/cio-tower/metric-packet-store.ts | Tower until publication |  | consumption.metric_measure_results | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | cio_tower.measures | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/qa/tower-answer-contract-server-runner.ts; scripts/tower/load-cio-tower-standardized-v1.mjs; src/lib/cio-tower/answer.ts; src/lib/cio-tower/cxo-view-model.ts; src/lib/cio-tower/metric-packet-store.ts | Tower until publication | knowledge.metric_definition |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | cio_tower.prompt_packages | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/qa/tower-answer-contract-executor.ts; scripts/tower/query-cio-tower-answer-traces.mjs; src/lib/cio-tower/answer.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | cio_tower.question_contracts | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/tower/load-cio-tower-standardized-v1.mjs; scripts/tower/validate-cio-tower-quality.mjs; src/lib/cio-tower/answer.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | cio_tower.relationships | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/tower/load-cio-tower-standardized-v1.mjs; scripts/tower/project-meridian-v3-to-cio-tower.mjs; scripts/tower/query-cio-tower-proof.mjs; scripts/tower/validate-cio-tower-quality.mjs; src/lib/cio-tower/answer.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | cio_tower.source_registry | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/tower/load-cio-tower-standardized-v1.mjs; scripts/tower/project-meridian-v3-to-cio-tower.mjs; scripts/tower/query-cio-tower-proof.mjs; scripts/tower/validate-cio-tower-quality.mjs; src/lib/cio-tower/cxo-view-model.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | cio_tower.tool_identity_aliases | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | to_be_mapped |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | cio_tower.validation_results | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | cio_tower.validation_runs | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | intelligence_v7.active_tenant_contract_versions | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/audit/candidate-invisibility-guard.mjs; src/lib/tower/__tests__/v7-tower-projection.test.ts; src/lib/tower/v7-tower-projection.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_actions | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.risk_control |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_agent_outcomes | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.metric |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | public.ai_control_atlas_context_packs | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication |  | consumption.context_ai_control_atlas_context_packs | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_benefit_realization | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.risk_control |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_context_facts | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.risk_control |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_context_relationships | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.risk_control |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_dora_metrics | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.metric |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_evidence_items | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.risk_control |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_initiatives | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.program |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_persona_productivity | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.risk_control |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.ai_control_refresh_runs | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_risk_governance | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.risk_control |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_spend_contracts | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.contract |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.ai_control_tool_usage_monthly | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.risk_control |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | public.ai_control_tower_lens_mv | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication |  | consumption.ai_control_tower_lens_mv | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.ai_tool_footprint | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/repository.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.application_portfolio | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/repository.ts | Tower until publication | knowledge.application |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.clients | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/audit/ai-egress-cost-trace.ts; scripts/audit/demo-question-readiness.mjs; scripts/audit/live-tenant-population-audit.mjs; scripts/qa/home-intelligence-50q-live-audit.mjs; scripts/source/load-skyharbor-contract-optimization.ts; scripts/tower/ensure-lakeshore-industries-client.mjs; src/lib/tower/ingest/github-dora/ingest.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.discovery_instruments | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/repository.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.dora_baselines | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/repository.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.engagements | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | scripts/audit/knowledge-layer-inventory.sql; scripts/audit/live-tenant-population-audit.mjs; src/lib/tower/value-states/__tests__/repository.azure-read.test.ts; src/lib/tower/value-states/repository.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.enterprise_context_records | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | scripts/audit/build-module-migration-sunset-backlog.mjs; scripts/qa/home-know-data-gate.mjs; src/lib/tower/tower-budget-rollups.ts; src/lib/tower/tower-semantic-projection.ts | Tower until publication | to_be_mapped |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.kill_criteria | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/repository.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.pricing_towers | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.roles_inventory | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/repository.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.teams | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/types.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_ai_tool_usage | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/cio-tower/mart-projection/tool-identity-crosswalk.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | public.tower_budget_rollups | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication |  | consumption.tower_budget_rollups | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_claude_code_usage | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_cloud_cost | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.tower_cmdb_cis | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/tower/ingest/servicenow-cmdb/upsert.ts | Tower until publication | knowledge.application |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | public.tower_cmdb_dependencies | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/tower/ingest/servicenow-cmdb/upsert.ts | Tower until publication |  | consumption.relationship_tower_cmdb_dependencies | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | public.tower_dora_metrics | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/tower/ingest/github-dora/ingest.ts | Tower until publication |  | consumption.metric_tower_dora_metrics | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_forbidden_identifiers | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_gap_register | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_itsm_records | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/ingest/servicenow-itsm/writer.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_jira_issues | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_l3_answer_dossiers | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/tower-l3-dossiers.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_materialization_runs | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | public.tower_program_financials | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/tower/ingest/erp/writer.ts | Tower until publication |  | consumption.metric_tower_program_financials | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_read_model_initiatives | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.tower_read_model_vendors | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower until publication | knowledge.vendor |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_spend_realism_audit | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_user_preferences | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | No focused code consumer found | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 5 cross-module consumption | Tower | public.tower_vendor_spend | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/tower/ingest/erp/writer.ts | Tower until publication |  | consumption.metric_tower_vendor_spend | Build/refresh projection from active publications; dual-read compare before switching consumers | Backfill published observations needed for baseline reports and exports | Required: old module read versus new projection read | Counts, tenant scope, lineage, period, unit, and headline metric parity | Build stable projection; dual-read compare; switch dashboards/aVa after parity. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.tower_workforce | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/ingest/workday-hcm/ingest.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only
Wave 1 identity and references | Tower | public.use_cases | Candidate/domain-derived; not canonical until promoted | Live writer inspection required; static audit records focused consumers only | src/lib/tower/ingest-portfolio.ts | Tower until publication | knowledge.program |  | Map local IDs through governance.object_identity_map; publish reviewed facts through canonical adapter | Backfill approved/current rows only after stale/superseded filtering | Required for promoted object family until identity and fact parity pass | One local object maps to one canonical object or an explicit reviewed many-to-one link | Backfill identity map; shadow-read canonical projection; switch consumers after reconciliation. | Revert consumer flag to domain read path; preserve published rows as superseded audit evidence | 30-60 days after new read primary | Keep legacy rows immutable during observation | Explicit later approval required; not authorized by this package | planning_only
Module-specific workflow preservation | Tower | public.value_states | Domain workflow system of record | Live writer inspection required; static audit records focused consumers only | src/lib/tower/value-states/repository.ts | Tower |  |  | Preserve current table; add publication outbox only when accepted enterprise facts are emitted | No backfill until workflow emits accepted publication | No dual-run until a consumer moves off local reads | Operational behavior must remain unchanged | Keep domain owner path; publish outbox if facts are accepted. | Keep current domain read/write path | Not applicable before consumer migration | None now | Explicit later approval required; not authorized by this package | planning_only