## Einstein Status
APEX RETAIL — Salesforce Einstein Activation Status (18 Months Post-Deployment)
Einstein Module | Licensed? | Activated? | Adoption % | Revenue Opportunity ($M) | Blocker | Priority | Time to Activate
Einstein Personalisation (Commerce) | Yes | No | 0% | 142 | No configuration. No product catalogue sync. No customer data model. | Critical | 8 weeks with Maestro
Einstein Recommendations | Yes | No | 0% | 48 | Depends on personalisation activation. Sequential. | Critical | 10 weeks (after personalisation)
Einstein Search | Yes | Partial | 18% | 22 | Partial activation. No AI ranking. Rules-based only. | High | 4 weeks
Einstein Next Best Action | Yes | No | 0% | 18 | No decision logic configured. Sales team not trained. | High | 6 weeks
Einstein Forecasting | Yes | No | 0% | 12 | Salesforce data quality insufficient. Clean data required. | High | 12 weeks (data prep first)
Einstein Bots (Service) | Yes | Partial | 12% | 8 | 2 of 8 intents configured. Bot handles 12% of service queries. | Medium | 8 weeks to full activation
Einstein Vision (Loss Prevention) | Yes | No | 0% | 16 | Camera infrastructure not connected. IT project required. | Medium | 16 weeks (IT infrastructure)
Einstein Analytics (Tableau CRM) | Yes | Partial | 34% | N/A | Some dashboards built. Predictive features not enabled. | Medium | 4 weeks
TOTAL UNACTIVATED OPPORTUNITY | — | — | 23% avg | $248M+ | See individual modules above | — | 10-16 weeks phased