## Consulting Audit
ARCTURUS — Consulting Output vs Promise Audit (All Active Engagements)
Vendor | Engagement | Promised Deliverable | Delivered? | Quality /10 | Knowledge Transferred? | Annual Cost (£M) | Value Rating | Maestro Replacement?
Bloomberg LP | OMS Core Maintenance | 24/7 support, 99.9% uptime, quarterly feature releases | Partial — SLA met, features delayed | 6 | No — vendor owns all knowledge | 8.4 | Poor — trapped dependency | Yes — API wrapper + internal OMS team
Infosys | Risk Tech & Analytics Development | 90% sprint velocity, knowledge wiki, internal team upskilling | No — 71% velocity, wiki incomplete, no upskilling | 5 | No — 22% KT score | 3.6 | Below expectations | Yes — 2 Maestros replace 12 Infosys
Wipro | Client Portal + Data Platform | 85% velocity, full knowledge transfer, golden record delivery | No — 58% velocity, KT 15%, golden record not started | 3 | No — Wipro own all customisations | 4.8 | Poor — knowledge hostage | Yes — exit plan + 2 Maestros
Deloitte | MAS FEAT Compliance Programme | Compliance by December 2025, internal team capability | No — deadline missed, internal team not capable | 4 | Partial — 45% KT | 2.6 | Below expectations — advisory only | Partial — internal compliance team with Maestro support
TCS | APAC Technology Operations | 96% SLA, knowledge transfer, documentation | Yes for SLA, partial for KT | 6 | Partial — 38% KT | 0.9 | Adequate | No — retain, value for APAC ops
Google PSO | AI/ML Platform Setup | Full MLOps infrastructure delivered | No — 22% delivered, engagement ended | 2 | No — 5% KT score | 3.5 | Failed | Yes — internal ML engineering with Maestro
AWS ProServe | Infrastructure Modernisation | Runbook delivery, internal team training | Mostly — 88% complete | 7 | Partial — 62% KT | 1.4 | Good — retain | No — continue with internal support
Salesforce PS | FSC Customisation | Feature delivery, internal admin capability | Partial — 71% features, no admin capability | 5 | No — 28% KT | 1.6 | Below expectations | Yes — internal Salesforce admin team
Various Contractors | Enterprise Architecture | Architecture decisions, documentation | No — no documentation, no knowledge retention | 1 | None — 0% KT | 1.8 | Critical risk | Yes — permanent EA hire + Maestro