## AI Spend ROI
ARCTURUS — AI Investment ROI Tracker (£94M Committed · £0 Verified Return)
Initiative | Budget Committed (£M) | Spent to Date (£M) | Expected ROI (£M pa) | Verified ROI (£M) | ROI Gap (£M) | Months Since Start | Status | Root Cause of Zero ROI
AI Trade Execution Optimisation | 4.2 | 3.8 | 12 | 0 | -12 | 25 | Pilot - Stalled | No MLOps. No deployment infrastructure. Model trained, cannot serve.
Portfolio Rebalancing AI | 3.1 | 2.6 | 8 | 0 | -8 | 27 | Pilot - Stalled | Bloomberg data latency. Manual override required. Cannot automate.
ESG Scoring Automation | 2.4 | 1.8 | 4 | 0 | -4 | 19 | In Development | ESG data inconsistent. No golden record. Model not trained on reliable data.
Client Sentiment Analysis | 1.8 | 1.4 | 6 | 0 | -6 | 24 | Pilot - Stalled | CDO vacant. No governance. FSC data sparse. Cannot build model.
MAS FEAT Compliance AI | 3.6 | 2.9 | 18 | 0 | -18 | 21 | BREACH — Overdue | Deployed too late. Manual process continued. Now regulatory breach.
Risk Model Automation | 4.8 | 4.1 | 9 | 0 | -9 | 31 | Pilot - Stalled | CDO vacant for 11 months. No model risk sign-off possible.
NL Client Reporting | 2.1 | 1.2 | 5 | 0 | -5 | 15 | In Development | 3-day data lag. Reports on stale data. Useless for clients.
Fraud Detection AI | 2.8 | 2.3 | 7 | 0 | -7 | 26 | Pilot - Stalled | Transaction data in 5 systems. No unified feed. Cannot train reliably.
AI Trade Surveillance | 4.1 | 3.4 | 14 | 0 | -14 | 24 | Pilot - Stalled | FCA model validation required. No framework. CDO vacant.
Real-Time Performance Attribution | 3.8 | 3.2 | 8 | 0 | -8 | 27 | Pilot - Stalled | Bloomberg latency. No streaming infrastructure. T+1 at best.
Predictive Cash Flow | 1.9 | 1.1 | 6 | 0 | -6 | 15 | In Development | 3-day data lag makes 30-day forecasts inaccurate.
AI Regulatory Capital | 2.9 | 2.4 | 12 | 0 | -12 | 24 | Pilot - Stalled | Model validation absent. CDO vacant. Cannot deploy.
AI Investment Research (AI-023) | 1.8 | 1 | 6 | 0 | -6 | 15 | In Development | Best chance at production. Needs serving infrastructure only.
AI Trade Matching | 3.4 | 2.9 | 9 | 0 | -9 | 26 | Pilot - Stalled | Custodian data fragmented. No unified settlement feed.
Automated Client Onboarding | 3.2 | 2.7 | 11 | 0 | -11 | 22 | Pilot - Stalled | CDO vacant. Regulatory AI framework undefined.
Earnings Call Analysis (AI-026) | 1.4 | 0.8 | 4 | 0 | -4 | 15 | In Development | External data. Near production. Needs serving layer only.
Automated Compliance Monitoring | 2.8 | 2.3 | 10 | 0 | -10 | 22 | Pilot - Stalled | Mandate data in 14 formats. No unified compliance layer.
Dynamic Asset Allocation | 5.6 | 0.8 | 22 | 0 | -22 | 6 | Concept | Foundation not in place. Should not have been started.
Remaining initiatives (10) | 38.4 | 24.6 | 63 | 0 | -63 | Various | Various stalled | All blocked by same root causes: MLOps, data quality, CDO vacancy.
TOTALS