## AI Spend ROI
MERIDIAN HEALTH — AI Spend ROI Tracker ($94M Committed · $0 Verified)
Initiative | Budget ($M) | Spent ($M) | Expected ROI ($M pa) | Verified ROI ($M) | Months Active | Status | Root Cause / Fix
Prior Auth Automation | 8.4 | 6.2 | 37.6 | 0 | 18 | Pilot - Stalled | Epic integration incomplete. No MLOps. Cohere Health pilot approved but not deployed. Fix: Epic API + serving layer.
GenAI Clinical Documentation | 4.2 | 2.8 | 42 | 0 | 12 | Pilot - Limited | AWS Bedrock ready. 10-physician pilot positive. No enterprise deployment plan. CDO needed for clinical AI governance. Fix: CDO + deployment plan.
Predictive Readmission | 1.8 | 0.2 | 6 | 0 | 6 | Concept - Blocked | Epic data quality insufficient. Fix: Epic optimization sprint first.
Clinical Coding AI (3M HIS) | 2.8 | 1.9 | 11 | 0 | 14 | Pilot - Improving | 84% accuracy vs 96% needed. Continuing. Fix: More Meridian-specific training data.
Patient No-Show Prediction | 0.9 | 0.6 | 4 | 0 | 10 | Pilot - Ready | Model trained. No serving infrastructure. Fix: SageMaker endpoint — 4 weeks.
Supply Chain Stockout AI | 1.4 | 0.2 | 3 | 0 | 6 | Concept | Data in Infor not accessible to ML. Fix: Infor API integration.
Telehealth Triage AI | 2.2 | 0.3 | 8 | 0 | 4 | Concept - Blocked | CDO required for clinical AI governance. Fix: CDO appointment.
MA Star Rating AI | 3.4 | 0.4 | 24 | 0 | 6 | Concept - Blocked | CDO required. Multiple Epic modules need coordination. Fix: CDO + Epic Healthy Planet activation.
Travel Nurse Forecasting | 1.2 | 0.8 | 8 | 0 | 10 | In Development | Workforce data in 3 systems. Fix: Data consolidation + ML pipeline.
Ambient Documentation (Nuance DAX) | 0.3 | 0.3 | 3 | 0 | 6 | Pilot - Limited | 10-physician pilot. Budget small. Competing with GenAI option. Fix: Choose GenAI or DAX — don't run both.
Salesforce Health Cloud AI | 1.4 | 0.4 | 5 | 0 | 8 | Pilot - Low adoption | 38% adoption limits AI value. Fix: Adoption programme first.
All other / exploration | 66 | 48.7 | 0 | 0 | Various | Various | Various exploratory spending. Poorly tracked. CDO needed to govern.
TOTALS