## Sprint Velocity
MERIDIAN HEALTH — Sprint Velocity by Squad (Apr 2025 – Mar 2026)
Squad | Quarter | Planned Pts | Completed Pts | Velocity % | Unplanned % | Carryover % | Deployments | Incidents | Vendor Blocked | AI Initiative Blocked | RAG | Notes
Epic EHR Core | Q1 2025 | 55 | 48 |  | 18% | 14% | 1 | 1 | 2 | 0 | Amber | Epic upgrade Q1 consumed 3 sprints. Internal feature delivery paused.
Epic EHR Core | Q2 2025 | 52 | 44 |  | 22% | 18% | 1 | 2 | 3 | 0 | Red | Epic upgrade delayed. 3 payer integration fixes required mid-sprint.
Epic EHR Core | Q3 2025 | 58 | 51 |  | 16% | 12% | 2 | 1 | 2 | 0 | Amber | Better quarter. MyChart module work progressing.
Epic EHR Core | Q4 2025 | 54 | 47 |  | 19% | 15% | 1 | 1 | 2 | 0 | Amber | Year-end freeze reduced capacity. Epic controls Q4 window.
Revenue Cycle Technology | Q1 2025 | 38 | 26 |  | 32% | 28% | 0 | 3 | 5 | 0 | Red | Ensemble Health SLA breach Q1. $2.1M in denied claims traced to integration bug. Ensemble fixed after 6 weeks.
Revenue Cycle Technology | Q2 2025 | 35 | 24 |  | 34% | 30% | 0 | 4 | 6 | 0 | Red | Denial rate worsening. Ensemble contract renegotiation underway. Squad morale low.
Revenue Cycle Technology | Q3 2025 | 36 | 26 |  | 30% | 26% | 0 | 3 | 5 | 0 | Red | Ensemble vendor fix deployed. Partial recovery. Internal team still cannot modify RCM logic.
Revenue Cycle Technology | Q4 2025 | 34 | 23 |  | 35% | 31% | 0 | 4 | 5 | 0 | Red | Ensemble SLA penalty $1.8M claimed but disputed. Denial rate 18.2% at year end.
AI & Innovation Lab | Q1 2025 | 28 | 16 |  | 42% | 38% | 0 | 0 | 0 | 6 | Red | 6 AI initiatives stalled. CDO search started. No sponsor for AI deployments.
AI & Innovation Lab | Q2 2025 | 25 | 12 |  | 48% | 44% | 0 | 0 | 0 | 8 | Red | Prior auth pilot failed integration testing. CDO search month 4. No production deployments.
AI & Innovation Lab | Q3 2025 | 22 | 10 |  | 52% | 48% | 0 | 0 | 0 | 9 | Red | GenAI documentation pilot positive feedback but no enterprise deployment approved without CDO.
AI & Innovation Lab | Q4 2025 | 20 | 9 |  | 55% | 51% | 0 | 0 | 0 | 10 | Red | 10 items blocked for CDO approval. Zero production AI. $94M portfolio idle.
Prior Auth & Payer Integration | Q1 2025 | 24 | 14 |  | 40% | 36% | 0 | 2 | 0 | 0 | Red | Lead vacant month 1. CMS prior auth mandate January 2027 — 21 months. No automation started.
Prior Auth & Payer Integration | Q2 2025 | 20 | 11 |  | 44% | 40% | 0 | 3 | 0 | 0 | Red | Cohere Health pilot proposal approved but no project lead to run it.
Prior Auth & Payer Integration | Q3 2025 | 18 | 10 |  | 46% | 42% | 0 | 2 | 0 | 0 | Red | Interim contractor assigned. 18 months to CMS deadline. Electronic prior auth design not started.
Prior Auth & Payer Integration | Q4 2025 | 16 | 9 |  | 48% | 44% | 0 | 3 | 0 | 0 | Red | 14 months to CMS mandate. Electronic prior auth — zero progress. $37.6M value idle.
Patient Engagement & MyChart | Q1 2025 | 42 | 36 |  | 14% | 10% | 3 | 1 | 0 | 0 | Amber | MyChart adoption 34%. Module rollout programme started Q1.
Patient Engagement & MyChart | Q2 2025 | 44 | 38 |  | 12% | 8% | 4 | 1 | 0 | 1 | Amber | MyChart 35%. 1 AI feature blocked (sentiment analysis — no CDO).
Patient Engagement & MyChart | Q3 2025 | 46 | 41 |  | 10% | 6% | 4 | 0 | 0 | 0 | Green | Best quarter. Patient portal redesign launched. Adoption 36%.
Patient Engagement & MyChart | Q4 2025 | 44 | 39 |  | 12% | 8% | 3 | 1 | 0 | 1 | Amber | Adoption 37%. Progress slow — target 60%. 1 AI feature still blocked.
Infrastructure & Cloud | Q1 2025 | 60 | 56 |  | 8% | 4% | 8 | 1 | 0 | 0 | Green | Strong. Cloud migration progressing. AWS Bedrock POC started.
Infrastructure & Cloud | Q2 2025 | 62 | 58 |  | 7% | 3% | 9 | 0 | 0 | 0 | Green | Excellent. No ML pipeline yet but infra for it being designed.
Infrastructure & Cloud | Q3 2025 | 64 | 60 |  | 6% | 3% | 10 | 1 | 0 | 0 | Green | Best squad. ML pipeline scoped — waiting on AI Lab direction.
Infrastructure & Cloud | Q4 2025 | 62 | 57 |  | 8% | 4% | 8 | 1 | 0 | 0 | Green | Solid. Year-end good. AWS Bedrock access configured for GenAI.