## AI Initiatives
MERIDIAN HEALTH SYSTEM — AI Initiative Inventory (FY2026)
ID | Initiative | Sponsor | Status | Budget ($M) | Spent ($M) | ROI Verified ($M) | Data Readiness | Genome Pattern | Blocker | Annual Value ($M) | Recommendation
AI-001 | Prior Auth Automation (Cohere Health) | Robert Chen (CIO) | Pilot — CMS mandate pressing | 8.4 | 6.2 | 0 | 62% | F006 (79%) — no MLOps infra | Epic integration 60% complete. No deployment pipeline. | 37.6 | PRIORITY 1. $37.6M value. 91% Genome confidence. Cohere Health scored 94/100. CMS mandate January 2027.
AI-002 | GenAI Clinical Documentation | Dr. Sarah Kim (CMIO) | Pilot — physician demand high | 4.2 | 2.8 | 0 | 58% | F008 (61%) — adoption risk | Pilot positive. 2 departments. No enterprise deployment plan. CDO needed. | 42 | PRIORITY 2. $42M productivity. 68% of physicians cite documentation burden. AWS Bedrock ready.
AI-003 | CDO Executive Hire | Emily Rodriguez (CEO) | Search active — month 4 | 0.4 | 0.2 | 0 | N/A | F002 (84%) — no sponsor | Search ongoing. Interim coverage by CIO. | 94 | CRITICAL enabler. $94M in blocked value. Every month of delay costs the portfolio.
AI-004 | Epic Optimization Sprint | Robert Chen (CIO) | Planning — not started | 2.1 | 0.4 | 0 | 68% | F008 (61%) — training gap | 22 modules underutilized. Training completion 41%. No MLOps needed. | 12 | HIGH. $12M annual value. 8-week sprint. Internal capability sufficient with Maestro.
AI-005 | RCM Vendor Renegotiation (Ensemble) | James Park (CFO) | Active negotiation | 0.2 | 0.2 | 0 | N/A | F011 (74%) — vendor misalignment | $8M SLA penalties enforceable. Ensemble underperforming on denial rate. | 8 | ACT NOW. Leverage SLA breach. Cohere Health as competitive threat in negotiation.
AI-006 | Predictive Readmission Model | Dr. Sarah Kim (CMIO) | Concept — data not ready | 1.8 | 0.2 | 0 | 32% | F003 (68%) — data readiness | Epic data quality 58/100. Insufficient clean data for model training. Block until Epic optimized. | 6 | BLOCK. Prerequisite: Epic Optimization Sprint. Then fast to deploy with GenAI.
AI-007 | Travel Nurse Demand Forecasting | VP HR | In Development | 1.2 | 0.8 | 0 | 52% | F003 (68%) | Workforce data in 3 systems. Workday, manual spreadsheets, agency portal. | 8 | MEDIUM. $8M savings. Workforce data consolidation required first.
AI-008 | MA Star Rating AI | Emily Rodriguez (CEO) | Concept | 3.4 | 0.4 | 0 | 44% | F002 (84%) — no CDO | CDO hire prerequisite. Multiple quality measures need coordinated AI overlay. | 24 | BLOCK until CDO. $24M revenue at risk if star rating drops below 3.5.
AI-009 | Clinical Coding Automation | James Park (CFO) | Pilot | 2.8 | 1.9 | 0 | 61% | F006 (79%) | Coding AI pilot with 3M HIS. Accuracy 84% vs 96% required. Not production-ready. | 11 | CONTINUE PILOT. Target 96% accuracy before enterprise deployment.
AI-010 | Patient No-Show Prediction | Robert Chen (CIO) | In Development | 0.9 | 0.6 | 0 | 71% | F008 (61%) | Model trained on Epic scheduling data. Deployment blocked — no serving infrastructure. | 4 | QUICK WIN once MLOps infra live. Model ready. Infrastructure gap only.
AI-011 | Supply Chain AI (Stockout Prediction) | COO | Concept | 1.4 | 0.2 | 0 | 38% | F003 (68%) | Supply chain data in Infor and manual. No unified feed. | 3 | LOW priority. Data consolidation required. Defer to Wave 2.
AI-012 | Telehealth Triage AI | Dr. Sarah Kim (CMIO) | Concept | 2.2 | 0.3 | 0 | 42% | F002 (84%) | CDO required for clinical AI governance. No framework. | 8 | BLOCK until CDO and clinical AI governance established.
TOTALS | [5 empty] | 0