## MLOps Assessment
MERIDIAN HEALTH — MLOps Infrastructure Assessment
MLOps Capability | Current State | Maturity (0-5) | Initiatives Blocked | Effort to Fix | AWS Bedrock Status | Recommendation
Model Registry | No registry. Models tracked in spreadsheets by data scientists. | 0 | 8 | Medium — 2 months | Not configured | Implement MLflow on AWS. Link to Bedrock model catalog.
Feature Store | No feature store. Each model rebuilds features independently. | 0 | 6 | High — 3 months | Not configured | Start with Epic clinical features — highest demand across initiatives.
ML Pipeline / CI-CD | No ML CI-CD. Infrastructure pipeline exists (AWS CodePipeline) but not extended to ML. | 0 | 8 | Medium — 2 months | Partially available | Extend existing CodePipeline. Add model validation gate. 2-month effort.
Model Serving | No serving layer. Models run ad-hoc on analyst workstations. | 0 | 10 | Medium — 2 months | SageMaker available | Deploy SageMaker Endpoints. Containerise prior auth and GenAI models first.
Model Monitoring | No monitoring. No drift detection. No performance tracking. | 0 | 6 | Medium — 2 months | CloudWatch available | Implement using CloudWatch + custom metrics. Prior auth model first.
Experiment Tracking | Partial — 2 data scientists use MLflow locally. No shared server. | 1 | 5 | Low — 3 weeks | Not configured | Deploy shared MLflow server on EC2. Quick win — 3 weeks.
AWS Bedrock / GenAI | AWS Bedrock access configured. Foundation models available. No clinical fine-tuning. | 2 | 3 | Low — in progress | Active — POC stage | BEST ASSET. GenAI documentation and prior auth both viable. Prioritise.
Data Pipeline for ML | Manual Epic Clarity extracts. No automated clinical data pipeline for ML. | 0 | 9 | High — 4 months (Epic dependency) | Not configured | Epic Clarity automation + feature pipeline. Requires Epic cooperation.
HIPAA Compliance for AI | No AI-specific HIPAA framework. PHI in training data not governed. | 0 | 6 | High — requires CDO + Legal | Not assessed | CDO appointment prerequisite. Legal review of AI data handling required.
Model Validation (Clinical) | No clinical AI validation framework. FDA/ONC requirements undefined. | 0 | 5 | High — requires CDO + CMIO | Not assessed | Clinical AI governance framework required before production deployment.
Automated Retraining | No automated retraining. All models static after initial training. | 0 | 4 | Medium — 3 months | Not configured | Implement after serving layer. Prior auth model will drift as payer rules change.

## Priority Deployment Plan
MERIDIAN — AI Deployment Priority Sequence
Priority | Initiative | Prerequisite MLOps | Earliest Deploy | Annual Value ($M) | Notes
1 | GenAI Clinical Documentation (AWS Bedrock) | Serving layer only — Bedrock handles model | Month 2 | 42 | Fastest path. Bedrock ready. No training data required. Physician-facing.
2 | Prior Auth Automation (Cohere Health) | Serving layer + Epic integration | Month 3 | 37.6 | CMS mandate January 2027. Cohere Health manages the model. Epic API integration is the blocker.
3 | Patient No-Show Prediction | Serving layer only — model trained | Month 3 | 4 | Model already trained on Epic scheduling data. Serving layer is only blocker.
4 | Clinical Coding AI (3M HIS) | Serving layer + accuracy improvement | Month 5 | 11 | Pilot at 84% accuracy. Target 96%. Continue training while infrastructure built.
5 | Epic Optimization Sprint (all modules) | No MLOps needed — configuration only | Month 1 | 12 | First initiative to start. No AI/MLOps required. Pure Epic configuration and training.
6 | Predictive Readmission | Feature store + Epic data pipeline | Month 8 | 6 | Requires clean Epic data first. Epic Optimization Sprint prerequisite.
7 | Travel Nurse Forecasting | Feature store + workforce data pipeline | Month 6 | 8 | Workforce data consolidation required. Then standard ML pipeline.
8 | MA Star Rating AI | Full MLOps + CDO approval | Month 9 | 24 | CDO appointment and clinical AI governance prerequisite.